## Timeline
GOALS | STATUS | JANUARY | FEBRUARY | MARCH
January to March
Billboards | Spoke with Kofi 11/22/22 for proposal | 1/20/23 informed proposal is accepted. | 2/6/23 ARORP Approval, submitted to LAMAR | 3/6/23 Billboards start going up
| 12/1/22 new proposal received | 1/23/23 Panals secured
1/30/23 First Artwork/2nd artwork
Media | 11/18/22 Keli Williams for proposal | 1/9/23 moving forward with iHeart | 2/13/23 Kirk provides takeback info for script | 3/3/23 first recording
| 11/21/22 Proposal received, Bobby Bones agrees |  | 2/14/23 first draft | 3/3/23 changes from funder
| 12/5/22 changes made for diverse stations |  |  | 3/3/23 version 2 chosen, 30 sec spot sent
| 12/6/22 moving forward with iHeart |  |  | 3/7/23 updated version
3/8/23 updated 2nd version
3/9/23 request of takeback music track
3/9/23 another update
3/13/23 spots start
Stickers
|  |  | 2/6/23 called and emailed Pam Clements | 3/21/23 email from Pam with price again
|  |  | 2/8/23 Spoke with Pam Clements | 3/22/23 Ivory emailed Pam
|  |  | 2/8/23 sent a follow up email | 3/22/23 3 week turn around
|  |  | 2/8/23 spoke with Tenesha regarding blue stickers | 3/22/23 Ivory request 4/1/23
|  |  | 2/8/23 email regarding purple stickers, request for color purple to use | 3/23/23 Pam emails with no 4/1/23
2/8/23 purple sent
2/8/23 request for quote
2/10/23 price given
2/21/23 request for quote
Coins | 12/1/22 coin is requested by funder | 1/9/23 coin design sent to symbol art | 2/1/23 vendor follows up | 3/1/23 follow up on PO
| 12/1/22 request is made to symbol art | 1/12/23 mock-up sent | 2/6/23 requisition follow up | 3/3/23 PO issued
| 12/1/22 quotes for multiple levels | 1/20/23 Kirk likes design, call to confirm | 2/6/23 vendor sent paperwork to get in system | 3/6/23 coins in production
|  | 1/20/23 symbol art to discuss size | 2/21/23 follow up on PO | 3/22/23 coin arrival?
|  | 1/20/23 sizes back to funder | 2/21/23 paperwork back from vendor | 3/22/23 April 3
1/20/23 size is chosen
1/20/23 new pricing
1/23/23 new quote
1/24/23 funder approves
1/24/23 quote for requisition
Tablecloths
|  | 1/9/23 design sent to staples | 2/9/23 logo needs to be changed due to color scheme | 3/15/23 tablecloths delivered
|  | 1/10/23 quote received | 2/14/23 changes from funder
2/21/23 all logos back to staples
2/22/23 new art work
2/22/23 proof to funder
2/28/23 change in design from funder
2/28/23 changes to vendor
2/28/23 new artwork
2/28/23 new artwork approved by funder
TakeBack Boxes
| 12/1/22 quote received |  | 2/15/23 Bid Posted to procurement | 3/7/23 bid closed
3/20/23 intent to award
3/28/23 label to funders
Website
| 11/16/22 met with Lapero |  | 2/6/2023 Issues with invoicing not matching the proposal | 3/7/23 follow up on new proposal
| 11/30/22 first proposal |  | 2/10/23 requested invoices from Jordan to correct proposal | 3/7/23 new proposal
| 12/1/22 updated proposal |  | 2/15/23 spoke with Jordan to clear up some confusion | 3/8/23 wrong name on proposal
|  |  | 2/20/23 zoom with Coleen and Jordan | 3/17/23 follow up on changes
3/22/23 new proposal received
3/28/23 contract's meeting, wrong dates
3/28/23 request for proposal update

## Budget
UALR MidSOUTH Center for Prevention and Training (Agency) |  |  | ACTUALS
Arkansas Opioid Recovery Partnership
January 1, 2023 - December 31, 2023
Item | Expense Calculations
Salaries |  |  |  | Jan | Feb | Mar
Prevention Process Coordinator | 5% FTE @ $57,000 | 2850 |  |  | 237.5
Opioid Coordinator | 10% FTE @ $45,000 | 4500 |  |  | 0
Contracts Specialist | 5% FTE @ $40,000 | 2000 |  |  | 166.66
Finance Assistance | 2% FTE @ $67,500 | 1350 |  |  | 112.5
| Subtotal | 10700 |  | 0 | 516.66 | 0
Fringe | 32% Fringe Rate | 3424 |  |  | 184.57
Total Personnel |  | 14124
Maintenance/General Operations
LAPERO
Take Back Website Maintenance | Lapero hosting fee ($1500 per year) and 20 hours of TA ($3700) | 5200 | 4214
|  |  | Billboards | Media | Coins | Stickers | Tablecloths
Media Campaigns | Opioid Prevention campaigns | 148299 | 99891 | 45620 | 1493.84 | 1915 | 458.96 | 149378.8
American Standard
Take Back Boxes | 25 Take Back Boxes and shipping/graphics | 59650 | 60473.75
| Subtotal | 213149 | 214066.55
TOTAL DIRECT COSTS |  | 227273 |  |  | 14102.23
Indirect Costs | 10% of total direct costs | 22727 |  |  | 1410.25
TOTAL COSTS |  | 250000

## Takeback Boxes
American Security Cabinets
# | Agency | Location for Box | Contact | Email | Phone
1 | Stamps Police Department | 207 E. Antigo, Stamps, AR 71860 | Chief Orlando Dennis | Stampspd@outlook.com | 870-533-4951
2 | Faulkner County SO | 801 Locust street, Conway, AR 72034 | Sheriff Tim Ryals | tim.ryals@fcso.ar.gov
|  |  | Chelsea McDaniel | chelsea.mcdaniel@fcso.ar.gov | 501-450-4917
3 | Bonanza Police Department | 200 Sherwood Ave, Bonanza, AR 72916 | Chief Michael Barber | Bonanzapd@gmail.com
4 | Central City Police Department | 1101 West State HWY 255, Central City, AR 72941 | Chief Daymon Blount | blountslaw@gmail.com | 479-474-9044
5 | Tuckerman Police Department | 400 Hwy 367 South, Tuckerman, AR 72473 | Chief Justin Collom | chief@tuckermanpd.org | 870-512-9586
6 | Earle Police Department | 1004 2nd street, Earle, AR 72331 | Chief Johnathan Parks Sr. | ChiefEPDArk@outlook.com | 870-558-2690
7 | University of Arkansas Fort Smith PD | 425 N 51st Street, Fort Smith, AR 72903 | Lt Tiffany Johnson | Tiffany.Johnson@uafs.edu | 479-788-7480
8 | Pea Ridge Police Department | 187 Slack Street, Pea Ridge, AR 72751 | Chief Lynn Hahn | Lynn.hahn@cityofpearidgear.gov | 479-451-0328
9 | Sulphur Springs PD | 512 S Black Ave, Sulphur Springs, AR 72768 | Chief Jarod Morgan | Jmorgan@sulphurspringsar.gov
10 | Fayetteville PD | 100 West Rock Street, Fayetteville, AR 72701 | Chief Jamie Fields | jfields@fayetteville-ar.gov | 479-973-4844
11 | Guy Police Department | 405 AR-25, Guy, AR 72061 | Chief Humphrey | chumphreygpd@gmail.com
12 | Shannon Hills PD | 11610 County Line Rd. Alexander, AR 72002 | Chief Spears | shannonhillspdchief@aristotle.net
13 | Chidester Police Department | 118 Willow Street, Chidester, AR 71726 | Chief Jarrod Purifoy | Chidesterpd1@yahoo.com | 870-617-2230
| Box Sticker: | 3/29/23 - not approved yet
2

## Billboards
Billboards | 14388748
Lamar
March to April

## Media
iHeart | 53664 |  |  |  | 1. 8x per day :15 second spots on the back end of our Cash Contest Giveaway - runs through programming inventory so you will not have spot times or an invoice. I will send over air-checks for you to hear. Spots will run 3/27-4/21 on the following stations.
Market | Station | Schedule Date | Actual Date | Title | KHKN – Little Rock AR – Contemporary Hit Radio
Fort Smith | KMAG-FM | 2023-03-06 | 2023-03-06 | Bobby Bones influencer #2 | KIGL – Fayetteville – Classic Rock
Fort Smith | KMAG-FM | 2023-03-07 | 2023-03-07 | Bobby Bones influencer #2 | KMAG & KBZZ – Country & Hot Contemporary Radio
Fort Smith | KKBD-FM | 2023-03-07 | 2023-03-07 | 30 AR DRUG TAKE BACK-BOBBY_REV
Fort Smith | KMAG-FM | 2023-03-08 | 2023-03-08 | Bobby Bones influencer #2
Fort Smith | KKBD-FM | 2023-03-08 | 2023-03-08 | 30 AR DRUG TAKE BACK-BOBBY_REV
Fort Smith | KKBD-FM | 2023-03-08 | 2023-03-08 | 30 AR DRUG TAKE BACK-BOBBY_REV
Fort Smith | KKBD-FM | 2023-03-08 | 2023-03-08 | 30 AR DRUG TAKE BACK-BOBBY_REV
Fort Smith | KMAG-FM | 2023-03-09 | 2023-03-09 | Bobby Bones influencer #2
Fort Smith | KKBD-FM | 2023-03-09 | 2023-03-09 | 30 AR DRUG TAKE BACK-BOBBY_REV
Fort Smith | KKBD-FM | 2023-03-09 | 2023-03-09 | 30 AR DRUG TAKE BACK-BOBBY_REV
Fort Smith | KMAG-FM | 2023-03-10 | 2023-03-10 | Bobby Bones influencer #2
Fort Smith | KKBD-FM | 2023-03-10 | 2023-03-10 | 30 AR DRUG TAKE BACK-BOBBY_REV
Fort Smith | KKBD-FM | 2023-03-10 | 2023-03-10 | 30 AR DRUG TAKE BACK-BOBBY_REV
Fort Smith | KKBD-FM | 2023-03-10 | 2023-03-10 | 30 AR DRUG TAKE BACK-BOBBY_REV
Fort Smith | KMAG-FM | 2023-03-13 | 2023-03-13 | Bobby Bones influencer #2
Fort Smith | KKBD-FM | 2023-03-13 | 2023-03-13 | 30 AR DRUG TAKE BACK-BOBBY_REV
Fort Smith | KKBD-FM | 2023-03-13 | 2023-03-13 | 30 AR DRUG TAKE BACK-BOBBY_REV
Fort Smith | KKBD-FM | 2023-03-13 | 2023-03-13 | 30 AR DRUG TAKE BACK-BOBBY_REV
Fort Smith | KMAG-FM | 2023-03-14 | 2023-03-14 | Bobby Bones influencer #2
Fort Smith | KKBD-FM | 2023-03-14 | 2023-03-14 | 30 AR DRUG TAKE BACK-BOBBY_REV
Fort Smith | KKBD-FM | 2023-03-14 | 2023-03-14 | 30 AR DRUG TAKE BACK-BOBBY_REV
Fort Smith | KKBD-FM | 2023-03-14 | 2023-03-14 | 30 AR DRUG TAKE BACK-BOBBY_REV
Fort Smith | KMAG-FM | 2023-03-15 | 2023-03-15 | Bobby Bones influencer #2
Fort Smith | KKBD-FM | 2023-03-15 | 2023-03-15 | 30 AR DRUG TAKE BACK-BOBBY_REV
Fort Smith | KMAG-FM | 2023-03-16 | 2023-03-16 | Bobby Bones influencer #2
Fort Smith | KKBD-FM | 2023-03-16 | 2023-03-16 | 30 AR DRUG TAKE BACK-BOBBY_REV
Fort Smith | KKBD-FM | 2023-03-16 | 2023-03-16 | 30 AR DRUG TAKE BACK-BOBBY_REV
Fort Smith | KMAG-FM | 2023-03-17 | 2023-03-17 | Bobby Bones influencer #2
Fort Smith | KKBD-FM | 2023-03-20 | 2023-03-20 | 30 AR DRUG TAKE BACK-BOBBY_REV
Fort Smith | KMAG-FM | 2023-03-20 | 2023-03-20 | Bobby Bones influencer #2
Fort Smith | KKBD-FM | 2023-03-20 | 2023-03-20 | 30 AR DRUG TAKE BACK-BOBBY_REV
Fort Smith | KKBD-FM | 2023-03-20 | 2023-03-20 | 30 AR DRUG TAKE BACK-BOBBY_REV
Fort Smith | KKBD-FM | 2023-03-20 | 2023-03-20 | 30 AR DRUG TAKE BACK-BOBBY_REV
Fort Smith | KKBD-FM | 2023-03-20 | 2023-03-20 | 30 AR DRUG TAKE BACK-BOBBY_REV
Fort Smith | KKBD-FM | 2023-03-20 | 2023-03-20 | 30 AR DRUG TAKE BACK-BOBBY_REV
Fort Smith | KKBD-FM | 2023-03-20 | 2023-03-20 | 30 AR DRUG TAKE BACK-BOBBY_REV
Fort Smith | KKBD-FM | 2023-03-20 | 2023-03-20 | 30 AR DRUG TAKE BACK-BOBBY_REV
Fort Smith | KKBD-FM | 2023-03-20 | 2023-03-20 | 30 AR DRUG TAKE BACK-BOBBY_REV
Fort Smith | KMAG-FM | 2023-03-21 | 2023-03-21 | Bobby Bones influencer #2
Fort Smith | KMAG-FM | 2023-03-22
Fort Smith | KMAG-FM | 2023-03-23
Fort Smith | KMAG-FM | 2023-03-24
Fort Smith | KKBD-FM | 2023-03-27
Fort Smith | KMAG-FM | 2023-03-27
Fort Smith | KKBD-FM | 2023-03-27
Fort Smith | KMAG-FM | 2023-03-28
Fort Smith | KKBD-FM | 2023-03-28
Fort Smith | KMAG-FM | 2023-03-29
Fort Smith | KKBD-FM | 2023-03-29
Fort Smith | KKBD-FM | 2023-03-29
Fort Smith | KMAG-FM | 2023-03-30
Fort Smith | KKBD-FM | 2023-03-30
Fort Smith | KKBD-FM | 2023-03-30
Fort Smith | KKBD-FM | 2023-03-31
Fort Smith | KKBD-FM | 2023-03-31
Fayetteville | KKIX-FM | 2023-03-06 | 2023-03-06 | DRUGTAKEBACKBOBBYREV
Fayetteville | KMXF-FM | 2023-03-07 | 2023-03-07 | 30DRUGTAKEBACKBOBREV
Fayetteville | KKIX-FM | 2023-03-07 | 2023-03-07 | DRUGTAKEBACKBOBBYREV
Fayetteville | KMXF-FM | 2023-03-07 | 2023-03-07 | 30DRUGTAKEBACKBOBREV
Fayetteville | KKIX-FM | 2023-03-08 | 2023-03-08 | DRUGTAKEBACKBOBBYREV
Fayetteville | KMXF-FM | 2023-03-08 | 2023-03-08 | 30DRUGTAKEBACKBOBREV
Fayetteville | KMXF-FM | 2023-03-08 | 2023-03-08 | 30DRUGTAKEBACKBOBREV
Fayetteville | KMXF-FM | 2023-03-08 | 2023-03-08 | 30DRUGTAKEBACKBOBREV
Fayetteville | KKIX-FM | 2023-03-09 | 2023-03-09 | DRUGTAKEBACKBOBBYREV
Fayetteville | KMXF-FM | 2023-03-09 | 2023-03-09 | 30DRUGTAKEBACKBOBREV
Fayetteville | KMXF-FM | 2023-03-09 | 2023-03-09 | 30DRUGTAKEBACKBOBREV
Fayetteville | KMXF-FM | 2023-03-09 | 2023-03-09 | 30DRUGTAKEBACKBOBREV
Fayetteville | KKIX-FM | 2023-03-10 | 2023-03-10 | DRUGTAKEBACKBOBBYREV
Fayetteville | KMXF-FM | 2023-03-10 | 2023-03-10 | 30DRUGTAKEBACKBOBREV
Fayetteville | KMXF-FM | 2023-03-10 | 2023-03-10 | 30DRUGTAKEBACKBOBREV
Fayetteville | KKIX-FM | 2023-03-13 | 2023-03-13 | DRUGTAKEBACKBOBBYREV
Fayetteville | KMXF-FM | 2023-03-13 | 2023-03-13 | 30DRUGTAKEBACKBOBREV
Fayetteville | KMXF-FM | 2023-03-13 | 2023-03-13 | 30DRUGTAKEBACKBOBREV
Fayetteville | KMXF-FM | 2023-03-13 | 2023-03-13 | 30DRUGTAKEBACKBOBREV
Fayetteville | KMXF-FM | 2023-03-13 | 2023-03-13 | 30DRUGTAKEBACKBOBREV
Fayetteville | KKIX-FM | 2023-03-14 | 2023-03-14 | DRUGTAKEBACKBOBBYREV
Fayetteville | KKIX-FM | 2023-03-15 | 2023-03-15 | 60ARDRUGTBBOBBYREV
Fayetteville | KMXF-FM | 2023-03-15 | 2023-03-15 | 30ARDRUGTB-BOBBYREV
Fayetteville | KKIX-FM | 2023-03-16 | 2023-03-16 | 60ARDRUGTBBOBBYREV
Fayetteville | KMXF-FM | 2023-03-16 | 2023-03-16 | 30ARDRUGTB-BOBBYREV
Fayetteville | KKIX-FM | 2023-03-17 | 2023-03-17 | 60ARDRUGTBBOBBYREV
Fayetteville | KMXF-FM | 2023-03-18 | 2023-03-18 | 30ARDRUGTB-BOBBYREV
Fayetteville | KMXF-FM | 2023-03-18 | 2023-03-18 | 30ARDRUGTB-BOBBYREV
Fayetteville | KMXF-FM | 2023-03-18 | 2023-03-18 | 30ARDRUGTB-BOBBYREV
Fayetteville | KMXF-FM | 2023-03-18 | 2023-03-18 | 30ARDRUGTB-BOBBYREV
Fayetteville | KKIX-FM | 2023-03-20 | 2023-03-20 | 60ARDRUGTBBOBBYREV
Fayetteville | KMXF-FM | 2023-03-20 | 2023-03-20 | 30ARDRUGTB-BOBBYREV
Fayetteville | KMXF-FM | 2023-03-21 | 2023-03-21 | 30ARDRUGTB-BOBBYREV
Fayetteville | KMXF-FM | 2023-03-21 |  | 30ARDRUGTB-BOBBYREV
Fayetteville | KKIX-FM | 2023-03-21 |  | 60ARDRUGTBBOBBYREV
Fayetteville | KMXF-FM | 2023-03-21 |  | 30ARDRUGTB-BOBBYREV
Fayetteville | KMXF-FM | 2023-03-21 |  | 30ARDRUGTB-BOBBYREV
Fayetteville | KKIX-FM | 2023-03-22
Fayetteville | KMXF-FM | 2023-03-22
Fayetteville | KKIX-FM | 2023-03-23
Fayetteville | KMXF-FM | 2023-03-23
Fayetteville | KKIX-FM | 2023-03-24
Fayetteville | KMXF-FM | 2023-03-24
Fayetteville | KMXF-FM | 2023-03-25
Fayetteville | KMXF-FM | 2023-03-25
Fayetteville | KKIX-FM | 2023-03-27
Fayetteville | KMXF-FM | 2023-03-27
Fayetteville | KMXF-FM | 2023-03-27
Fayetteville | KKIX-FM | 2023-03-28
Fayetteville | KKIX-FM | 2023-03-29
Fayetteville | KMXF-FM | 2023-03-29
Fayetteville | KMXF-FM | 2023-03-29
Fayetteville | KKIX-FM | 2023-03-30
Fayetteville | KMXF-FM | 2023-03-30
Fayetteville | KMXF-FM | 2023-03-31
Fayetteville | KKIX-FM | 2023-03-31
Fayetteville | KMXF-FM | 2023-03-31
Fayetteville | KMXF-FM | 2023-03-31
Fayetteville | KMXF-FM | 2023-03-31
Little Rock | KSSN-FM | 2023-03-06 | 2023-03-06 | Bobby Bones influencer #2
Little Rock | KSSN-FM | 2023-03-07 | 2023-03-07 | Bobby Bones influencer #2
Little Rock | KDJE-FM | 2023-03-07 | 2023-03-07 | 30 AR DRUG TAKE BACK-BOBBY_REV
Little Rock | KDJE-FM | 2023-03-07 | 2023-03-07 | 30 AR DRUG TAKE BACK-BOBBY_REV
Little Rock | KSSN-FM | 2023-03-08 | 2023-03-08 | Bobby Bones influencer #2
Little Rock | KDJE-FM | 2023-03-08 | 2023-03-08 | 30 AR DRUG TAKE BACK-BOBBY_REV
Little Rock | KDJE-FM | 2023-03-08 | 2023-03-08 | 30 AR DRUG TAKE BACK-BOBBY_REV
Little Rock | KDJE-FM | 2023-03-09 | 2023-03-09 | 30 AR DRUG TAKE BACK-BOBBY_REV
Little Rock | KDJE-FM | 2023-03-09 | 2023-03-09 | 30 AR DRUG TAKE BACK-BOBBY_REV
Little Rock | KDJE-FM | 2023-03-09 | 2023-03-09 | 30 AR DRUG TAKE BACK-BOBBY_REV
Little Rock | KSSN-FM | 2023-03-10 | 2023-03-10 | Bobby Bones influencer #2
Little Rock | KDJE-FM | 2023-03-10 | 2023-03-10 | 30 AR DRUG TAKE BACK-BOBBY_REV
Little Rock | KSSN-FM | 2023-03-10 | 2023-03-10 | Bobby Bones influencer #2
Little Rock | KDJE-FM | 2023-03-10 | 2023-03-10 | 30 AR DRUG TAKE BACK-BOBBY_REV
Little Rock | KDJE-FM | 2023-03-10 | 2023-03-10 | 30 AR DRUG TAKE BACK-BOBBY_REV
Little Rock | KDJE-FM | 2023-03-13 | 2023-03-13 | 30 AR DRUG TAKE BACK-BOBBY_REV
Little Rock | KDJE-FM | 2023-03-13 | 2023-03-13 | 30 AR DRUG TAKE BACK-BOBBY_REV
Little Rock | KDJE-FM | 2023-03-13 | 2023-03-13 | 30 AR DRUG TAKE BACK-BOBBY_REV
Little Rock | KDJE-FM | 2023-03-13 | 2023-03-13 | 30 AR DRUG TAKE BACK-BOBBY_REV
Little Rock | KSSN-FM | 2023-03-14 | 2023-03-14 | Bobby Bones influencer #2
Little Rock | KSSN-FM | 2023-03-15 | 2023-03-15 | 60ARDRUGTBBOBBYREV
Little Rock | KDJE-FM | 2023-03-15 | 2023-03-15 | 30ARDRUGTB-BOBBYREV
Little Rock | KDJE-FM | 2023-03-15 | 2023-03-15 | 30ARDRUGTB-BOBBYREV
Little Rock | KSSN-FM | 2023-03-16 | 2023-03-16 | 60ARDRUGTBBOBBYREV
Little Rock | KSSN-FM | 2023-03-16 | 2023-03-16 | 60ARDRUGTBBOBBYREV
Little Rock | KDJE-FM | 2023-03-16 | 2023-03-16 | 30ARDRUGTB-BOBBYREV
Little Rock | KSSN-FM | 2023-03-17 | 2023-03-17 | 60ARDRUGTBBOBBYREV
Little Rock | KDJE-FM | 2023-03-17 | 2023-03-17 | 30ARDRUGTB-BOBBYREV
Little Rock | KDJE-FM | 2023-03-17 | 2023-03-17 | 30ARDRUGTB-BOBBYREV
Little Rock | KDJE-FM | 2023-03-18 | 2023-03-18 | 30ARDRUGTB-BOBBYREV
Little Rock | KSSN-FM | 2023-03-20 | 2023-03-20 | 60ARDRUGTBBOBBYREV
Little Rock | KSSN-FM | 2023-03-20 | 2023-03-20 | 60ARDRUGTBBOBBYREV
Little Rock | KDJE-FM | 2023-03-20 | 2023-03-20 | 30ARDRUGTB-BOBBYREV
Little Rock | KSSN-FM | 2023-03-21 | 2023-03-21 | 60ARDRUGTBBOBBYREV
Little Rock | KDJE-FM | 2023-03-21 |  | 30ARDRUGTB-BOBBYREV
Little Rock | KDJE-FM | 2023-03-21 |  | 30ARDRUGTB-BOBBYREV
Little Rock | KDJE-FM | 2023-03-21 |  | 30ARDRUGTB-BOBBYREV
Little Rock | KSSN-FM | 2023-03-22
Little Rock | KDJE-FM | 2023-03-22
Little Rock | KSSN-FM | 2023-03-23
Little Rock | KDJE-FM | 2023-03-23
Little Rock | KDJE-FM | 2023-03-25
Little Rock | KDJE-FM | 2023-03-25
Little Rock | KDJE-FM | 2023-03-25
Little Rock | KDJE-FM | 2023-03-25
Little Rock | KSSN-FM | 2023-03-27
Little Rock | KDJE-FM | 2023-03-27
Little Rock | KSSN-FM | 2023-03-28
Little Rock | KDJE-FM | 2023-03-28
Little Rock | KSSN-FM | 2023-03-29
Little Rock | KDJE-FM | 2023-03-29
Little Rock | KDJE-FM | 2023-03-29
Little Rock | KSSN-FM | 2023-03-30
Little Rock | KDJE-FM | 2023-03-30
Little Rock | KDJE-FM | 2023-03-30
Little Rock | KSSN-FM | 2023-03-31
Little Rock | KDJE-FM | 2023-03-31
Little Rock | KDJE-FM | 2023-03-31

## Website
Have had multiple issues with the contract with Lapero, still working to get this resolved.
Leadership tab is up-to-date
April takeback day is up-to-date
Contact information is up to date