## Sheet1
Organization: | HOPE MOVEMENT COALITION
Project Title: | YOU ARE NOT ALONE
Quarter: | 1st QUARTER
You are responsible for keeping track of receipts for all purchases for your agency’s records. You will not submit receipts to ARORP unless requested.
Category | Description | Annual Amount | Annual Amount Notes | Spent to Date | Spend to Date Notes | Amount Left to Spend | Plan to Spend | Does this plan align with project milestones?
Employee Salary | Exeuctive Director | 75000 | Salary set | 14423.1 | Salary $75k | 60576.9 | Pay salary for 3 additional quarters at $75k | Yes
Employee Salary | Operations Manager | 45000 | Salary range $40k to $45k | 8653.8 | Salary $45k | 36346.2 | Pay salary for 3 additional quarters at $45k | Yes
Employee Salary | Case Manager with experience | 58000 | Salary range $55k to $58k | 1561.54 | Salary $58k | 56438.46 | Pay salary for 3 additional quarters at $58k | Yes
Employee Salary | Case Manager with experience | 58000 | Salary range $55k to $58k | 0 | Salary $58k | 58000 | Pay salary for 3 additional quarters at $58k | Yes
Operating Equipment | 4 Laptops, 4 wireless mouse, 4 printers with scanning ability | 6480 | 4 laptops @ $1,500 each, 4 wireless mouse @ $40 each, 4 printers @ $80 each | 3622.9 | 4 laptops @ $1,500 each, 4 wireless mouse @ $40 each, 4 printers @ $80 each | 2857.1 | Needed equipment purchased, more may come up as we move forward | Yes
Operating Equipment/Office Supplies | Office Supplies | 4500 | All necessary essentials paper/pens/ink etc | 1016.18 | Will be adding on as needed | 3483.82 | Basic start up purchased for all employees, more will follow, as we move forward | Yes
Family retreat | Cause specific grief retreats prior to holiday season at no cost to families | 12500 | Stone Creek Ranch | 6896 | Retreat will be held in quarter 3. | 5604 | Milestone for quarter 4, deposit reuired due now to hold the date | Yes
Health Insurance for all employess | United Healthcare | 36000 | Health Insurance | 0 | 2 employees insurance will start 4/1 the 2 case managers will start 5/1/23 | 36000 | See notes below | Yes
Directors and Officers Insurance | Liabilty insurance for the board of directors and serve as liabilty insurance for any all all events and retreats | 1500 | Insurance | 698 |  | 802 | See notes below | Yes
Professional Errors and Omissions Insurance | Professional Insurance for case managers | 3500 | Insurance | 695 |  | 2805 | See notes below | Yes
Hired and Non Owned Vechile Insurance | Insurance to protect HMC should an employee be involved in an accident | 1200 | Insurance | 300 |  | 900 | See notes below | Yes
You Are Not Alone Launch event | Central Arkansas Library System | 6000 | Venue Rental | 1100 | 6/15/23 launch date set | 4900 | Milestone for quarter 2 deposit was required to hold the date | Yes
Travel | Exeuctive director & case managers | 44400 | Mileage reimburstment, overnight stays. | 1709.83 |  | 42690.17 | Will have an updated amount for quarter 2
Legal Services | Legal Services | 6000 | Retainer | 6000 | Employee handbook, review of contracts, unforseen need for council | $ - | Paid in full | Yes
| Annual Budget: | 358080 | Spent to Date: | 46676.35 | Amount Left to Spend: | 311403.65
Notes | Response from the insurance carrier. While we are excited the fact that we came in well under budget, we want to expand on why we were able to save so much money. The main contributing factor is the class code the UW (Underwriters) assigned to our risk. We made all estimations on the class code of Rehabilitation Facility. Thought the UW process and the many applications completed on behalf of your organizations, it was confirmed that the most accurate rating class code would be Professional Case Manager. This change in class codes accounted for half of the savings. In addition, we assumed of more counselors than you currently have employed. As you add this year and in the years to come, your rate will increase. This in crease is based off of the more people you have serving more families, the more you will be on the road, the more you will be in family’s homes. Basically, the more you do the more risk you assume