## Quarter 1
Organization: Craighead County Sheriffs Office
Project Title: Craighead County Sheriff’s Office ORT
Quarter: 1
Milestones were sent to each participant after receiving a notice of award. Please upload any supplemental materials through the quarterly reporting form.
Milestones | Status | Updates/Notes
Hire Law Enforcement Investigator | Complete | Investigator selected and began 03/07/23 at a salary of $48,296.00.
Hire Peer Specialist | Complete | Chris Beltran was hired and started on 04/16/2023 at a salary of $36,650.
Develop Recovery Support Program | Complete | Recovery support program launched 2/14/23. More information on services that have been provided in the data tracking tool.
Develop Educational Materials | Complete | Educational materials were completed 2/14/23. More information on educational material dispersal in the data tracking tool. Sample educational materials have been uploaded in the "Supplemental Materials" portion of the quarterly reporting form.
Develop Data tracking system | Complete | Uploaded into the quarterly reporting form
Submit first ARORP report | Not Complete | Submitted on 5/10/23