## Timeline
GOALS | STATUS | JANUARY | FEBRUARY | MARCH | April | May | June
Billboards | Spoke with Kofi 11/22/22 for proposal | 1/20/23 informed proposal is accepted. | 2/6/23 ARORP Approval, submitted to LAMAR | 3/6/23 Billboards start going up | 4/1/23 to 4/30/23 Billboards up through the end of the month
| 12/1/22 new proposal received | JANUARY: 1/23/23 Panals secured
1/30/23 First Artwork/2nd artwork
Media | 11/18/22 Keli Williams for proposal | 1/9/23 moving forward with iHeart | 2/13/23 Kirk provides takeback info for script | 3/3/23 first recording | 4/1/23 to 4/30/23 Radio Ads continue
| 11/21/22 Proposal received, Bobby Bones agrees | FEBRUARY: 2/14/23 first draft; MARCH: 3/3/23 changes from funder
| 12/5/22 changes made for diverse stations | MARCH: 3/3/23 version 2 chosen, 30 sec spot sent
| 12/6/22 moving forward with iHeart | MARCH: 3/7/23 updated version
3/8/23 updated 2nd version
3/9/23 request of takeback music track
3/9/23 another update
3/13/23 spots start
Stickers
|  |  | 2/6/23 called and emailed Pam Clements | 3/21/23 email from Pam with price again | 4/27/23 Stickers received at ARORP office per T Barnes
|  |  | 2/8/23 Spoke with Pam Clements | 3/22/23 Ivory emailed Pam
|  |  | 2/8/23 sent a follow up email | 3/22/23 3 week turn around
|  |  | 2/8/23 spoke with Tenesha regarding blue stickers | 3/22/23 Ivory request 4/1/23
|  |  | 2/8/23 email regarding purple stickers, request for color purple to use | 3/23/23 Pam emails with no 4/1/23
2/8/23 purple sent
2/8/23 request for quote
2/10/23 price given
2/21/23 request for quote
Coins | 12/1/22 coin is requested by funder | 1/9/23 coin design sent to symbol art | 2/1/23 vendor follows up | 3/1/23 follow up on PO | 4/18/23 Coins received by MidSOUTH
| 12/1/22 request is made to symbol art | 1/12/23 mock-up sent | 2/6/23 requisition follow up | 3/3/23 PO issued | 4/18/23 Ivory to delivery to ARORP office
| 12/1/22 quotes for multiple levels | JANUARY: 1/20/23 Kirk likes design, call to confirm; FEBRUARY: 2/6/23 vendor sent paperwork to get in system; MARCH: 3/6/23 coins in production
|  | 1/20/23 symbol art to discuss size | 2/21/23 follow up on PO | 3/22/23 coin arrival?
|  | 1/20/23 sizes back to funder | 2/21/23 paperwork back from vendor | 3/22/23 April 3
1/20/23 size is chosen
1/20/23 new pricing
1/23/23 new quote
1/24/23 funder approves
1/24/23 quote for requisition
Tablecloths
|  | 1/9/23 design sent to staples | 2/9/23 logo needs to be changed due to color scheme | 3/15/23 tablecloths delivered | 4/18/23 Ivory to delivery to ARORP office
|  | 1/10/23 quote received | 2/14/23 changes from funder
2/21/23 all logos back to staples
2/22/23 new art work
2/22/23 proof to funder
2/28/23 change in design from funder
2/28/23 changes to vendor
2/28/23 new artwork
2/28/23 new artwork approved by funder
TakeBack Boxes |  | April: First set of boxes delivered; June: Requested more locations for delivery 6/27/23
| 12/1/22 quote received | FEBRUARY: 2/15/23 Bid Posted to procurement; MARCH: 3/7/23 bid closed
3/20/23 intent to award
3/28/23 label to funders
Website |  | May: 5/23 Received information from Lapero
| 11/16/22 met with Lapero | FEBRUARY: 2/6/2023 Issues with invoicing not matching the proposal; MARCH: 3/7/23 follow up on new proposal; May: 5/23/23 Forward to Mandy at DAABHS
| 11/30/22 first proposal | FEBRUARY: 2/10/23 requested invoices from Jordan to correct proposal; MARCH: 3/7/23 new proposal
| 12/1/22 updated proposal | FEBRUARY: 2/15/23 spoke with Jordan to clear up some confusion; MARCH: 3/8/23 wrong name on proposal
|  |  | 2/20/23 zoom with Coleen and Jordan | 3/17/23 follow up on changes
3/22/23 new proposal received
3/28/23 contract's meeting, wrong dates
3/28/23 request for proposal update

## Budget
UALR MidSOUTH Center for Prevention and Training (Agency) |  |  | ACTUALS |  |  |  | ACTUALS
Arkansas Opioid Recovery Partnership
January 1, 2023 - December 31, 2023
Item | Expense Calculations
Salaries |  |  |  | Jan | Feb | Mar |  | April | May | June
Prevention Process Coordinator | 5% FTE @ $57,000 | 2612.51 |  |  | 237.5 | 237.5 |  | 237.51 | 237.5
Opioid Coordinator | 10% FTE @ $45,000 | 3732.95 |  |  | 0 | 357.95 |  | 375 | 375
Contracts Specialist | 5% FTE @ $40,000 | 1833.27 |  |  | 166.66 | 166.67 |  | 166.66 | 166.67
Finance Assistance | 2% FTE @ $67,500 | 1237.49 |  |  | 112.5 | 112.49 |  | 112.5 | 112.5
| Subtotal | 9416.22 |  | 0 | 516.66 | 874.61 |  | 891.67 | 891.67 | 0
Fringe | 32% Fringe Rate | 2978.76 |  |  | 184.57 | 274.19 |  | 278.41 | 278.4
Total Personnel |  | 12394.98 |  |  | 701.23 | 1148.8 |  | 1170.08 | 1170.07
Maintenance/General Operations
Take Back Website Maintenance | Lapero hosting fee ($1500 per year) and 20 hours of TA ($3700) | 4214
Media Campaigns | Opioid Prevention campaigns | 147937.08 |  |  | 13401 | 87421.38 |  | 1493.84
Take Back Boxes | 25 Take Back Boxes and shipping/graphics | 62726.94 | [5 empty] | 32617.92
| Subtotal | 214878.02 |  |  | 13401 | 87421.38 |  | 34111.76 | 0 | 0
TOTAL DIRECT COSTS |  | 227273 |  |  | 14102.23 | 88570.18 |  | 35281.84 | 1170.07 | 0
Indirect Costs | 10% of total direct costs | 22727 |  |  | 1410.25 | 8857.1 |  | 3528.26 | 117.04
TOTAL COSTS |  | 250000 |  |  | 15512.48 | 97427.28 |  | 38810.1 | 1287.11
.

## Takeback Boxes
American Security Cabinets
# | Agency | Location for Box | Contact | Email | Phone | Delivered
1 | Stamps Police Department | 207 E. Antigo, Stamps, AR 71860 | Chief Orlando Dennis | Stampspd@outlook.com | 870-533-4951
2 | Faulkner County SO | 801 Locust street, Conway, AR 72034 | Sheriff Tim Ryals | tim.ryals@fcso.ar.gov
|  |  | Chelsea McDaniel | chelsea.mcdaniel@fcso.ar.gov | 501-450-4917
3 | Bonanza Police Department | 200 Sherwood Ave, Bonanza, AR 72916 | Chief Michael Barber | Bonanzapd@gmail.com | 479-638-8649
4 | Central City Police Department | 1101 West State HWY 255, Central City, AR 72941 | Chief Daymon Blount | blountslaw@gmail.com | 479-474-9044
5 | Tuckerman Police Department | 400 Hwy 367 South, Tuckerman, AR 72473 | Chief Justin Collom | chief@tuckermanpd.org | 870-512-9586
6 | Earle Police Department | 1004 2nd street, Earle, AR 72331 | Chief Johnathan Parks Sr. | ChiefEPDArk@outlook.com | 870-558-2690
7 | University of Arkansas Fort Smith PD | 425 N 51st Street, Fort Smith, AR 72903 | Lt Tiffany Johnson | Tiffany.Johnson@uafs.edu | 479-788-7480
8 | Pea Ridge Police Department | 187 Slack Street, Pea Ridge, AR 72751 | Chief Lynn Hahn | Lynn.hahn@cityofpearidgear.gov | 479-451-0328
9 | Sulphur Springs PD | 512 S Black Ave, Sulphur Springs, AR 72768 | Chief Jarod Morgan | Jmorgan@sulphurspringsar.gov | 479-298-7773
10 | Fayetteville PD | 100 West Rock Street, Fayetteville, AR 72701 | Chief Jamie Fields | jfields@fayetteville-ar.gov | 479-973-4844
11 | Guy Police Department | 405 AR-25, Guy, AR 72061 | Chief Humphrey | chumphreygpd@gmail.com | 501-679-4585
12 | Shannon Hills PD | 11610 County Line Rd. Alexander, AR 72002 | Chief Spears | shannonhillspdchief@aristotle.net | 501-455-3125
13 | Chidester Police Department | 118 Willow Street, Chidester, AR 71726 | Chief Jarrod Purifoy | Chidesterpd1@yahoo.com | 870-617-2230
2
Check Box 4
Check Box 4
Check Box 4
Check Box 4
Check Box 4
Check Box 4
Check Box 4
Check Box 4
Check Box 4
Check Box 4
Check Box 4
Check Box 4
Check Box 4
Check Box 4

## Billboards
Billboards | 14388748
Lamar
March to April

## Media
iHeart | 53664 |  | 1. 8x per day :15 second spots on the back end of our Cash Contest Giveaway - runs through programming inventory so you will not have spot times or an invoice. I will send over air-checks for you to hear. Spots will run 3/27-4/21 on the following stations.
April:
KMAG & KBZZ – Country & Hot Contemporary Radio

## Website
Have had multiple issues with the contract with Lapero, still working to get this resolved.
Leadership tab is up-to-date
April takeback day is up-to-date
Contact information is up to date