|  |  |  |
| --- | --- | --- |
| **Organization: Sevier County Detention Center** |  |  |
| **Project Title: Sevier County RSAT/Community Outreach Program** |  |  |
| **Quarter: 1** |  |  |
| *Milestones were sent to each participant after receiving a notice of award. Please upload any supplemental materials through the quarterly reporting form.*  |  |  |
|  |  |  |
|  |  |  |
| **Quarter 1 Milestones** | **Status** | **Updates/Notes** |
| Hire 2 Program Coordinators | Complete | Eleuterio Hernandez started at ARORP on 5/01/23 at a salary of $37,502.00 and Ana Mejia started at ARORP on 05/01/23 art a salary of $37,502.00  |
| Hire 2 Full time Peer specialist and Hire 1 Part Time Peer specialist  | Complete | Lynette Hanley started at ARORP on 5/01/23 at a salary of $37,502.00 and Galena Gallardo started at ARORP on 5/01/23 at a salary of $37,502.00 and our Part time Terry Smith started at ARORP on 5/01/23 at a salary of $18,751.00 and Part time /fill-in/Extra Help for Program Coordinators for the amount of $6,000.00 |
| Update on services provided for incarcerated & outpatient participants | Complete | Drug testing, Community outreach, Metamorphosis counseling, Transitions counseling, Peer Recovery training, Educational classes,(Fatherhood classes, Adult education, Criminal thinking/mindset, Motherhood, Social poverty, Wages class, Career development, Substance abuse education, Narcotics anonymous, Celebrate recovery, Alcoholics anonymous, Anger management) |
| Update on staff training | Pending | Peer conference, state/county meetings, county/state conferences, peer/recovery meetings, Harbor house trainings meetings, and speaking engagements |
| Develop Data tracking system | Complete | Uploaded into the quarterly reporting form |
| Submit first ARORP report | Complete | Submitted on 7/01/23  |