## Timeline
GOALS | STATUS | JANUARY | FEBRUARY | MARCH | April | May | June | July | August | September | October | November | December
Billboards | Spoke with Kofi 11/22/22 for proposal | JANUARY: 1/20/23 informed proposal is accepted.; FEBRUARY: 2/6/23 ARORP Approval, submitted to LAMAR; MARCH: 3/6/23 Billboards start going up; April: 4/1/23 to 4/30/23 Billboards up through the end of the month; September: Sept 11. billboards up; October: Remain up through end of the month to ensure maximum coverage for take back day
| 12/1/22 new proposal received | JANUARY: 1/23/23 Panals secured; September: Sept 27, moving some locations to southern part of state
1/30/23 First Artwork/2nd artwork
Media | 11/18/22 Keli Williams for proposal | 1/9/23 moving forward with iHeart | 2/13/23 Kirk provides takeback info for script | 3/3/23 first recording | 4/1/23 to 4/30/23 Radio Ads continue |  |  |  | August 25, spoke with Keli Williams regarding new media | 9/11 start date | Spots run through end of the month to ensure maximum coverage for take back day |  | Final report and invoices paid.
| 11/21/22 Proposal received, Bobby Bones agrees | FEBRUARY: 2/14/23 first draft; MARCH: 3/3/23 changes from funder; August: August 25, spoke with Keli Williams regarding new media
| 12/5/22 changes made for diverse stations | MARCH: 3/3/23 version 2 chosen, 30 sec spot sent
| 12/6/22 moving forward with iHeart | MARCH: 3/7/23 updated version
3/8/23 updated 2nd version
3/9/23 request of takeback music track
3/9/23 another update
3/13/23 spots start
Stickers
|  |  | 2/6/23 called and emailed Pam Clements | 3/21/23 email from Pam with price again | 4/27/23 Stickers received at ARORP office per T Barnes
|  |  | 2/8/23 Spoke with Pam Clements | 3/22/23 Ivory emailed Pam
|  |  | 2/8/23 sent a follow up email | 3/22/23 3 week turn around
|  |  | 2/8/23 spoke with Tenesha regarding blue stickers | 3/22/23 Ivory request 4/1/23
|  |  | 2/8/23 email regarding purple stickers, request for color purple to use | 3/23/23 Pam emails with no 4/1/23
2/8/23 purple sent
2/8/23 request for quote
2/10/23 price given
2/21/23 request for quote
Coins | 12/1/22 coin is requested by funder | JANUARY: 1/9/23 coin design sent to symbol art; FEBRUARY: 2/1/23 vendor follows up; MARCH: 3/1/23 follow up on PO; April: 4/18/23 Coins received by MidSOUTH
| 12/1/22 request is made to symbol art | JANUARY: 1/12/23 mock-up sent; FEBRUARY: 2/6/23 requisition follow up; MARCH: 3/3/23 PO issued; April: 4/18/23 Ivory to delivery to ARORP office
| 12/1/22 quotes for multiple levels | JANUARY: 1/20/23 Kirk likes design, call to confirm; FEBRUARY: 2/6/23 vendor sent paperwork to get in system; MARCH: 3/6/23 coins in production
|  | 1/20/23 symbol art to discuss size | 2/21/23 follow up on PO | 3/22/23 coin arrival?
|  | 1/20/23 sizes back to funder | 2/21/23 paperwork back from vendor | 3/22/23 April 3
1/20/23 size is chosen
1/20/23 new pricing
1/23/23 new quote
1/24/23 funder approves
1/24/23 quote for requisition
Tablecloths
|  | 1/9/23 design sent to staples | 2/9/23 logo needs to be changed due to color scheme | 3/15/23 tablecloths delivered | 4/18/23 Ivory to delivery to ARORP office
|  | 1/10/23 quote received | 2/14/23 changes from funder
2/21/23 all logos back to staples
2/22/23 new art work
2/22/23 proof to funder
2/28/23 change in design from funder
2/28/23 changes to vendor
2/28/23 new artwork
2/28/23 new artwork approved by funder
TakeBack Boxes |  | April: First set of boxes delivered; July: July 14 is deadline for PD and Sheriff request for boxes; August: Columbia County box placement; October: 3 boxes shipped; December: made arrangements for ARORP to take over shipping containers through American Standard, final invoice received.
| 12/1/22 quote received | FEBRUARY: 2/15/23 Bid Posted to procurement; MARCH: 3/7/23 bid closed
3/20/23 intent to award
3/28/23 label to funders
Website |  | May: 5/23 Received information from Lapero; December: Spoke with Accounting to advise that MidSOUTH will no longer hold this contract with Lapero, have instructed them to reach out to ARORP for continued website hosting
| 11/16/22 met with Lapero | FEBRUARY: 2/6/2023 Issues with invoicing not matching the proposal; MARCH: 3/7/23 follow up on new proposal; May: 5/23/23 Forward to Mandy at DAABHS
| 11/30/22 first proposal | FEBRUARY: 2/10/23 requested invoices from Jordan to correct proposal; MARCH: 3/7/23 new proposal
| 12/1/22 updated proposal | FEBRUARY: 2/15/23 spoke with Jordan to clear up some confusion; MARCH: 3/8/23 wrong name on proposal
|  |  | 2/20/23 zoom with Coleen and Jordan | 3/17/23 follow up on changes
3/22/23 new proposal received
3/28/23 contract's meeting, wrong dates
3/28/23 request for proposal update