## Y1Q3(AugSeptOct)
Organization: Craighead County Sheriffs Office
Project Title: Craighead County Sheriff’s Office ORT
Year: 1
Quarter: 3
MIlestone Reporting Link
Milestones | Status | Updates/Notes
Identify key regional stakeholders and form relationships | Complete | The new investigator has met with each police chief within the region and formed a partnership in collecting overdose data.
Regional stakeholders and officers utilize ORT | Complete | The ORT has continued the utilization of the TruNarc when requested by local agencies.
ORT Tracking Database | Complete | Data is collected by PRS and Investigator and stored within Google sheets. A formula was placed within the date field to reminding the team to follow up with the Victim, Family, or Law Enforcement partner (if needed).
Submit 3rd ARORP report | Complete | Submitted Y1Q3 report on12/19/2023

## Y1Q2(MayJuneJuly)
Organization: Craighead County Sheriffs Office
Project Title: Craighead County Sheriff’s Office ORT
Year: 1
Quarter: 2
MIlestone Reporting Link
Milestones | Status | Updates/Notes
Six Month Goal Review: Goal 1 | Complete | "Establish an office and working space within the Craighead County Detention Facility to conduct meetings, training, and support for incoming inmates with substance abuse." Partnership established and an office was acquired.
Six Month Goal Review: Goal 2 | Complete | "Establish working space at NEA Divine Interventions in Jonesboro to conduct meetings, provide training, and support reentry for people suffering from substance abuse." Partnership established and an office was acquired.
Six Month Goal Review: Goal 3 | Complete | "Establish working relationships with participating members of criminal justice in an effort to provide education and reduce stigma for those suffering from substance disorder." Partnerships have been extablished, with the Cornors office, 2nd Judicial Drug Task Force, Jonesboro Police Department, and various other agencies.
ORT Tracking Database | Complete | Data is collected by PRS and Investigator and stored within Google sheets. A formula was placed within the date field to reminding the team to follow up with the Victim, Family, or Law Enforcement partner (if needed).
Investigator Training | Complete | ORT Investigator completed Criminal Justice Institute (CJI) Advanced Overdose Investigations course.
PRS Training | Complete | PRS completed and passed Peer Support Specialist Core test in May 2023.
Submit 2nd ARORP report | Complete | Submitted on 8/9/2023

## Y1Q1(FebMarApr)
Organization: Craighead County Sheriffs Office
Project Title: Craighead County Sheriff’s Office ORT
Year: 1
Quarter: 1
MIlestone Reporting Link
Milestones | Status | Updates/Notes
Hire Law Enforcement Investigator | Complete | Investigator selected and began 03/07/23 at a salary of $48,296.00.
Hire Peer Specialist | Complete | Chris Beltran was hired and started on 04/16/2023 at a salary of $36,650.
Develop Recovery Support Program | Complete | Recovery support program launched 2/14/23. More information on services that have been provided in the data tracking tool.
Develop Educational Materials | Complete | Educational materials were completed 2/14/23. More information on educational material dispersal in the data tracking tool. Sample educational materials have been uploaded in the "Supplemental Materials" portion of the quarterly reporting form.
Develop Data tracking system | Complete | Uploaded into the quarterly reporting form
Submit first ARORP report | Complete | Submitted on 5/10/23