## Sheet1
Organization: CADCA
Project Title: Phase II
Quarter: 3
You are responsible for keeping track of receipts for all purchases for your agency’s records. You will not submit receipts to ARORP unless requested.
Category | Description | Annual Amount | Annual Amount Notes | Spent to Date | Spend to Date Notes | Amount Left to Spend | Plan to Spend | Does this plan align with project milestones?
Staff Salaries and Wages | Training, Operations and Evaluation teams' salaries | 48179 | Training, Operations and Evaluation teams' salaries | 18191.89 | Salaries for teams to facilitate logistics/details leading up to and during all three weeks of OCA, as well as all three reinforcement webinars and both internal & partner meetings. | 29987.11 | NA | Yes
Fringe - 21.56% | Fringe | 10387 | Fringe | 3929.44 | Fringe: 21.56% | 6457.56 | Set Rate
Staff Travel | Staff Travel | 10704 | Staff Travel | 13548.22 | Deputy Director and Training Mgr travel to AR for Week 1 OCA and Vice President of Training Ops travel to AR for Week 3 OCA | -2844.22 | Travel to support current and future coalitions, if/as needed | Yes
Supplies | Supplies | 1200 | Supplies | 760.04 | Weeks 1 and 3 Training Supplies: Flip Charts, Markers, etc. + shipping of workbooks | 439.96 | NA | Yes
Contractual | Master Trainer - Curriculum Development | 36000 | Master Trainer - Curriculum Development | 45950 | Master Trainer - Curriculum Development Completion - 240 Hours | -9950 | NA | Yes
Contractual | Master Trainer - Training | 49000 | Master Trainer - Training; also added Cision, Arkansas Newsline | 50940 | Master Trainer - Training Weeks 1-3 + all three Reinforcement Webinars & CDS | -1940 | NA | Yes
Training Materials | Workbook Printing | 7500 | Workbook Printing | 7381.94 | Weeks 1 -3 Workbooks | 118.06 | NA | Yes
Trainer Travel | Travel to Arkansas | 8400 | Travel to Arkansas | 10562.48 | Two trainers travel to Arkansas for Weeks 1 and 3 Training | -2162.48 | NA--All travel completed | Yes
Learning Mgmt System | Learning Mgmt System | 1000 | Learning Mgmt System to facilitate training | 1000 | Docebo Setup for coalitions | 0 | NA | Yes
Graduation | Graduation at 2024 Forum | 1500 | Graduation at 2024 Forum | 2913.9 | Forum Graduation | -1413.9 | NA | Yes
MYTI Meeting Space | Orientation space | 3500 | Orientation space | 0 | Orientation event space at MYTI | 3500 | NA | Yes
Training Facility Rental | Venue Cost | 15000 | Venue Cost | 4572.97 | Week 1 and 3 training facility & AV setup | 10427.03 | NA-Venue rental for future meetings with current or future cohorts if/as needed | Yes
Indirect Costs | Indirect Costs | 19237 | Indirect Costs | 15975.1 | Indirect Costs: 10% | 3261.9 | Set Rate
| Annual Budget: | 211607 | Spent to Date: | 175725.98 | Amount Left to Spend: | 35881.02