## Sheet1
Annotated Milestones
Organization: | Wyoming Survey & Analysis Center at the University of Wyoming
Project Title: | Program Evaluation of the ARORP Project
Quarter: | For the 2024 Calendar Year
Milestones were sent to each participant after receiving a notice of award. Please copy and paste these milestones and due dates into the first and second columns. Please upload any supplemental materials through the quarterly reporting form.
Quarter 1 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Description (Please provide one to two sentence of description include details like who, what, where, when, and how).
EXAMPLE: Hire staff | EXAMPLE: January 1, 2024 | Yes | EXAMPLE: Jane Doe was hired into the Peer Position at ARORP on 2/28/23 at a salary of $55,000.
Work with ARORP staff to identify key process data measures | 2023-12-01 | Yes | We worked with ARORP to use milestones and other partner/grantee documentation to identify process measures for each type of project.
Develop a REDCap process data collection system | 2023-12-01 | Yes | The first version of the RedCAP system was created and presented to partners/grantees in early December.
Analyze and provide process data for ARORP quarterly and annual reports | 2023-12-01 | No | We began analyzing data, but the first quarterly report wasn't finalized until summer of 2024 and included data from January through June of 2024.
Research best practices in transparency evaluation | 2023-12-01 | Yes | We completed a literature review of transparency evaluation and included it in transparency evaluation plan.
Develop measures and tools for transparency evaluation | 2023-12-01 | Yes | The transparency evaluation tools and plan were completed in December 2024.
Work with ARORP staff to identify key outcome data measures | 2023-12-01 | Yes | Identified outcome measures were included in the ARORP evaluation plan completed in October 2023.
Contribute to the creation of ARORP quarterly and annual reports | 2023-12-01 | No | We worked with ARORP on process data collection and people served, but the first quarterly report covers January through June 2024. The annual report will cover the calendar year 2024 and wasn't created in December 2023.
Provide outcome data charts and graphs for ARORP quarterly and annual reports | 2023-12-01 | No | While we have a data spreadsheet with draft charts for the annual report, the outcome data will not be presented until the 2024 annual report.
Develop an ARORP evaluation plan | 2023-12-01 | Yes | The ARORP evaluation plan was completed in October 2023.
Submit first quarterly ARORP report | 2023-12-01 | No | The first quarterly report covers January through June 2024 because the RedCAP system was not due or ready for data entry until January 2024.
Quarter 2 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Update on collecting transparency evaluation data | 2024-03-01 | Yes | The first transparency evaluation reporting took place in January 2024, and a fact sheet was created in February 2024.
Analyze and provide process data for ARORP quarterly and annual reports | 2024-03-01 | Yes | We began analyzing process data and were able to provide data to ARORP, but the first quarterly report was published in the summer of 2024. It covers January through June 2024.
Provide outcome data charts and graphs for ARORP quarterly and annual reports | 2024-03-01 | No | While we have a data spreadsheet with draft charts for the annual report, the outcome data will not be presented until the 2024 annual report.
Submit quarterly ARORP report | 2024-03-01 | Yes | The first quarterly report covers January through June 2024, which includes this period. However, after creating the template and finalizing the RedCAP system, it was not complete until summer 2024.
Quarter 3 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Update on collecting transparency evaluation data | 2024-06-01 | No | The transparency scoring did not take place this quarter. It happens every six months.
Analyze and provide process data for ARORP quarterly and annual reports | 2024-06-01 | Yes | The first quarterly report covered January through June 2024, and the first draft was completed in June 2024. It was presented to the Board of Directors in September 2024.
Provide outcome data charts and graphs for ARORP quarterly and annual reports | 2024-06-01 | No | While we have a data spreadsheet with draft charts for the annual report, the outcome data will not be presented until the 2024 annual report.
Submit quarterly ARORP report | 2024-06-01 | Yes | The first quarterly report covered January through June 2024, and the first draft was completed in June 2024. It was presented to the Board of Directors in September 2024.
Quarter 4 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Update on collecting transparency evaluation data | 2024-09-01 | Yes | The transparency scoring was completed a second time in July 2024 with an accompanying fact sheet. However, there are issues with the scoring and we are looking into improving the process for accuracy and reliability.
Analyze and provide process data for ARORP quarterly and annual reports | 2024-09-01 | Yes | We presented the January through June 2024 quarterly report to the Board of Directors and will create the July through September 2024 quarterly report in October.
Provide outcome data charts and graphs for ARORP quarterly and annual reports | 2024-09-01 | No | While we have a data spreadsheet with draft charts for the annual report, the outcome data will not be presented until the 2024 annual report.
Attend annual ARORP evaluation meeting | Scheduled by ARORP | Yes | Attended September 26 as scheduled by ARORP.
Submit annual ARORP report | 2024-09-01 | No | We decided to create the annual report on a calendar year basis as partners move to regular fiscal quarters and to better align with the 2024 calendar year. Data and information for the annual report has been collected throughout the year, and the report should be completed in January 2025.