## Sheet1
Annotated Milestones
Organization: Hot Springs School District
Project Title: Peer Prevention
Quarter: 4
Milestones were sent to each participant after receiving a notice of award. Please copy and paste these milestones and due dates into the first and second columns. Please upload any supplemental materials through the quarterly reporting form.
Quarter 1 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Description (Please provide one to two sentence of description include details like who, what, where, when, and how).
Hire Law Enforcement Investigator | Prior to March 1, 2024 | yes | Jason Graves started at HSSD on 01/08/2024 at a salary of $47,700
Hire Peer specialist | Prior to March 1, 2024 | yes | Anthony Tidwell started at HSSD on 01/08/2024 at a salary of $40,000
Begin the Associate Preventionist and Peer Recovery Support Specialist Training | Prior to March 1, 2024 | yes | Tidwell currently is a Certified Prevention Specialist
Launch Program | Prior to March 1, 2024 | yes | TruNarc has been purchased but we has not been received nor has training began. Coalitions have been formed on multiple campuses. One-on-one and small group trainings have been developed (01/24/2024). Drug Take Back is scheduled for 04/27/2024.
Develop Data tracking system | Prior to March 1, 2024 | yes | 01/18/2024 developed data tracking
Submit first ARORP report | By March 1, 2024 | yes | Submitted on 03/29/24
Quarter 2 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Provide update on prevention and recovery efforts | Prior to June 1, 2024 | yes | Services were provided
Submit Quarterly ARORP report | By June 1,2024 | yes | Submitted 04/11/2024
Quarter 3 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Provide update on prevention and recovery efforts | Prior to October 1, 2024 | yes | Services were provided
Submit Quarterly ARORP report | By October 1, 2024 | yes | Submitted 10/31/24
Quarter 4 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Provide update on prevention and recovery efforts | Prior to December 1, 2024 | yes | Services were provided
Attend annual ARORP evaluation meeting | Prior to December 1, 2024 |  | 2024-11-04
Submit annual ARORP report | By December 1, 2024 | yes | Submitted 11/0/324