## Sheet1
Annotated Milestones
Organization: Hope's Bridge
Project Title: Hope's Bridge Housing
Quarter: 4
Milestones were sent to each participant after receiving a notice of award. Please copy and paste these milestones and due dates into the first and second columns. Please upload any supplemental materials through the quarterly reporting form.
Quarter 1 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Description (Please provide one to two sentence of description include details like who, what, where, when, and how).
EXAMPLE: Hire staff | EXAMPLE: January 1, 2024 | Yes | EXAMPLE: Jane Doe was hired into the Peer Position at ARORP on 2/28/23 at a salary of $55,000.
Purchase property | Prior to September 1, 2023 | Yes | Property purchased on 6/2/23
Open facility | Prior to September 1, 2023 | Yes | Facility opened for residents on 8/1/23
Launch peer services | Prior to September 1, 2023 | Yes | Peer services launched on 8/1/23
Develop data tracking system | Prior to September 1, 2023 | Yes | Good Grid to be implemented
Submit first quarterly ARORP report | 2023-09-01 | Yes | Submitted on 8/28/23
Quarter 2 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Operate recovery house at full capacity | Prior to December 1, 2023 | Yes | Completed 9/1/23
Submit quarterly ARORP report | 2023-12-01 | Yes, late | Submitted to new Redcap on 4/1/24
Quarter 3 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Submit quarterly ARORP report | 2024-03-01 | Yes, late | Submitted to new Redcap on 4/1/24
Quarter 4 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Attend annual ARORP evaluation meeting | 2024-06-01 | Yes | Missed original appointment scheduled July 22. Rescheduled for July 29th.
Submit annual ARORP report | 2024-06-01 | Yes, late | Completed July 22, 2024.