## Sheet1
John 3:16 Ministries
John 3:16 40 resident multipurpose housing
Quarter: 4
Category | Description | Annual Amount | Annual Amount Notes | Spend to Date | Spend to Date Notes | Amount Leftover
Building | Pinnacle Structures 80X200 | 450000 | Building and second floor materials | 453878.36 | Completed | -3878.36
Dirt Work | Preparation for building | 20990.9 | Excavation and materials for foundation and landscaping | 126149 | Completed | -105158.1
Foundation | Rebar Anchors and Concrete | 109855.54 | Concrete and materials for foundation | 199953.9 | Completed | -90098.36
Retaining Wall | Blocks Mortar and Cells Filled | 46424.95 | Block and materials for retaining wall | 69426.9 | Completed | -23001.95
Plumbing | Water Main, Water, Septic, and Gas | 529531.24 | Water main and all utilities for housing | 302208.32 | Completed | 227322.92
HVAC | Air Condition Units and Duct Work | 296994.38 | Charlie Wade to provide and install HVAC equipment | 257309.97 | Completed | 39684.41
Electric | Rough In, Trim Out, and Main Panel | 308340.96 | RGB to provide and install electrical equipment | 485572.45 | Completed | -177231.49
Metal Stud Framing and Sheetrock | Metal Studs Framing and Sheetrock | 122725.7 | Metal studs and sheetrock for the construction of the walls | 76123.29 | Completed | 46602.41
Drop Ceiling | Drop Ceiling | 59709.1 | Ceiling material for building | 1594.91 | Completed | 58114.19
Kitchen | Kitchen Appliances and Counter Door | 87344.68 | Comercial kitchen and material | 100465.17 | Completed | -13120.49
Walk-in Coolers | 2 10X10 Walk-in Coolers | 47313.2 | 2 walk-in coolers | 36010.44 | Completed | 11302.76
Paint | Paint for Walls | 20904.41 | Interior paint for walls | 17109.69 | Completed | 3794.72
Stairs and Handrails | Metal Stairs and Handrail around Building | 7729.7 | Inside and outside stairs with handrails around building | 14395.33 | Completed | -6665.63
Stained Concrete | First and Second Floor Stain | 42012.14 | Floor covering for building | 12211.04 | Completed | 29801.1
Finished Carpentry | Showers, Bathroom Pertitions, Cabinetry | 158599.2 | Materials for bathrooms and showers | 255149.38 | Completed | -96550.18
Glass Frontage and Windows | Storefront Doors and Windows | 49436 | Exterior doors and windows | 43092 | Completed | 6344
| Annual Budget: | 2357912.1 | Spent to Date: | 2450650.15 | Amount left to spend: | -92738.05 | -92738.05
Added to plumbing $15,583.73 (miller-newell) and 9,000 (white river construction) that does not reflect in the totals
17

## Building
Building
Pinnacle Structures | 2023-08-02 | 59973
Home Depot | 2023-10-01 | 400.4
Home Depot | 2023-10-05 | 421.27
Home Depot | 2023-10-08 | 749.8
Home Depot | 2023-10-15 | 110.2
Home Depot | 2023-10-18 | 421.36
Home Depot | 2023-10-22 | 26.88
Pinnacle Structures | 2023-10-23 | 263881
Home Depot | 2023-11-06 | 142.05
Home Depot | 2023-11-30 | 105.2
Home Depot | 2023-12-03 | 151.34
Home Depot | 2023-12-10 | 52.94
Home Depot | 2023-12-28 | 1036.75
Home Depot | 2023-12-31 | 249
Metal Roofing Supply | 2024-01-09 | 130.14
Tripp Supply | 2024-01-16 | 510.83
Home Depot | 2024-01-21 | 89.98
Home Depot | 2024-02-05 | 146.19
Tool Central | 2024-02-05 | 46.16
Home Depot | 2024-02-07 | 3107.26
Home Depot | 2024-02-12 | 2180.12
Home Depot | 2024-02-13 | 59.68
Home Depot | 2024-02-15 | 33
Tractor Supply | 2024-02-15 | 46.2
Home Depot | 2024-02-20 | 11007.92
Home Depot | 2024-02-25 | 423.32
Pinnacle Structures | 2024-02-26 | 528.83
Pinnacle Structures | 2024-02-29 | 105.19
Home Depot | 2024-02-29 | 406.56
Sanders Supply | 2024-03-04 | 199.06
Home Depot | 2024-03-20 | 370.7
All Steel Construction | 2024-03-25 | 60000
Home Depot | 2024-03-26 | 31.42
Hedge's | 2024-04-01 | 91.81
Pinnacle Structures | 2024-04-03 | 940.68
Home Depot | 2024-04-05 | 185.03
Hatfield Ready Mix | 2024-04-09 | 1360.8
Home Depot | 2024-04-10 | 142.07
Stubbs | 2024-04-11 | 155.92
Metal Roofing Supply | 2024-04-29 | 477.9
Hedge's | 2024-05-06 | 91.81
Bartons | 2024-05-06 | 373.9
Home Depot | 2024-05-22 | 965.79 | MC
Hedge's | 2024-06-03 | 91.81
Home Depot | 2024-06-08 | 965.8 | MC
Home Depot | 2024-06-19 | 177.94 | MC
Home Depot | 2024-06-19 | 285.14 | MC
Hedge's | 2024-06-27 | 91.81
Home Depot | 2024-07-12 | 50.12 | MC
Hedge's | 2024-08-01 | 91.81
Amazon | 2024-08-01 | 186.55 | MC
Home Depot | 2024-08-01 | 84.15 | MC
Home Depot | 2024-08-02 | 33.43 | MC
Home Depot | 2024-08-02 | 45.28 | MC
Amazon | 2024-08-12 | 386.4 | MC
Amazon | 2024-08-13 | 377.8 | MC
Amazon | 2024-08-13 | 632.27 | MC
Home Depot | 2024-08-13 | 603.14 | MC
Home Depot | 2024-08-15 | 378.64 | MC
Grimco | 2024-08-19 | 2550.21
Advanced Plastics | 2024-08-19 | 173.75
Grimco | 2024-08-21 | 124.74
101 Mobility, LLC | 2024-09-18 | 5241.8
Hanks | 2024-09-23 | 21505.8
Hedges | 2024-09-04 | 91.81
Woodson & Bozeman | 2024-09-11 | 4297.79
Stubbs | 2024-08-26 | 1913.13
Halbert Pipe & Steel | 2024-08-22 | 1053.01
Halbert Pipe & Steel | 2024-09-04 | 514.77
. | TOTAL
453878.36

## Dirt Work
Dirt Work
Riggs | 2024-01-04 | 122178.44
Bradley Contracting, Inc | 2024-01-08 | 514.69
Midwest Lime Company | 2024-04-30 | 455.87
Gibson Construction LLC | 2024-06-03 | 3000
| TOTAL | 126149

## Foundation
Foundation
Barton's | 2023-08-31 | 203.96
JMS | 2023-09-28 | 4217.7
Hatfield Ready Mix | 2023-10-09 | 32527.98
JMS | 2023-10-11 | 2592
Tool Central | 2023-10-12 | 973.57
Walmart | 2023-10-15 | 230.56
Hatfield Ready Mix | 2023-10-16 | 32858.09
Tripp Supply | 2023-10-17 | 255.41
Nettleton Concrete | 2023-10-17 | 3026.63
JMS | 2023-10-18 | 2835.01
Hatfield Ready Mix | 2023-10-23 | 10107.28
Barton's | 2023-10-25 | 5296.53
Nettleton Concrete | 2023-10-25 | 2217
Hatfield Ready Mix | 2023-10-30 | 7580.46
Nettleton Concrete | 2023-10-30 | 1814.06
Tripp Supply | 2023-11-07 | 6.83
Hatfield Ready Mix | 2023-11-14 | 2741.06
Halbert Pipe & Steel | 2024-01-10 | 6861.02
Halbert Pipe & Steel | 2024-01-23 | 2134.08
Halbert Pipe & Steel | 2024-01-23 | 43.74
Hatfield Ready Mix | 2024-01-24 | 447.12
Hatfield Ready Mix | 2024-01-24 | 27901.8
Roy Casady | 2024-01-24 | 7500
Nettleton Concrete | 2024-01-25 | 5065.16
Barton's | 2024-01-31 | 2048.98
Hatfield Ready Mix | 2024-02-05 | 745.2
Hatfield Ready Mix | 2024-08-31 | 907.2
Littlefield | 2024-06-03 | 2992.07
Littlefield | 2024-06-03 | 4154.47
Littlefield | 2024-06-03 | 3653.9
Littlefield | 2024-06-03 | 4473.59
Littlefield | 2024-05-01 | 2568.5
Littlefield | 2024-05-01 | 4044.05
Littlefield | 2024-05-01 | 3770.28
Littlefield | 2024-04-01 | 3456.81
Littlefield | 2024-04-01 | 2241.27
Littlefield | 2024-04-01 | 3352.32
Littlefield | 2024-04-01 | 2108.21
| TOTAL | 199953.9

## Retaining Wall
Retaining Wall
JMS | 2023-06-06 | 2625
Nettleton Concrete | 2023-06-19 | 4028.14
Nettleton Concrete | 2023-06-22 | 4712.07
Hatfield Ready Mix | 2023-06-23 | 13686.88
Nettleton Concrete | 2023-06-27 | 4311.94
Hatfield Ready Mix | 2023-06-28 | 518.4
Nettleton Concrete | 2023-06-29 | 6106.92
JMS | 2023-06-29 | 2835.01
Nettleton Concrete | 2023-06-30 | 4101.34
Hatfield Ready Mix | 2023-07-02 | 414.72
Home Depot | 2023-07-02 | 1012.13
Home Depot | 2023-07-09 | 751.86
Harbor Freight | 2023-07-09 | 219.97
Hatfield Ready Mix | 2023-07-10 | 996.03
Home Depot | 2023-07-16 | 12.57
Buchheit | 2023-07-19 | 177.21
Hatfield Ready Mix | 2023-07-20 | 1151.55
Home Depot | 2023-07-23 | 443.81
Tripp Supply | 2023-07-28 | 504.86
Hatfield Ready Mix | 2023-07-31 | 1372.28
Hatfield Ready Mix | 2023-07-31 | 1151.55
Midwest Lime Co | 2023-08-01 | 1168.02
JMS | 2023-08-02 | 3047.22
Nettleton Concrete | 2023-08-04 | 585.63
Midwest Lime Co | 2023-08-09 | 1146.64
Amazon | 2023-08-16 | 67.05
Hatfield Ready Mix | 2023-08-16 | 2072.26
Bradley Contracting | 2023-08-21 | 496.57
JMS | 2023-08-30 | 6428.16
Hatfield Ready Mix | 2023-09-04 | 1263.6
Hatfield Ready Mix | 2023-09-07 | 600
JMS | 2023-09-07 | 1417.51
| TOTAL | 69426.9

## Plumbing
Plumbing
Tripp Supply | 2023-08-17 | 1050.83
Albert Bland Plumbing | 2023-08-22 | 2540.4
Albert Bland Plumbing | 2023-09-13 | 4482.95
White River Construction | 2023-09-15 | 1000
AR DOT | 2023-09-25 | 1000
Nettleton Concrete | 2023-10-10 | 2918.69
White River Construction | 2023-12-05 | 9000
Core & Main | 2023-12-07 | 79667.28
Core & Main | 2023-12-07 | 28039.63
Core & Main | 2023-12-11 | 1086.35
Core & Main | 2023-12-11 | 1109.02
Core & Main | 2023-12-11 | 1159.61
Core & Main | 2023-12-18 | 987.12
Tripp Supply | 2023-12-20 | 15.53
Tri-County Supply | 2023-12-21 | 192.98
Tripp Supply | 2023-12-27 | 43.59
Interstate Tapping | 2024-01-01 | 500
Core & Main | 2024-01-01 | 6836.49
Core & Main | 2024-01-03 | 54.29
Tripp Supply | 2024-01-03 | 123.32
Scott Clark | 2024-01-18 | 1500
Henard Utility | 2024-01-19 | 5727.87
Core & Main | 2024-02-05 | 1558.72
Core & Main | 2024-02-15 | 345.5
Core & Main | 2024-02-21 | 216.81
Core & Main | 2024-02-26 | 1760.94
Tripp Supply | 2024-02-26 | 185.35
Tripp Supply | 2024-03-06 | 102.94
Tripp Supply | 2024-03-18 | 36.67
Home Depot | 2024-03-24 | 3112.63
Albert Bland Plumbing | 2024-03-27 | 7698.41
Home Depot | 2024-04-02 | 316.65
Home Depot | 2024-04-03 | 290.25
Home Depot | 2024-04-09 | 5511.91
Home Depot | 2024-04-12 | 43.63
Tripp Supply | 2024-04-15 | 133.82
White River Construction | 2024-04-15 | 2600
Home Depot | 2024-04-16 | 2657.78
Albert Bland Plumbing | 2024-04-24 | 31758.97
Core & Main | 2024-04-29 | 79.33
White River Construction | 2024-05-13 | 2600
Miller-Newell | 2024-05-13 | 15583.73
Earthtech, Inc. | 2024-05-31 | 2000
Tripp Supply | 2024-06-05 | 1115.19
Scott Clark | 2024-06-12 | 12247.2
Albert Bland Plumbing | 2024-06-20 | 692.18
Scott Clark | 2024-07-11 | 206.23
Albert Bland Plumbing | 2024-07-15 | 6500
Core & Main | 2024-07-17 | 1927.25
Home Depot | 2024-07-21 | 111.29
Scott Clark | 2024-07-29 | 8855
Tripp Supply | 2024-07-29 | 952.41
Home Depot | 2024-07-29 | 191 | MC
Tripp Supply | 2024-07-30 | 2285.01
Home Depot | 2024-07-31 | 9.55 | MC
Tripp Supply | 2024-08-02 | 132.14
Tripp Supply | 2024-08-15 | 540.75
Tripp Supply | 2024-08-21 | 136.58
OnPoint Drilling and Trenching | 2024-07-22 | 29800
Home Depot | 2024-08-05 | 106.35
Ferguson | 2024-09-10 | 399.06
Core & Main | 2024-09-23 | 1248.91
Tripp Supply | 2024-09-09 | 3298.53
Scott Clark | 2024-09-09 | 3806
Tripp Supply | 2024-09-04 | 17.7
| Total | 302208.32

## HVAC
HVAC
Stubbs | 2024-05-01 | 1436.72
Wades Heating Cooling & Electric | 2024-05-14 | 188300
Home Depot | 2024-07-16 | 198.25 | MC
Wades Heating Cooling & Electric | 2024-09-30 | 67375
| TOTAL | 257309.97

## Electrical
Electrical
RGB | 2023-10-23 | 45800
RGB | 2023-12-20 | 45800
RGB | 2024-02-20 | 91600
RGB | 2024-03-20 | 45800
RGB | 2024-04-22 | 62075
Home Depot | 2024-05-03 | 3.56
RGB | 2024-06-19 | 48512.5
RGB | 2024-07-22 | 48512.5
Tri-County Supply | 2024-08-14 | 430.38
Tri-County Supply | 2024-08-19 | 13.51
RGB | 2024-09-23 | 48512.5
RGB | 2024-08-28 | 48512.5
| TOTAL | 485572.45

## Metal Stud Framing Sheetrock
Metal Stud Framing/ Sheetrock
Campbell Acoustical & Drywall | 2024-02-26 | 37239.3
Campbell Acoustical & Drywall | 2024-03-28 | 23484.79
Stubbs | 2024-04-03 | 312.85
Stubbs | 2024-04-11 | 1321.42
Home Depot | 2024-04-30 | 1668.29
Stubbs | 2024-05-07 | 95
Home Depot | 2024-05-08 | 1331.61
Stubbs | 2024-05-15 | 698.02
Home Depot | 2024-06-03 | 315.66 | MC
Home Depot | 2024-06-04 | 69.72 | MC
Home Depot | 2024-06-06 | 248.16 | MC
Home Depot | 2024-06-06 | 402.51 | MC
Home Depot | 2024-06-08 | 59.93 | MC
Home Depot | 2024-06-09 | 362.99 | MC
Home Depot | 2024-06-12 | 38.81 | MC
Home Depot | 2024-06-14 | 798.6 | MC
Home Depot | 2024-06-18 | 221.1 | MC
Home Depot | 2024-06-25 | 937.86 | MC
Home Depot | 2024-06-28 | 702.9 | MC
Home Depot | 2024-07-05 | 716.96 | MC
Home Depot | 2024-07-14 | 46.99 | MC
Home Depot | 2024-07-26 | 4670.45 | MC
Home Depot | 2024-07-28 | 305.56 | MC
Home Depot | 2024-07-29 | 73.81 | MC
| TOTAL | 76123.29

## Drop Ceiling
Drop Ceiling
Home Depot | 2024-07-05 | 1354.72 | MC
Home Depot | 2024-07-05 | 47.98 | MC
Home Depot | 2024-07-14 | 122.98 | MC
Home Depot | 2024-07-15 | 69.23 | MC
| Total | 1594.91
1594.91

## Kitchen
Kitchen
Webstaurant | 2024-03-04 | 29927.87
Webstaurant | 2024-03-05 | 5915.27
Sweetwater | 2024-06-06 | 35935.13
Sweetwater | 2024-06-17 | 1861.89 | MC
Amazon | 2024-06-19 | 3002.1 | MC
Sweetwater | 2024-06-29 | 1062.79 | MC
Sweetwater | 2024-07-10 | 1240.88 | MC
Amazon | 2024-07-14 | 142.62 | MC
Stage Audio Electronics | 2024-07-16 | 120 | MC
Webstaurant | 2024-07-22 | 4933.05 | MC
Home Depot | 2024-07-26 | 191.01 | MC
Amazon | 2024-07-26 | 150.12 | MC
Amazon | 2024-07-26 | 135.36 | MC
Royal Overhead Door Inc. | 2024-08-08 | 7977.42
TCC | 2024-08-15 | 450
Amazon | 2024-08-13 | 19.97
Amazon | 2024-08-13 | 29.72
Sweetwater | 2024-08-15 | 6306.03 | MC
Sweetwater | 2024-08-14 | 637.16 | MC
Sweetwater | 2024-08-14 | 77.97 | MC
Amazon | 2024-08-13 | 348.81 | MC
| TOTAL | 100465.17

## Walk-in Coolers
Walk-in Coolers
Webstaurant | 2024-02-22 | 36010.44
| TOTAL | 36010.44

## Paint
Paint
Home Depot | 2024-06-05 | 87.97 | MC
Home Depot | 2024-06-05 | 244.19 | MC
Home Depot | 2024-06-05 | 906.11 | MC
Home Depot | 2024-06-07 | 299.73 | MC
Home Depot | 2024-06-07 | 448.79 | MC
Home Depot | 2024-06-10 | 378.09 | MC
Home Depot | 2024-06-13 | 710.09 | MC
Home Depot | 2024-06-19 | 63.73 | MC
Home Depot | 2024-06-26 | 27.7 | MC
Sherwin-Williams | 2024-06-27 | 6890.7
Home Depot | 2024-07-10 | 88.73 | MC
Home Depot | 2024-07-11 | 396.13 | MC
Home Depot | 2024-07-13 | 100.21 | MC
Home Depot | 2024-07-13 | 15.47 | MC
Home Depot | 2024-07-14 | 69.7 | MC
Sherwin-Williams | 2024-07-17 | 1370.74
Home Depot | 2024-07-19 | 162.78 | MC
Home Depot | 2024-07-19 | 104.06 | MC
Home Depot | 2024-07-20 | 49.68 | MC
Home Depot | 2024-07-24 | 141.2 | MC
Home Depot | 2024-07-28 | 198.08 | MC
Home Depot | 2024-07-29 | 68.42 | MC
Home Depot | 2024-08-04 | 24.17 | MC
Sherwin-Williams | 2024-08-06 | 183.02
Home Depot | 2024-08-14 | 48.33 | MC
Sherwin-Williams | 2024-08-19 | 252.95
Sherwin-Williams | 2024-09-04 | 3778.92
| TOTAL | 17109.69

## Stairs Handrails
Stairs Handrails
Halbert Pipe & Steel | 2024-03-26 | 4725.63
Halbert Pipe & Steel | 2024-04-09 | 7777.62
JMS | 2024-05-03 | 978.48
Halbert Pipe & Steel | 2024-07-15 | 913.6
| TOTAL | 14395.33

## Stained Concrete
Stained Concrete
White Cap | 2024-04-26 | 7806.47
White Cap | 2024-06-04 | 2974 | MC
Fence Brokers | 2024-07-05 | 1430.57 | MC
| TOTAL | 12211.04

## Finished Carpentry
Finish Carpentry
Home Depot | 2024-03-25 | 9329.31
Chris Ishmael Tile | 2024-03-28 | 24453.15
Carpenter's Club | 2024-03-28 | 72923.71
Gary Ponder | 2024-04-04 | 11502.5
Campbell Acoustical & Drywall | 2024-04-22 | 12020.06
Campbell Acoustical & Drywall | 2024-05-23 | 22263.76
Bartons | 2024-07-01 | 3448.02
Amazon | 2024-07-02 | 959.4 | MC
Amazon | 2024-07-02 | 114.18 | MC
Amazon | 2024-07-02 | 36.7 | MC
Campbell Acoustical & Drywall | 2024-07-03 | 41233.82
Home Depot | 2024-07-08 | 1091.07 | MC
Blick | 2024-07-08 | 2261.52 | MC
Professional Flooring Supply | 2024-07-09 | 244.5 | MC
Home Depot | 2024-07-14 | 72.45 | MC
Home Depot | 2024-07-19 | 62.54 | MC
Stubbs | 2024-07-22 | 1436.28
Home Depot | 2024-07-22 | 493.1 | MC
Stubbs | 2024-07-24 | 646.23
Home Depot | 2024-07-24 | 154.44 | MC
Home Depot | 2024-07-27 | 479.8 | MC
101 Mobility LLC | 2024-07-31 | 12241.8
Home Depot | 2024-08-05 | 35.37 | MC
American Paper & Twine | 2024-08-07 | 1296.77
Home Depot | 2024-08-07 | 267.54 | MC
Home Depot | 2024-08-12 | 104.39 | MC
Stubbs | 2024-08-13 | 593.55
Home Depot | 2024-08-13 | 307.41 | MC
Home Depot | 2024-08-13 | 114.8 | MC
American Paper & Twine | 2024-08-14 | 557.63
Home Depot | 2024-08-15 | 84.98 | MC
Jones Glass Inc | 2024-08-20 | 4566
Campbell Acoustical & Drywall | 2024-08-29 | 29007.32
Home Depot | 2024-08-28 | 15.18
Home Depot | 2024-08-28 | 41.65
Home Depot | 2024-08-29 | 12.31
Home Depot | 2024-08-23 | 89.13
Home Depot | 2024-08-24 | 108.18
Campbell Acoustical & Drywall | 2024-09-26 | 478.83
| TOTAL | 255149.38

## Glass Frontage Windows
Glass Frontage Windows
Jones Glass Builders | 2024-05-04 | 32190
Jones Glass Builders | 2024-05-17 | 10902
| TOTAL | 43092