## Sheet1
Annotated Milestones
Organization: | Arkansas Pharmacists Association
Project Title: | Under 100
Quarter: | Quarters 1-4
Milestones were sent to each participant after receiving a notice of award. Please copy and paste these milestones and due dates into the first and second columns. Please upload any supplemental materials through the quarterly reporting form.
Quarter 1 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Description (Please provide one to two sentence of description include details like who, what, where, when, and how).
EXAMPLE: Hire staff | EXAMPLE: January 1, 2024 | Yes | EXAMPLE: Jane Doe was hired into the Peer Position at ARORP on 2/28/23 at a salary of $55,000.
Hire APA Pharmacist | Prior to April 1, 2024 | Yes | Marlene Battle (Director of Education) is the lead on this project with a salary of $42,899.
Complete development of programming for meetings and establish CE opportunities | Prior to April 1, 2024 | Yes | CE accreditation is through UAMS and was approved for 2 hours. Accreditation fee is $2600. Other CE related fees will be applied at the end of these meetings.
Develop Data tracking system | Prior to April 1, 2024 | Yes | Uploaded into the quarterly reporting form
Submit first ARORP report | By April 1, 2024 | Yes | Submitted on 3/30/24
Quarter 2 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Launch Trainings | Prior to July 1, 2024 | Yes | 4 out of 5 trainings/meetings have been completed. The last training will be held in late June or early July
Provide uppdate on trainings | Prior to July 1, 2024 | Yes | Updates have been provided in the Quarter 2 report as well via email when asked by ARORP
Submit quarterly ARORP report | By July 1, 2024 | Yes | Submitted on 6/10/2024
Quarter 3 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Provide uppdate on trainings | Prior to November 1, 2024 | Yes | All five trainings/meetings have been completed.
Submit quarterly ARORP report | By November 1, 2024 | Yes | Submitted on 10/2/2024
Quarter 4 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Complete five in-person trainings and one virtual training | Prior to January 1, 2025 | Yes | All five trainings/meetings have been completed.The last training was held on 8-6-24 in Helena, AR
Attend annual ARORP evaluation meeting | Prior to January 1, 2025 | Yes | Attended stakeholders meeting on December 4, 2024 and annual evaluation meeting is in February 2025
Submit annual ARORP report | By January 1, 2025 | Yes | Last report was submitted in RedCap on January 15, 2025