## Sheet1
Annotated Milestones
Organization: HOPE MOVEMENT COALITION
Project Title: YOU ARE NOT ALONE
Quarter: Year 2 Quarter 4
Milestones were sent to each participant after receiving a notice of award. Please copy and paste these milestones and due dates into the first and second columns. Please upload any supplemental materials through the quarterly reporting form.
Quarter 1 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Description (Please provide one to two sentence of description include details like who, what, where, when, and how).
EXAMPLE: Hire staff | EXAMPLE: January 1, 2024 | Yes | EXAMPLE: Jane Doe was hired into the Peer Position at ARORP on 2/28/23 at a salary of $55,000.
Hire case manager x2, operations manager and executive director | Prior to March 31, 2023 | YES
Purchase all insurance | Prior to March 31, 2023 | YES
Develop user manual and training for staff and peers | Prior to March 31, 2023 | YES
Develop date tracking system | Prior to March 31, 2023 | YES
Submit first ARORP report | 2023-03-31 | YES
Quarter 2 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Lauch first round of direct mail advertising | Prior to June 30, 2023 | YES
Complete CONNECT staff and peer training | Prior to June 30, 2023 | YES
Lauch Services: You Are Not Alone | Prior to June 30, 2023 | YES
Host You Are Note Alone Lauch Event | Prior to June 30, 2023 | YES
Begin to distribute YANA brochures | Prior to June 30, 2023 | YES
Complete staff and peer training | Prior to June 30, 2023 | YES
Launch CONNECT App | Prior to June 30, 2023 | YES
Host Semi-annual 2023 grief course | Prior to June 30, 2023 | YES
Launch Hope Movement You Are Not Alone website | Prior to June 30, 2023 | YES
Submit quarterly ARORP report | 2023-06-30 | YES
Quarter 3 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Launch grief sensitivity trainings for law enforcement, clergy and first responders | Prior to September 30, 2023 | YES
Update on advertising, direct mail, and brochures | Prior to September 30, 2023 | YES
Host Bridge the Gap 2023 | Prior to September 30, 2023 | YES
Update on You Are Not Alone Services | Prior to September 30, 2023 | YES
Submit quarterly ARORP report | Prior to September 30, 2023 | YES
Quarter 4 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Update on advertising, direct mail, and brochures | Prior to December 30, 2023 | YES
Host 2023 Grief Retreat | Prior to December 30, 2023 | YES
Host semi-annual 2023 grief course | Prior to December 30, 2023 | YES
Update on You Are Not Alone Services | Prior to December 30, 2023 | YES
Yearly ARORP evaluation meeting | Prior to December 30, 2023 | YES
Submit quarterly ARORP report | 2023-12-30 | YES
Quarter 5 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Schedule 4 Grief Courses | Prior to March 31, 2024 | YES | Grieving While in Recovery - 3/27 - 4/30; Conquering Grief Central Arkansas 9/10-10/29; Conquering Grief - NWA 9/11-10/29; Grieving While in Recovery Fall 10/1 - 11/5
Begin Graphic Design | Prior to March 31, 2024 | YES | Graphic design for brochures, one pagers, social media and marketing. Print materials will include the creation of brochures featuring oipiod focused language as well as small foldable print materials for partners and agencies addressing specific needs. Running Pony is working on all designs for brochures, one pages, social media, and marketing. Social Media posts have been consistent since February and print documents have been desinged ordered and received.
Begin Website Revisions | Prior to March 31, 2024 | YES | Website revisions to incorporate more diverse inmages, accommodate emotional video storytelling, prominently feature advocacy and educational work while maintaining focus on providing support to grieving families, create highly branded content (videos, PDFs and inforgraphics).
Enroll Case Manager in LCS and Trauma Training | Prior to March 31, 2024 | YES | LCS/trauma training completed 3/11/24
Provide update on YANA services | Prior to March 31, 2024 | YES
Submit ARORP quarterly report | 2024-03-31 | YES
Quarter 6 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Launch New Program Advertising | Prior to June 30, 2024 | YES | Digital marketing and social media focus on using video storytelling featuring Arkansas families impacted by loss to convey the missionand impact of Hope Movement. This includes the You Are Not Alone initiative to display services and grief support provided. Also using the videos for fundraising campaigns, education, and awareness across all platforms. Simplified shareable content for social media specific content across all platforms including Facebook, Instagram, and TikTok to engage a wider audience and raise awareness. Create real people graphics to bring attention to the impact opioid abuse has on families. Highlight the emotional connection to the cause throgh stories and testimonies.
Launch Children Small Animal Therapy Sessions | Prior to June 30, 2024 | YES | The first two small animal therapy sessions were hosted at Royal Sanctuary Therapy Farm on 5/4/24 with 7 child participants. The two sessions were combined to avoid a severe weather event. Second animal therapy is scheduled for 10/12.
Provide Update on YANA services | Prior to June 30, 2024 | YES
Submit quarterly ARORP report | June 30,2024 | YES
Quarter 7 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Complete website revisions | Prior to September 30, 2024 | YES | Website revisions were complete 6/1/24
Complete graphic design | Prior to September 30, 2024 | YES | Graphic design is ongoing. We completed all new brochures, one-pagers, LEO and funeral cards 6/1/24. As a new need arises, we will continue to create new content.
Host Bridge the Gap 2024 | Prior to September 30, 2024 | YES | Held 8/31/24. Estimated BTG attendance 650. Angel Family Lunch attendance 106. We feel the event falling on Labor Day Weekend affected attendance. We are discussing moving the event to a Saturday either earlier in August or the 3rd week of September.
Update on YANA service | Prior to September 30, 2024 | YES | see attached report
Submit quarterly ARORP report | 2024-09-30 | YES
Quarter 8 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Complete Printing and Shipping | Prior to December 31, 2024 | YES | YANA brochures, fliers, opioid one pagers, funeral cards, LEO cards, PTEA one pagers, stamps, shipping costs associated with marketing materials, operations, events and memorial items.
Complete 4 Grief Courses | Prior to December 31, 2024 | NO | Only two grief course sessions were held in 2024. Grieving While in Recovery was held 3/27 - 4/30 and Conquering Grief Central Arkansas was held 9/10-10/29; Grieving While in Recovery Second Session was scheduled for 10/1 - 11/5, but the instructor was unable to lead the course due to personal issues. It has been resculed for Spring 2025. Conquering Grief NWA Second Session was scheduled 9/11-10/29, but was postponed until Spring 2025 due to all members of the new chapter but one partcipated in the Fall 2024 session.
Complete 4 Children Small Animal Therpay Sessions | Prior to December 31, 2024 | NO | The first two small animal therapy sessions were hosted at Royal Sanctuary Therapy Farm on 5/4/24 with 7 child participants. The two sessions were combined to avoid a severe weather event. The second and third sessions were scheduled for 10/12 but were not held due to therapist being unable to lead sessions due to unexpected business travel. Sessions were not rescheduled due to calendar conflicts and the upcoming holiday season. Next session to be held Spring 2025
Complete Case Manager LCS and Trauma Training | Prior to December 31, 2024 | YES | All case managers have been LCS and trauma trained as well as completing and receiving certification as a Grief Edcucator through David Kessler and Grief.Com's program.
Host 3-Day Grief Management Conference | Prior to December 31, 2024 | YES | Conference held 11/8 - 11/10
Update on YANA service | Prior to December 31, 2024 | YES | ARORP adjusted the reporting deadline for all to 1/15/25.
Yearly ARORP evaluation meeting | Prior to December 31, 2024 | YES | Hope Movement's evaluation meeting was held in February of 2025.
Submit annual ARORP report | Prior to December 31, 2024 | YES | ARORP adjusted the reporting deadline for all to 1/15/25.