## Y1
Annotated Milestones
Organization: | Western Arkansas Counseling and Guidance Center
Project Title: | Logan County Peer 23-024
Quarter: YEAR 1
Milestones were sent to each participant after receiving a notice of award. Please copy and paste these milestones and due dates into the first and second columns. Please upload any supplemental materials through the quarterly reporting form.
Quarter 1 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Description (Please provide one to two sentence of description include details like who, what, where, when, and how).
EXAMPLE: Hire staff | EXAMPLE: January 1, 2024 | Yes | EXAMPLE: Jane Doe was hired into the Peer Position at ARORP on 2/28/23 at a salary of $55,000.
Hire Peer Specialist | Prior to July 1, 2023 | Yes | Job offer has been sent, but peer support position is on hold pending approval from her State Probation Officer; hired 7/3/2023
Develop Peer Support Program | Prior to July 1, 2023 | Yes | Curriculum used during groups has been developed, with a large percentage coming from the core training and lived experience within the jail.
Develop Data tracking system | Prior to July 1, 2023 | Yes | Jail Admin and WACGC are utilizing the tools provided by ARORP to track the program's progress and success. Reporting on those tools will occur daily. UPDATE: Due to changing data reporting, a newer data tracking system was developed for use by Logan County Peer.
Submit first ARORP report | 2023-07-01 | Yes | Submitted on 7/1/2023
Quarter 2 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Specialist attends Crisis Ally Training | Prior to October 1, 2023 | No | Specialist was unable to attend Crisis Ally Training until November 2023 due to scheduling conflicts.
Specialist attends Moral Reconation Training | Prior to October 1, 2023 | Yes | Certificate of completion turned in to WACGC HR staff for approval.
Update on Peer Support Program | Prior to October 1, 2023 | Yes | See "Supplemental Materials"
Submit Quarterly ARORP report | 2023-10-01 | Yes | Submitted on 10/01/2023
Quarter 3 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Update on Peer Support Program | Prior to January 1, 2024 | Yes | See "Supplemental Materials;" Peer was able to attend Crisis Ally Training in November 2023
Submit Quarterly ARORP report | 2024-01-01 | Yes | Submitted on 01/01/2024
Quarter 4 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Update on Peer Support Program | Prior to April 1, 2024 | Yes | See "Supplemental Materials"
Yearly ARORP Evaluation Meeting | Prior to April 1, 2024 | Yes | Peer remains in good standing
Submit Yearly ARORP Report | 2024-04-01 | Yes | Submitted by Tye Brown on 3/31/2024

## Y2
Annotated Milestones
Organization: | Western Arkansas Counseling and Guidance Center
Project Title: | Logan County Peer 23-024
Quarter: YEAR 2
Milestones were sent to each participant after receiving a notice of award. Please copy and paste these milestones and due dates into the first and second columns. Please upload any supplemental materials through the quarterly reporting form.
Quarter 1 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Description (Please provide one to two sentence of description include details like who, what, where, when, and how).
EXAMPLE: Hire staff | EXAMPLE: January 1, 2024 | Yes | EXAMPLE: Jane Doe was hired into the Peer Position at ARORP on 2/28/23 at a salary of $55,000.
Update on Peer Support Program | Prior to July 1, 2024 | Yes | Peer has continued to show success through program, boasting an 81% success rate in those who have graduated the program. See "Supplemental Materials."
Submit Quarterly ARORP report | 2024-07-01 | Yes | Submitted by Tye Brown on 6/28/2024.
Quarter 2 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Update on Peer Support Program | 2024-09-30 | Yes | Peer maintained a high success rate throughout Q2, continuing to provide recovery and life skills services to the individuals she served. Danielle Sherman left The Guidance Center on 9/20/2025, having her duties in LCDC taken over by another peer, Cindy Moore, who has worked for The Guidance Center in addiction services before Danielle was hired on. Cindy took on the challenge of meeting with the individuals in the program and has worked to keep the momentum going in LCDC.
Specialist attends Crisis Ally Training | 2024-09-30 | Yes | Peer attended Crisis Ally training in July 2024.
Specialist attends Moral Reconation Training | 2024-09-30 | No | Specialist was unable to attend MRT due to scheduling conflicts and subsequent departure from WACGC.
Submit Quarterly ARORP report | 2024-10-15 | Yes | Submitted by Tye Brown on 10/15/2024.
Quarter 3 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Update on Peer Support Program | 2024-12-31 | Yes | Logan County Peer program as headed by Cindy Moore saw continued success despite less overall engagement. Cindy has continued to facilitate recovery groups for the Logan County Detention Center to further the recovery efforts of the inmates in the detention center. See "Supplemental Materials."
Submit Quarterly ARORP report | 2025-01-15 | Yes | Submitted by Tye Brown on 1/10/2025
Quarter 4 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Update on Peer Support Program | 2025-03-31 | Yes | Cindy Moore successfully brought the LCDC Peer program to a close, continuously providing critical recovery support services and resources to individuals in the Logan County Detention Center. Project end.
Submit Quarterly ARORP report | 2025-04-15 | Yes
Yearly ARORP Evaluation Meeting | As scheduled by ARORP | Yes | Scheduled for 4/23/2025 and will be attended.