## Y1
Annotated Milestones
Organization: | Western Arkansas Counseling and Guidance Center
Project Title: | Five West Crisis Stabilization Unit Peer Recovery Support Specialist Program, ARORP23-036
Quarter: YEAR 1
Milestones were sent to each participant after receiving a notice of award. Please copy and paste these milestones and due dates into the first and second columns. Please upload any supplemental materials through the quarterly reporting form.
Quarter 1 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Description (Please provide one to two sentence of description include details like who, what, where, when, and how).
EXAMPLE: Hire staff | EXAMPLE: January 1, 2024 | Yes | EXAMPLE: Jane Doe was hired into the Peer Position at ARORP on 2/28/23 at a salary of $55,000.
Hire Peer Specialist | Prior to June 1, 2023 | Yes | Tye Brown was hired on 24 April 2024 as the Peer Specialist for the ARORP position at Five West CSU at a salary of $28,000.
Develop Peer Support Program | Prior to June 1, 2023 | Yes | Peer Support program developed by Tye Brown to target under-represented populations living with SUD and MHD that came to the CSU, using lived experience of going through the program as a way to connect with those seeking services.
Develop Data tracking system | Prior to June 1, 2023 | Yes | CSU and WACGC are utilizing the tools provided by ARORP to track the program's progress and success. Reporting on those tools will occur daily. UPDATE: Due to changing data reporting, a newer data tracking system was developed for use by CSU Peer.
Submit first ARORP report | 2023-06-01 | Yes | Submitted on 6/1/2023
Quarter 2 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Specialist attends Crisis Ally Training | Prior to September 1, 2023 | No | Specialist was unable to attend Crisis Ally Training until November 2023 due to scheduling conflicts.
Specialist attends Moral Reconation Training | Prior to September 1, 2023 | No | Specialist was unable to attend MRT until September 18-21 due to scheduling conflicts. Certificate of completion turned in to WACGC HR staff for approval.
Update on Peer Support Program | Prior to September 1, 2023 | Yes | See "Supplemental Materials"
Submit Quarterly ARORP report | 2023-09-01 | Yes | Submitted on 9/01/2023
Quarter 3 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Update on Peer Support Program | Prior to December 1, 2023 | Yes | See "Supplemental Materials;" Peer was able to attend Crisis Ally Training in November 2023
Submit Quarterly ARORP report | 2023-12-01 | Yes | Submitted on 12/01/2023
Quarter 4 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Update on Peer Support Program | Prior to March 1, 2024 | Yes | See "Supplemental Materials"
Yearly ARORP Evaluation Meeting | Prior to March 1, 2024 | Yes | Peer remains in good standing
Submit Yearly ARORP Report | 2024-03-01 | Yes | Submitted by on 03/01/2024

## Y2
Annotated Milestones
Organization: | Western Arkansas Counseling and Guidance Center
Project Title: | Five West Crisis Stabilization Unit Peer Recovery Support Specialist Program, ARORP23-036
Quarter: YEAR 2
Milestones were sent to each participant after receiving a notice of award. Please copy and paste these milestones and due dates into the first and second columns. Please upload any supplemental materials through the quarterly reporting form.
Quarter 1 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Description (Please provide one to two sentence of description include details like who, what, where, when, and how).
EXAMPLE: Hire staff | EXAMPLE: January 1, 2024 | Yes | EXAMPLE: Jane Doe was hired into the Peer Position at ARORP on 2/28/23 at a salary of $55,000.
Update on Peer Support Program | Prior to June 1, 2024 | Yes | Peer Support Program has shown continued success, reaching individuals that typically feel they need to guard themselves in similar situations. Peer has assisted in de-escalating multiple confrontations as well as convinced individuals to give the CSU and, by extension, treatment a chance to help them. A break down of services can be found in "Supplemental Materials."
Submit Quarterly ARORP report | 2024-06-01 | Yes | Submitted on 05/31/2024.
Quarter 2 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Update on Peer Support Program | Prior to September 1, 2024 | Yes | Peer Support Program has continued to find success in providing individuals with services conducive to their own personal pathway of recovery. See "Supplemental Materials."
Specialist attends Crisis Ally Training | Prior to September 1, 2024 | Yes | Specialist attended Crisis Ally Training July 2024.
Specialist attends Moral Reconation Training | Prior to September 1, 2024 | No | Specialist was unable to attend MRT due to scheduling conflicts.
Submit Quarterly ARORP report | 2024-09-01 | Yes | Submitted on 8/27/2024
Quarter 3 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Continue Peer Support Program | 2024-12-31 | Yes | Peer Support program has continued to grow and reach individuals within the CSU as well as the community through different outreach and education opportunities. CSU Peer has engaged with multiple organizations in the area to promote Peer Recovery services, opioid education and naloxone training, and mental health urgent care facilitated by the CSU.
Submit Quarterly ARORP report | 2025-01-15 | Yes | Submitted by Tye Brown 1/10/2025.
Quarter 4 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Continue Peer Support Program | 2025-02-28 | Yes | Project End.
Yearly ARORP Evaluation Meeting | As scheduled by ARORP. | Yes | Scheduled for 4/23/2025 and will be attended.
Submit Yearly ARORP Report | 2025-04-15 | Yes | Submitted by Tye Brown on 4/3/2025.