## Sheet1
Organization: |  | Recovery Center of the Ozarks
Project Title: |  | Housing Expansion 23-052
Quarter: 4
Milestones were sent to each participant after receiving a notice of award. Please upload any supplemental materials through the quarterly reporting form.
Quarter 1 Milestones | Status | Updates/Notes
Purchase property and furnishings | Near Completion | Purchased 406 Natchez Trace and majority of furnishings
Hire personnel | Complete | Jeremiah Woehl hired on 8/21 with a salary of 33k
| Complete | Larry Boyd hired on 9/25 with a salary of 33k
| Complete | Michelle McAlpin contracted on 9/25 for 10 hours per week at $15/hr
Launch new facility | Complete | Two residents moved into Natchez House on 10/5
Develop data tracking system | Complete | Uploaded into the quarterly reporting form
Submit first ARORP report | Complete | Submitted on 12/1/23
Quarter 2 Milestones | Status | Updates/Notes
Operate at full capacity | Partial Completion | Three additional residents moved into Natchez House. Fire code currently restricting us from adding more.
Provide update on housing | Complete | Uploaded into the quarterly reporting form
Submit quarterly ARORP report | Complete | Submitted on 2/29/24
Quarter 3 Milestones | Status | Updates/Notes
Operate at full capacity | Partial Completion | Two additional residents moved into Natchez House. Fire code issues appear to be resolved and we can begin moving in residents with more than three months sobriety.
Provide update on housing | Complete | Uploaded into the quarterly reporting form
Submit quarterly ARORP report | Complete | Submitted on 5/30/24
Update on Personnel | Overcoming Adversity | Larry Boyd resigned as Peer Specialist on 5/20/24. New hire begins on 6/3/24. Michelle McAlpin resigned on 5/3/24. New hire begins on 6/24/24.
Quarter 4 Milestones | Status | Updates/Notes
Operate at full capacity | Complete | All 12 beds are filled
Provide update on housing | Complete | Uploaded into the quarterly reporting form
Attend annual ARORP evaluation meeting | Complete | Scheduled by ARORP
Submit annual ARORP report | Complete | Uploaded into the quarterly reporting form