## Annotated Budget
Organization: | Renewal Ranch
Project Title: | Renewal Ranch Housing
Q4 2024 Annotated Budget (5th Quarter of Reporting)
You are responsible for keeping track of receipts for all purchases for your agency’s records. You will not submit receipts to ARORP until the end of the year.
Original Budget Line Item | Original Amount Budgeted | Cost Projection Following Bid Process | Description of Budget Line Item | Spent to Date | Spent to Date Notes* | Amount Left to Spend | Plan to Spend | Does this plan align with project milestones?
General Conditions | 133366 | 132918 | General construction expenses. | 112609.19 |  | 20308.81 | NA | Yes
Architectural Fees | 119390 | 119390 | Architecture plan development, documentation, and administration. | 119906 | Construction administration charges were slightly higher than expected due to changes. | -516 | NA | Yes
Earthwork | 106843 | 102707 | Preparing the grounds for construction and habitation. | 118465.57 | Earthwork is over budget due to ongoing issues with the red clay content of the soil, including additional issues related to landscaping. In an attempt to save back some of this unexpected overage, numerous loads of topsoil were harvested from another part of the Renewal Ranch property and used to improve the landscaping base around the building. Savings will be gained in other categories to keep us within our overall funding amount. | -15758.57 | NA | Yes
Termite Treatment | 0 | 1600 | Termite Prevention. | 479.6 |  | 1120.4 | NA | Yes
Landscaping | 30153 | 30153 | Features to make the area surrounding the facility attractive and functional. | 24660.64 |  | 5492.36 | NA | Yes
Concrete/Foundation | 161685 | 130170 | Concrete foundation and slab. | 148931.71 | Additional concrete was required to increase the space for handicapped and visitor parking and to allow more clearance for parked vehicles away from Lake Drive. Savings will be gained in other categories to keep us within our overall funding amount. | -18761.71 | NA | Yes
Structural Steel | 61492 | 0 |  | 0 | No spending in this category. We are maintaining the same quality and durability with a lower-cost all-wood construction. | 0 | NA | Yes
Structural Steel Erection | 10480 | 0 |  | 0 | No plan to spend in this category. | 0 | NA | Yes
Rough/Finish Carpentry | 278485 | 255303 | All carpentry for the facility. | 203808.26 |  | 51494.74 | NA | Yes
Millwork | 79446 | 32400 | Additional strucural items processed in another facility before installation. | 33775 |  | -1375 | NA | Yes
Shingle Roof System | 43913 | 35250 | Standard shingle roof. | 35250 |  | 0 | NA | Yes
Siding and Stone | 126158 | 99015 | Siding and stone for the building matching other facilities on the Renewal Ranch campus. | 91616.93 |  | 7398.07 | NA | Yes
Waterproofing& Sealants | 6732 | 6732 | Prevention of leaks. | 425.35 |  | 6306.65 | NA | Yes
Doors & Hardware | 62249 | 50566 | Doors and related hardware. | 72602.71 | Additional doors and hardware were required primarily due to the construction closets (22 closet doors and related) that were omitted from the original floor plan. This omission was reported to Tenesha Barnes and Joy Spense verbally on 04/01/23. Savings will be gained in other categories to keep us within our overall funding amount. | -22036.71 | NA | Yes
Glass, Glazing & Windows | 25881 | 19712 | Windows installed and finished. | 23458.49 | We are slighly over budget on this line item due to "installation labor" being omitted from the cost estimate. This was not discovered until the work was completed. We will reduce costs in other areas as needed to stay within funding. | -3746.49 | NA | Yes
Drywall & Insulation | 68669 | 68895 | Drywall and insulation. | 58945.5 |  | 9949.5 | NA | Yes
Flooring & Base | 67303 | 28790 | All flooring including the base underneath the floors. | 31831.72 | We are over in this category due to impacts of adding the closets. | -3041.72 | NA | Yes
Painting & Finishing | 81996 | 71900 |  | 73520.36 | Bedroom closets were inadvertently omitted from the building floor plan. This omission was communicated to Tenesha Barnes and Joy Spense verbally on 04/01/23. We will remain within our overall approved funding. | -1620.36 | NA | Yes
Internet/Low Voltage Wiring | 0 | 0 | Wiring for internet and related security. | 0 | Included with electric | 0 | NA | Yes
Fire Protection | 186375 | 231055 | Installation of sprinkler system consistent with local fire code. | 245035.59 | Fire Protection estimates have been increased by $32,471 due to the necessity of a water-pumping system for this building, as required by the fire marshal. This was communicated to Tenesha Barnes and Joy Spence on 04/16/24 and they approved. The fire marshal later required an additional separate fire suppression system to be installed for the cooking range. This was not known or estimated in the original building plans. | -13980.59 | NA | Yes
Plumbing | 87286 | 170926 | Plumbing within the building and connection to water system. | 164320.97 |  | 6605.03 | NA | Yes
Septic System | 28361 | 50000 | Human waste disposal. | 50000 |  | 0 | NA | Yes
HVAC | 107551 | 101950 | Heating and air conditioning. | 104399.95 |  | -2449.95 | NA | Yes
Electrical | 117440 | 128460 | Electrical system including connection to the local power utility. Includes internet wiring. | 132760 | Bedroom closets were inadvertently omitted from the building floor plan. This omission was communicated to Tenesha Barnes and Joy Spense verbally on 04/01/23. We will remain within our overall approved funding. | -4300 | NA | Yes
Overhead & Fees | 0 | 119390 | General contractor overhead and fees. | 119390 |  | 0 | NA | Yes
Peer Support Specialists | 63200 | 63200 | Peer Support Specialists. | 26333.35 | Funding was received for two specialists over a 12 month period. The first monthly payments occurred on August 18, 2024, for the month of July 2024. Seven months of funding remains to be allocated. | 36866.65 | NA | Yes
Case Management Software | 13182 | 13182 | Case management software. | 13182 |  | 0 | NA | Yes
Bunkhouse Furnishings | 75614.97 | 75614.97 | Furnishings. | 73379.49 |  | 2235.48 | NA | Yes
Total Budget / Projection | 2143250.97 | 2139278.97
|  | Spent to Date: | 0 | 2079088.38 | Amount Left to Spend at the end of Year 1: | 60190.59
TOTAL ARORP FUNDING | 2143014.97
[5 empty] | Allocated Year 2 Funds for Peers: | 36866.69
[5 empty] | Year 1 Funding to Return to the Qualified Settlement Fund: | 23323.9

## General Conditions
Total Cost per Receipt | Date | Vendor | Items Purchased with Unit Price
230.04 | 2024-02-05 | A1 Portable Toilets | RT021324-29-B Portable Toilet Rental
230.04 | 2024-02-13 | A1 Portable Toilets | RT31324-27B Portable Toilet Rental
191.19 | 2024-03-31 | LRS | AM71311 Dumpster Roll Off
230.04 | 2024-04-12 | A1 Portable Toilets | RT041224-23 Portable Toilet Rental
19499 | 2024-04-25 | NBMC Inc | 2-General Conditions
818.5 | 2024-04-30 | LRS | AM76014 Dumpster Roll Off
230.04 | 2024-05-09 | A1 Portable Toilets | RT51324-21 -Portable Toilet Rental
733.01 | 2024-05-31 | LRS | AM80448 Dumpster Roll Off
230.04 | 2024-06-07 | A1 Portable Toilets | RT061324-23 Portable Toilet Rental
29255.73 | 2024-06-14 | NBMC Inc | 2327-03 General Condition
633.21 | 2024-06-30 | LRS | AM85052 Dumpster Roll Off
460.08 | 2024-07-13 | A1 Portable Toilets | RT071324-25 Portable Toilet Rental
16836.88 | 2024-07-22 | NBMC Inc | 2327-4 General Conditions
460.08 | 2024-07-24 | A1 Portable Toilets | RT81324-26 Portable Toilet Rental
15662.34 | 2024-08-26 | NBMC Inc | 2327-05 General Conditions
460.08 | 2024-08-28 | A1 Portable Toilets | RT091324-23 Portable Toilet Rental
2400 | 2024-09-13 | Edward Spears | 9-13-2024 Cleaned Living Quarters/inside and outside windows
21824 | 2024-09-25 | NBMC Inc | General Conditions
116.42 | 2024-09-30 | LRS | AM97943-Dumpster Final Pick-up
2108.47 | 2024-10-28 | NBMC Inc | 2327--07 General Conditions
112609.19

## Architectural Fees
Total Cost per Receipt | Date | Vendor | Items Purchased with Unit Price
27000 | 2023-12-05 | Rik Sowell Architects | Design Development
36000 | 2024-01-02 | Rik Sowell Architects | Design Development
27516 | 2024-04-22 | Rik Sowell Architects | Design Development
29390 | 2024-10-22 | Rik Sowell Architects | Construction Administration
119906

## Earthwork
Total Cost per Receipt | Date | Vendor | Items Purchased with Unit Price
3878.65 | 2023-10-20 | Hum's Rental | Smooth Roller Rental
4825.5 | 2023-11-06 | Hum's Rental | Smooth Roller Rental
136.81 | 2023-11-08 | Conway Farm & Home Supply | Auto shut-off nozzle, pushpull switch, transfer nose
39240 | 2023-11-20 | A&B Dirt Movers | Load and haul fill
363.5 | 2023-11-20 | Associated Farmers Coop | Straw Bale
16359.42 | 2023-12-12 | NBMC | Site preparation
752.58 | 2024-04-25 | NBMC | Earthwork
41870 | 2024-05-14 | Paladino Construction | Installation of storm drain
547.67 | 2024-05-16 | Keeling Co. | Earthwork
2000 | 2024-06-14 | NBMC | Earthwork
439.5 | 2024-08-05 | M2 Equipment Rentals | Roller Rental
8452.44 | 2024-08-26 | NBMC | Earthwork
-439.5 | 2024-09-25 | NBMC | 2327-06 Earthwork
39 | 2024-10-28 | NBMC | 2327-07 Earthwork
118465.57

## Termite Treatment
Total Cost per Receipt | Date | Vendor | Items Purchased with Unit Price
479.6 | 2024-02-23 | Central Arkansas Pest Services | Termite Prevention
479.6

## Landscaping
Total Cost per Receipt | Date | Vendor | Items Purchased with Unit Price
133.14 | 2024-08-08 | Winsupply | Landscaping
22074.75 | 2024-08-22 | Little Rock Landscape | Landscaping
2452.75 | 2024-09-19 | Little Rock Landscape | Landscaping
24660.64

## Concrete Foundation
Total Cost per Receipt | Date | Vendor | Items Purchased with Unit Price
2727.29 | 2024-01-30 | Rogers Group | Foundation/Slab
20790 | 2024-02-01 | Brian Hutchings Concrete | Foundation/Slab
1220.33 | 2024-02-02 | Mallard Ready Mix | Concrete
13267.77 | 2024-02-05 | Ozark Rebar | Foundation Rebar
832.77 | 2024-02-05 | Rogers Group | Foundation/Slab
11550 | 2024-02-06 | Brian Hutchings Concrete | Concrete & Labor
9477.44 | 2024-02-08 | Mallard Ready Mix | Concrete
1830.05 | 2024-02-20 | Rogers Group | Foundation/Slab
13860 | 2024-02-21 | Brian Hutchings Concrete | Concrete application #2
6199.33 | 2024-02-23 | Rogers Group | Foundation/Slab
862.42 | 2024-02-26 | Rogers Group | Foundation/Slab
26832.9 | 2024-02-27 | Mallard Ready Mix | Concrete
576.93 | 2024-02-27 | Arkansas Rebar | Rebar
2478.33 | 2024-02-28 | Mallard Ready Mix | Concrete
2205.84 | 2024-02-28 | Harris Concrete Pumps | Concrete work
80 | 2024-03-04 | Associated Farmers Coop | Straw bale
573.73 | 2024-03-13 | MTA Engineers | Concrete sampling and testing
389.4 | 2024-03-27 | MTA Engineers | Lab manager review and submittal
-239.26 | 2024-04-12 | Ozark Rebar | Vendor Credit
237 | 2024-04-25 | NBMC, Inc. | Foundation/Slab
442.12 | 2024-06-11 | Rogers Group | Foundation/Slab
485.15 | 2024-07-22 | Arkansas Rebar | Foundation/Slab
2769.49 | 2024-07-24 | Mallard Ready Mix | Foundation/Slab
110.93 | 2024-07-25 | Arkansas Rebar | Foundation Rebar
9315.75 | 2024-08-01 | Mallard Ready Mix | Foundation/Slab
20056 | 2024-08-06 | Brian Hutchings Concrete | Foundation/Slab
148931.71

## Structural Steel
Total Cost per Receipt | Date | Vendor | Items Purchased with Unit Price
0

## Structural Steel Erection
Total Cost per Receipt | Date | Vendor | Items Purchased with Unit Price
0

## Carpentry
Total Cost per Receipt | Date | Vendor | Items Purchased with Unit Price
110.88 | 2024-02-29 | Whit Davis Lumber | Lumber
23767.38 | 2024-02-29 | A-1 Truss | Truss Package
41699.34 | 2024-02-29 | Whit Davis Lumber | Lumber
1005.69 | 2024-03-06 | Whit Davis Lumber | Lumber
304.88 | 2024-03-08 | Whit Davis Lumber | Lumber
413.75 | 2024-03-12 | Ridout Lumber | Lumber
339.32 | 2024-03-12 | Ridout Lumber | Lumber
591.15 | 2024-03-13 | Ridout Lumber | Lumber
1064.81 | 2024-03-14 | Ridout Lumber | Lumber
354.09 | 2024-03-15 | Ridout Lumber | Lumber
1583.3 | 2024-03-21 | Whit Davis Lumber | Lumber
81.15 | 2024-03-26 | Fastenal Company | Rough/Finish
37000 | 2024-03-27 | JU Rodriguez Brothers | Framing
2449.75 | 2024-04-03 | Whit Davis Lumber | Closets
192.14 | 2024-04-15 | Whit Davis Lumber | Lumber
62.43 | 2024-04-19 | Whit Davis Lumber | Lumber
6594 | 2024-04-25 | NBMC | Rough/Finish
5500 | 2024-05-21 | JU Rodriguez Brothers | Exterior Closet
5296.22 | 2024-05-24 | Whit Davis Lumber | Lumber
10000 | 2024-05-29 | D&T Carpentry | Closets, Window Sills, After Base
395.93 | 2024-05-29 | Whit Davis Lumber | Rough/Finish
29993.16 | 2024-06-14 | NBMC | Rough/Finish
-1793.2 | 2024-06-14 | Whit Davis Lumber | Credit for Lumber
6079.02 | 2024-06-20 | Whit Davis Lumber | Rough/Finish
12795 | 2024-07-08 | D&T Carpentry | Trim for attic and access cabinet closet rods
47.53 | 2024-07-10 | Whit Davis Lumber | Rough/Finish
5935.57 | 2024-07-22 | NBMC | Rough/Finish
6144.97 | 2024-08-26 | NBMC | Rough/Finish
5800 | 2024-09-25 | NBMC | 2327-06 Rough/Finish
203808.26

## Millwork
Total Cost per Receipt | Date | Vendor | Items Purchased with Unit Price
14580 | 2024-05-24 | Oliver Cook Millwork | Millwork
14580 | 2024-07-16 | Oliver Cook Millwork | Millwork
1375 | 2024-08-19 | Oliver Cook Millwork | Millwork
3240 | 2024-10-25 | Oliver Cook Millwork | Millwork
33775

## Shingle Roof System
Total Cost per Receipt | Date | Vendor | Items Purchased with Unit Price
26725 | 2024-03-29 | HD Roofing | Shingle Roof System
5000 | 2024-08-01 | HD Roofing | Shingle Roof System
3525 | 2024-10-23 | HD Roofing | Shingle Roof System
35250

## Siding & Stone
Total Cost per Receipt | Date | Vendor | Items Purchased with Unit Price
15428.17 | 2024-02-27 | Antique Brick & Block | Cast Stone Material
10000 | 2024-04-25 | Story Stone Masonry | Stone Masonry
20000 | 2024-04-30 | Story Stone Masonry | Stone Masonry
3394.5 | 2024-05-13 | Story Stone Masonry | Stone Masonry
68.76 | 2024-05-20 | Arkansas Rebar | Rebar
3710.5 | 2024-07-23 | Story Stone Masonry | Stone Masonry
39015 | 2024-09-26 | Xtreme Exteriors | 1-Final Siding & Stone
91616.93

## Waterproofing & Sealants
Total Cost per Receipt | Date | Vendor | Items Purchased with Unit Price
181.82 | 2024-07-22 | NBMC Inc | Thermal & Moisture Protection
141.09 | 2024-08-13 | Arkansas Rebar | Waterproofing & Sealant
102.44 | 2024-08-14 | Arkansas Rebar | Waterproofing & Sealant
425.35

## Doors & Hardware
Total Cost per Receipt | Date | Vendor | Items Purchased with Unit Price
1442.1 | 2024-03-08 | American Building Specialties | Metal Frames
2840.5 | 2024-03-26 | American Building Specialties | Hinges
4293.53 | 2024-04-18 | American Building Specialties | Hollow Metal Doors
900 | 2024-04-19 | B&B Construction | Doors/Hardware
4972.5 | 2024-05-20 | B&B Construction | Hollow Core & Fiberglass Doors & Hardware
34780.84 | 2024-05-24 | Whit Davis Lumber | Doors/Hardware
59.17 | 2024-06-03 | John Berry | Toilet Paper Holders
8561.25 | 2024-06-20 | B&B Construction | Hollow Core & Fiberglass Doors & Hardware
377.78 | 2024-07-09 | American Building Specialties | Door Closer
1567.74 | 2024-07-11 | American Building Specialties | Door Closer
7210.5 | 2024-07-11 | American Building Specialties | Door Closer
1631.25 | 2024-07-22 | B&B Construction | Doors/Hardware
990 | 2024-08-02 | B&B Construction | Doors/Hardware
419.03 | 2024-08-16 | Ridout Lumber Company | Barn Strap Hanger w/fasteners
1785 | 2024-08-22 | B&B Construction | Doors/Hardware
250.05 | 2024-08-26 | NBMC Inc | Doors/Hardware
150 | 2024-08-26 | B&B Construction | Doors/Hardware
371.47 | 2024-09-25 | NBMC Inc | 2327-06 Doors & Hardware
72602.71

## Glass, Glazing & Windows
Total Cost per Receipt | Date | Vendor | Items Purchased with Unit Price
23458.49 | 2024-03-26 | Pella Products of Arkansas | Glass, Glazing & Windows
23458.49

## Drywall & Insulation
Total Cost per Receipt | Date | Vendor | Items Purchased with Unit Price
47680.2 | 2024-05-22 | Stellar Interiors | Drywall & Insulation
11265.3 | 2024-07-24 | Stellar Interiors | Drywall & Insulation
58945.5

## Flooring & Base
Total Cost per Receipt | Date | Vendor | Items Purchased with Unit Price
15577.2 | 2024-07-01 | Moix Carpet & Fans | Flooring & Base
9973.8 | 2024-07-25 | Moix Carpet & Fans | Flooring & Base
2451.72 | 2024-08-26 | NBMC Inc | Flooring
590 | 2024-10-21 | Moix Carpet & Fans | Flooring & Base
360 | 2024-11-08 | Moix Carpet & Fans | Flooring & Base
2879 | 2024-11-08 | Moix Carpet & Fans | Flooring & Base
31831.72

## Painting & Finishing
Total Cost per Receipt | Date | Vendor | Items Purchased with Unit Price
32911.56 | 2024-05-21 | Lilley Paint Co. | Painting & Finishing
29864.88 | 2024-07-01 | Lilley Paint Co. | Painting & Finishing
3031.92 | 2024-07-22 | Lilley Paint Co. | Painting & Finishing
400 | 2024-08-06 | Turner Parking Lot Maintenance | Striping
7312 | 2024-08-22 | Lilley Paint Co. | Painting & Finishing
73520.36

## Internet Low Voltage Wiring
Total Cost per Receipt | Date | Vendor | Items Purchased with Unit Price
0

## Fire Protection
Total Cost per Receipt | Date | Vendor | Items Purchased with Unit Price
4500 | 2024-02-21 | Paladino Construction | Metal Riser for Fire Line
28.37 | 2024-03-08 | A&B Reprographics | Copies of Specs
42.3 | 2024-03-08 | A&B Reprographics | Digital Bond
11645.1 | 2024-03-21 | A&A Fire & Safety | Sprinklers
15360 | 2024-03-26 | Paladino Construction | Rip Rap & B-Stone
10250 | 2024-04-01 | Paladino Construction | Rip Rap & SB2
1920 | 2024-04-01 | Paladino Construction | Fire Protection
308.9 | 2024-04-02 | Boyd Metal | Pump House
100.32 | 2024-04-03 | Fastenal | Fire Protection
4829.95 | 2024-04-04 | Peterson Concrete Tank | Fire Protection
251 | 2024-04-04 | Airgas USA | Gas
175.9 | 2024-04-04 | Mallard Ready Mix | Fire Protection
43.41 | 2024-04-04 | Ozark Rebar | Rebar
330.9 | 2024-04-08 | Arkansas Rebar | Rebar
3052.81 | 2024-04-08 | McNichols Co. | Fire Protection
5558 | 2024-04-12 | Equipmentshare.com | Fire Protection
1920 | 2024-04-15 | Paladino Construction | Fire Protection
220 | 2024-04-17 | Paladino Construction | Storm Drain Ring & Cover
3913.88 | 2024-04-19 | Hum's Rental | Equipment Rental
42985.85 | 2024-04-22 | A&A Fire & Safety | Fire Protection
3373 | 2024-04-25 | NBMC, Inc. | Fire Protection
37895.83 | 2024-04-29 | Paladino Construction | Installation of Water
3960 | 2024-05-09 | Paladino Construction | Digging & backfilling trench for electric
3800 | 2024-05-16 | AV Concrete Construction | Slab form, pour and finish
22501.05 | 2024-05-16 | Lock-Wood Electric | Fire Pump Electrical
6250 | 2024-06-14 | NBMC, Inc. | Fire Protection
12545.1 | 2024-07-01 | A&A Fire & Safety | Fire Protection
18859.45 | 2024-07-10 | A&A Fire & Safety | Fire Protection
9652.9 | 2024-07-24 | A&A Fire & Safety | Fire Protection
840.6 | 2024-07-24 | A&A Fire & Safety | Fire Protection
3600 | 2024-08-28 | A&A Fire & Safety | Installation of new Pyro Chem Automatic Fire Suppression System
7904.55 | 2024-09-25 | Lock-Wood Electric | Fire Pump electrical and fiber material and labor
6416.42 | 12/04//24 | Lock-Wood Electric | Lakeview Security, Fire & Communications
245035.59

## Plumbing
Total Cost per Receipt | Date | Vendor | Items Purchased with Unit Price
34200 | 2024-02-21 | Steve Nichols Plumbing | Slab Rough-in
150 | 2024-02-21 | Steve Nichols Plumbing | App #1
53460 | 2024-03-28 | Steve Nichols Plumbing | App #2-Slab Rough-in
37320 | 2024-06-04 | Paladino Construction | Plumbing - installation of water line
17100 | 2024-07-16 | Steve Nichols Plumbing | App #3-Slab Rough-in
5450.4 | 2024-07-24 | Steve Nichols Plumbing | Plumbing
111.61 | 2024-08-26 | NBMC Inc | Plumbing
45.46 | 2024-08-27 | Winsupply of Conway | Plumbing
2025 | 2024-08-28 | Steve Nichols Plumbing | Plumbing
12471 | 2024-09-10 | Steve Nichols Plumbing | Plumbing
1987.5 | 2025-12-26 | Tyler Group | Waterline design, submittal to Ark. Dept. Health
164320.97

## Septic
Total Cost per Receipt | Date | Vendor | Items Purchased with Unit Price
24600 | 2024-05-06 | Tyler Group | Septic System
15500 | 2024-06-17 | Tyler Group | Septic System
9900 | 2024-08-20 | Tyler Group | Septic System
50000

## HVAC
Total Cost per Receipt | Date | Vendor | Items Purchased with Unit Price
45243.4 | 2024-03-29 | Stevenson Heating & Air | HVAC
20114.6 | 2024-05-06 | Stevenson Heating & Air | HVAC
23607 | 2024-07-01 | Stevenson Heating & Air | HVAC
4994.95 | 2024-09-19 | Stevenson Heating & Air | HVAC
10440 | 2024-09-19 | Stevenson Heating & Air | HVAC
104399.95

## Electrical
Total Cost per Receipt | Date | Vendor | Items Purchased with Unit Price
12600 | 2024-03-21 | Lock-Wood Electric | Electrical
31590 | 2024-04-19 | Lock-Wood Electric | Electrical
23256 | 2024-05-20 | Lock-Wood Electric | Electrical
41661 | 2024-06-20 | Lock-Wood Electric | Electrical
4050 | 2024-07-24 | Lock-Wood Electric | Electrical
7030 | 2024-09-19 | Lock-Wood Electric | Electrical
12573 | 2024-10-09 | Lock-Wood Electric | Electrical
132760

## Overhead & Fees
Total Cost per Receipt | Date | Vendor | Items Purchased with Unit Price
39762.67 | 2024-04-25 | NBMC, Inc. | Construction manager fee (3 months)
26531.11 | 2024-06-14 | NBMC, Inc. | Construction manager fee (3 months)
13265.56 | 2024-07-22 | NBMC, Inc. | Construction manager fee (06/15/24--07/22/24)
13265.56 | 2024-08-26 | NBMC, Inc. | Construction manager fee (07/22/24--08/26/24)
13265.56 | 2024-09-25 | NBMC, Inc. | Construction manager fee (08/27/24-09/25/24)
13299.54 | 2024-10-28 | NBMC, Inc. | Construction manager fee (09/26/24-10/28/24)
119390

## Peer Support Specialists
Total Cost per Receipt | Date | Vendor | Items Purchased with Unit Price
2633.33 | 2024-08-18 | Renewal Ranch | One Peer Support Specialist for one month
2633.34 | 2024-08-18 | Renewal Ranch | One Peer Support Specialist for one month
2633.33 | 2024-09-01 | Renewal Ranch | One Peer Support Specialist for one month
2633.34 | 2024-09-01 | Renewal Ranch | One Peer Support Specialist for one month
2633.33 | 2024-10-01 | Renewal Ranch | One Peer Support Specialist for one month
2633.34 | 2024-10-01 | Renewal Ranch | One Peer Support Specialist for one month
2633.33 | 2024-11-05 | Renewal Ranch | One Peer Support Specialist for one month
2633.34 | 2024-11-05 | Renewal Ranch | One Peer Support Specialist for one month
2633.33 | 2024-12-05 | Renewal Ranch | One Peer Support Specialist for one month
2633.34 | 2024-12-05 | Renewal Ranch | One Peer Support Specialist for one month
26333.35

## Case Management Software
Total Cost per Receipt | Date | Vendor | Items Purchased with Unit Price
7020 | 2024-05-28 | Social Solutions | Case Management Software Invoice #1
6162 | 2024-06-20 | Social Solutions | Case Management Software Invoice #2
0
0
0
13182

## Furnishings
Total Cost per Receipt | Date | Vendor | Items Purchased with Unit Price
58699.96 | 2024-06-18 | Cleo's Furniture | Bunkhouse furnishings
2005.8 | 2024-07-03 | Amazon.com | Bed frames
4829.84 | 2024-10-21 | Metro Appliances & More | Washer/Dryer Combo & Installation - 3
4663.89 | 2024-10-22 | Metro Appliances & More | Washer/Dryer Combo & Installation - 3
3180 | 2024-11-13 | Gregory's Moving & Delivery Co | Delivery Fee for furniture
73379.49