## Sheet1
Annotated Milestones
Organization: Invade
Project Title: Invade Housing
Quarter: 4
Milestones were sent to each participant after receiving a notice of award. Please copy and paste these milestones and due dates into the first and second columns. Please upload any supplemental materials through the quarterly reporting form.
Quarter 1 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Description (Please provide one to two sentence of description include details like who, what, where, when, and how).
EXAMPLE: Hire staff | EXAMPLE: January 1, 2024 | Yes | EXAMPLE: Jane Doe was hired into the Peer Position at ARORP on 2/28/23 at a salary of $55,000.
Purchase property and tiny house | 2024-12-01 | Complete | Resident House purchased for $435,000 on August 21, 2023 and tiny home purchased for $26,152.20 on October 20, 2023
Launch New Facility | 2024-12-01 | Complete | Residents moved into new property on August 28, 2023, classes also began on this date
Develop Data tracking system | 2024-12-01 | Complete | Uploaded into the quarterly reporting form
Submit first ARORP report | 2024-12-01 | Complete | Submitted on 12/19/23 (emailed on 12/1/23)
Quarter 2 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Operate at full capacity |  | Yes | House is currently at full-capacity including 10 residents and 1 house leader
Provide update on housing |  | Yes | We stay at full-capacity and have a wait list for those seeking to come for treatment.
Attend annual ARORP evaluation meeting |  | Yes | attended eval meeting in Oct, 2024
Submit annual ARORP report |  | Yes | annual reported was submitted
Quarter 3 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Operate at full capacity |  | Yes | House is at full capacity. We have 10 ARORP beds at main facility and 8 at step out. A few of our graduates will move to step-out while one graduate who is currenlty at step-out is in the process of moving to work at another ministy as house leader.
Provide update on housing |  | Yes | We stay at full-capacity and have a wait list for those seeking to come for treatment.
Attend annual ARORP evaluation meeting |  | Yes
Submit annual ARORP report |  | Yes
Quarter 4 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Operate at full capacity |  | Yes | House is at full capacity. We have 10 ARORP beds at main facility and 8 As residents complete 9 months they have the option to move to our step-out facility.
Provide update on housing |  | Yes | We stay at full-capacity and have a wait list for those seeking to come for treatment.
Attend annual ARORP evaluation meeting |  | Yes | completed in Oct 2024
Submit annual ARORP report |  | Yes | report was submitted but in wrong format..has been corrected