## Sheet1
Annotated Milestones
Organization: | mhp.si
Project Title: | 23-226 Arkansas Take Back - MHP/Team SI
Quarter: | 2025-01-04
Milestones were sent to each participant after receiving a notice of award. Please copy and paste these milestones and due dates into the first and second columns. Please upload any supplemental materials through the quarterly reporting form.
Quarter 1 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Description (Please provide one to two sentence of description include details like who, what, where, when, and how).
EXAMPLE: Hire staff | EXAMPLE: January 1, 2024 | Yes | EXAMPLE: Jane Doe was hired into the Peer Position at ARORP on 2/28/23 at a salary of $55,000.
Develop & Launch Take Back Campaign | 2024-03-31 | Yes | Developed and launched strategy for targeted social media advertising, retargeting, mass market advertising, video content, promotional and educational materials, and PR activities.
Develop Data Tracking System | 2024-03-31 | Yes | Developed Data Tracking System
Host Take Back Website & Complete Requested Updates | 2024-03-31 | Yes | Hosted website and completed periodic updates
Quarter 2 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Launch Take Back Campaign | 2024-04-27 | Yes | Developed and launched a targeted campaign utilizing paid digital media, mass market advertising, video content, promotional and educational materials, and PR activities in order to promote the spring Take Back event.
Host Take Back Website & Complete Requested Updates | 2024-06-30 | Yes | Hosted website and completed periodic updates
Submit Q1 & Q2 ARORP report covering January 1, 2024 to June 30, 2024 | 2024-07-15 | Yes | Q1 and Q2 report was submitted
Quarter 3 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Continue Take Back Campaign | 2024-09-30 | Yes | Developed and launched a targeted campaign utilizing paid digital media, mass market advertising, video content, promotional and educational materials, and PR activities in order to promote the fall Take Back event.
Host Take Back Website & Complete Requested Updates | 2024-09-30 | Yes | Hosted website and completed periodic updates
Submit Q3 ARORP report covering July 1, 2024 to Sept. 30, 2024 | 2024-10-15 | Yes | Q3 report was submitted
Quarter 4 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Complete 3 Take Back videos | 2024-10-15 | Yes | 3 videos created to promote "Monitor, Secure, Dispose" were completed on 8/5.
Continue Take Back Campaign | 2024-12-31 | Yes | Developed and launched a targeted campaign utilizing paid digital media, mass market advertising, video content, promotional and educational materials, and PR activities in order to promote the fall Take Back event.
Host Take Back Website & Complete Requested Updates | 2024-12-31 | Yes | Hosted website and completed periodic updates
Attend annual ARORP evaluation meeting | Scheduled by ARORP | Yes | Annual evaluation was attended on April 28th.
Submit Q4 ARORP report covering July 1, 2024 to Sept. 30, 2024 | 2025-01-15 | Yes | Q4 report was submitted