## Pre-Launch (Now – June 2026)

- Now–June 2026:

  - Begin outreach, job posting, and application review

  - Conduct interviews and finalize selections

## July 2026

### By July 1, 2026

- All employees hired

### July 1–19, 2026

- Employee onboarding

- Prepare for mandatory PREP training (travel/logistics)

### Mandatory 2-Week PREP Training in Little Rock

- Week 1: July 20–24, 2026 (8 AM–5 PM)

- Week 2: July 27–31, 2026 (8 AM–5 PM)

## August–September 2026

- Attend all mandatory school district trainings (as scheduled by district)

- Begin school site relationship-building

- Conduct programming for August 31st is International Overdose Awareness Day

- Host Education Meeting for Parents

- Launch development of the Prevention Coalition (recruit members, schedule kickoff)

## October–December 2026

- Conduct regular prevention programming

- Conduct Peer Recovery Groups

- October is Substance Misuse Prevention Month

- Conduct Red Ribbon Week Programming

- Hold monthly coalition meetings

- Quarterly Report #1 due: End of Q4 2026 (Dec 31)

## January–March 2027

- Continue programming and coalition activities

- Conduct Peer Recovery Groups

- Hold monthly coalition meetings

- Attend all required school trainings (if additional sessions occur)

- Quarterly Report #2 due: End of Q1 2027 (Mar 31)

## April–June 2027

- Maintain programming and coalition work

- National Prevention Week

- Conduct Peer Recovery Groups

- Hold monthly coalition meetings

- Conduct mid-year review with school partners

- Quarterly Report #3 due: End of Q2 2027 (Jun 30)

## July–September 2027

- Prep for new school year

- Attend annual school trainings

- Refresh coalition goals for the new cycle

- Conduct Peer Recovery Groups

- Hold monthly coalition meetings

- Annual Evaluation (program-wide): Summer 2027 (date TBD)

- Quarterly Report #4 due: End of Q3 2027 (Sept 30)

## October–December 2027

- Conduct regular prevention programming

- Conduct Peer Recovery Groups

- October is Substance Misuse Prevention Month

- Conduct Red Ribbon Week Programming

- Hold monthly coalition meetings

- Quarterly Report #1 due: End of Q4 2027 (Dec 31)

## January–March 2028

- Continue programming and coalition activities

- Conduct Peer Recovery Groups

- Hold monthly coalition meetings

- Attend all required school trainings (if additional sessions occur)

- Quarterly Report #2 due: End of Q1 2028 (Mar 31)

## April–June 2028

- Maintain programming and coalition work

- National Prevention Week

- Conduct Peer Recovery Groups

- Hold monthly coalition meetings

- Conduct mid-year review with school partners

- Quarterly Report #3 due: End of Q2 2028 (Jun 30)

## Ongoing (Annually)

- Annual evaluation each year

- Attend all mandatory school trainings

- Conduct Peer Recovery Groups

- Quarterly reporting at the end of each calendar quarter

- Maintain active prevention coalition with monthly/quarterly meetings