## Sheet1
Annotated Milestones
Organization: Renewal Ranch
Project Title: Renewal Ranch Housing
Quarter: Quarter 4 of Year 2 (2025 Q3)
Milestones were sent to each participant after receiving a notice of award. Please copy and paste these milestones and due dates into the first and second columns. Please upload any supplemental materials through the quarterly reporting form.
Quarter 1 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Description (Please provide one to two sentence of description include details like who, what, where, when, and how).
Complete Construction | 2025-01-15 | Complete | All construction was completed prior to December 1, 2024. We began moving Residents into the facility after December 1, 2024.
Provide Update on Peer Services | 2025-01-15 | Complete | Renewal Ranch staff has continued to add Peer Support services to our program. We currently have two staff leaders who have successfully passed the core level test (offered through NAADAC, the Association of Addiction Professionals) and are now certified Peer Support Specialists. Certification date was September 12,2024. We also have two additional staff members who are Peers in Training and working toward becoming certified Peer Support Specialists. ARORP is only funding two peer support specialists. Our team interacts and provides services to our Residents every day. See the accompanying Quarterly Report for more detials.
Attend annual ARORP evaluation meeting | 2025-01-15 | Complete | This meeting occurred on December 17, 2024, with Kirk Lane, Tenesha Barnes, and Joy Spence in attendance from ARORP. Audit was successful with a few follow-on tasks assigned to Renewal Ranch. (See accompanying Quarterly Report for more details.) Renewal Ranch will return unallocated funds sometime after January 17, 2025.
Submit Q5 ARORP report | 2025-01-15 | Complete | Quarterly Report submitted via ARORP portal on January 14, 2025.
Quarter 2 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Operate at full capacity | 2025-04-15 | Complete | We have steadily added to the population of Residents since the facility opened in December 2025. Our current population, as of this report, is 38 of our 42 beds are occupied. There are four open beds, and we continue taking applications for new Residents on a regular basis. There are 40 resident beds and 2 staff beds available. Total number of people in ARORP funded beds throughout the quarter was 64.
Provide Update on Peer Services | 2025-04-15 | Complete | Renewal Ranch staff has continued to add Peer Support services to our program. We currently have two staff leaders who have successfully passed the core level test on September 12, 2024, and are now certified Peer Support Specialists. We also have two additional staff members who are Peers in Training and working toward becoming certified Peer Support Specialists. ARORP is only funding two peer support specialists. Our team of addiction recovery specialists interacts with all Residents every day, teaching them to live their lives apart from the bondage of addiction. We conduct one-on-one meetings with Residents, counsel them, assist with job placement, facilitate classes, teach them budgeting skills, provide courtroom and medical advocacy, and many other activities and services.
Submit Q6 ARORP report | 2025-04-15 | Complete | Quarterly Report submitted via ARORP portal on April 14, 2025.
Quarter 3 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Operate at full capacity | 2025-07-15 | Complete | We have steadily added to the population of Residents since the facility opened in December 2025. Our current population, as of this report, is 42 of our 42 beds are occupied. We will continue taking applications for new Residents as beds become available. There are 40 resident beds and 2 staff beds available. Total number of people in ARORP funded beds throughout the quarter was 62.
Provide Update on Peer Services | 2025-07-15 | Complete | Renewal Ranch staff has continued to add Peer Support services to our program. We currently have three staff leaders who have successfully passed the core level test on September 12, 2024 and May 6th, 2025, and are now certified Peer Support Specialists. We also have one additional staff member who is a Peer in Training and working toward becoming a certified Peer Support Specialist. ARORP is only funding two peer support specialists. Our team of addiction recovery specialists interacts with all Residents every day, teaching them to live their lives apart from the bondage of addiction. We conduct one-on-one meetings with Residents, counsel them, assist with job placement, facilitate classes, teach them budgeting skills, provide courtroom and medical advocacy, and many other activities and services.
Submit Q7 ARORP report | 2025-07-15 | Complete | Quarterly Report submitted via ARORP portal on July 15, 2025.
Quarter 4 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Operate at full capacity | 2025-10-15 | Complete | We have steadily added to the population of Residents since the facility opened in December 2025. Our current population, as of this report, is 42 of our 42 beds are occupied. We will continue taking applications for new Residents as beds become available. There may be turnover so occupancy can vary. We work diligently to maintain full occupancy. There are 40 resident beds and 2 staff beds available. Total number of people in ARORP funded beds throughout the quarter was 69.
Provide Update on Peer Services | 2025-10-15 | Complete | Renewal Ranch staff has continued to add Peer Support services to our program. We currently have three staff leaders who have successfully passed the core level test on September 12, 2024 and May 6th, 2025, and are now certified Peer Support Specialists. We also have one additional staff member who is a Peer in Training and working toward becoming a certified Peer Support Specialist. ARORP is only funding two peer support specialists. Our team of addiction recovery specialists interacts with all Residents every day, teaching them to live their lives apart from the bondage of addiction. We conduct one-on-one meetings with Residents, counsel them, assist with job placement, facilitate classes, teach them budgeting skills, provide courtroom and medical advocacy, and many other activities and services.
Submit Q8 ARORP report | 2025-10-15 | Complete | Quarterly Report submitted via ARORP portal on October 15, 2025.