## Sheet1
Annotated Milestones
Organization: |  |  | CADCA
Project Title: |  |  | CADCA City and County Training ARORP22-05 PID 595
Quarter: |  |  | Jan-Mar 2025
Milestones were sent to each participant after receiving a notice of award. Please copy and paste these milestones and due dates into the first and second columns. Please upload any supplemental materials through the quarterly reporting form.
Quarter 1 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Description (Please provide one to two sentence of description include details like who, what, where, when, and how).
EXAMPLE: Hire staff | EXAMPLE: January 1, 2024 | Yes | EXAMPLE: Jane Doe was hired into the Peer Position at ARORP on 2/28/23 at a salary of $55,000.
Hire master trainer, trainers, and designers | 2023-05-01 | Yes | Complete, Trainers contracted.
Update on outreach/promotion | 2023-05-01 | Yes | Initial webinar Feb. 16 2023, promoting COPE application opportunity. Promotion of AAC & AML live/recorded webinars will commence when coordination is finalized.
Update on online module development | 2023-05-01 | Yes | Module content is outlined, PPTs being reviewed by CADCA internally the week of May 5th and plan to be sent to ARORP by May 12th.
Develop data tracking instrument | 2023-05-01 | Yes | Complete, Monday.com project tracking; Sogolytics Coalition Readiness Assessment instrument.
Submit first ARORP report | 2023-05-01 | Yes | Complete.
Quarter 2 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Present informational webinar to city and county officials | 2023-08-01 | Yes | AML webinar held on May 24. Waiting on information on AAC collaborations, currently anticipating September 7 Judges meeting.
Present test training at Association of Arkansas Counties Conference | 2023-08-01 | No | Anticipated September 7 Judges meeting
Present test training at Arkansas Municipal League Conference | 2023-08-01 | Yes | Full conference plenary delivered June 14, breakout session presented June 15.
Update on outreach/promotion | 2023-08-01 | Yes | Module 1 is completed and has been sent to ARORP for review. Upon approval, the module will be posted on CADCA’s LMS, Docebo, and information on accessing the training will be made available via ARORP’s website. CADCA will coordinate with ARORP on preferences for notifying AML and AAC contacts.
Host training materials on ARORP’s website | 2023-08-01 | In Progress
Submit quarterly ARORP report | 2023-08-01 | Yes | Complete.
Quarter 3 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Provide updates to AAC and AML on progress | 2023-12-01 | Yes | Met with ARORP to discuss lower sign-up, offer further promotional materials (Oct 12). Currently designing web form for ARORP review.
Viewership and enrollment data is on the attached Data Tracking Tool.
Submit quarterly ARORP report | 2023-12-01 | Yes | Complete.
Quarter 4 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Provide update on services provided | 2024-03-01 | Yes | Establish web-based module sign-up process. First version sent for review 11/6/2023. Feedback incorporated and sent 11/15/2023. Approved and published 11/27/2023. Establish module completion quiz. First version sent for review 11/17/2023. Approved and published 11/27/2023.
Attend ARORP annual evaluation meeting | 2024-03-01 | Yes | In March of 2024, the CADCA and ARORP teams determined that the modules created were not accessible to the target audience. To remedy this, CADCA committed to revising the content and structure of the modules based on project feedback. Based on this adjustment, ARORP has added an additional set of milestones (6th set of milestones) to reflect the revision plan agreed upon by ARORP and CADCA. The annual evaluation was scheduled to be held at end of these milestones in order to evaluate these revisions.
Submit quarterly ARORP report. | 2024-03-01 | Yes | Complete.
Quarter 5 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Promote and update resources on ARORP’s website | 2024-04-30 | Yes | CADCA in discussions with ARORP to adjust milestones, strategy for promotion.
Present training virtually and in-person at the Association of Arkansas Counties Conference | 2024-04-30 | No | While information was shared with AAC, it was not possible to arrange a presentation at the Sept 2023 Judges meeting, and an alternative occasion for presentation was not confirmed.
Present training virtually and in person at the Arkansas Municipal League Conference | 2024-04-30 | Yes | Webinar for AML held May 2023 and conference presentations delivered June 2023.
Submit final report to ARORP | 2024-04-30 | No | CADCA in discussions with ARORP to adjust milestones, strategy for promotion.
Final Quarter milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Complete 4 module videos | 2025-03-31 | Yes | “CADCA Arkansas – Awareness” video script submitted May 28, 2024. - Fourth video finalized and delivered February 14, 2025. “Recover and Rebuild”, “Find Solutions”, and “Access Settlement Dollars” scripts submitted September 12, 2024 with approved production versions sent October 24, 2024.Production version of “Awareness” submitted August 5. 2024; Recover and Rebuild” submitted November 18, 2024; “Find Solutions” submitted December 3, 2024. Final version of “Awareness” delivered August 26. 2024, “Recover and Rebuild” delivered December 9, 2024; “Find Solutions” delivered December 30, 2024. - Before finalization of fourth video, we will be coordinating a new script and re-recording of voiceover narration due to significant edits. This work is to be completed in Q1 2025.- The addition of more specific information for the audience than the original scripts offered has also established the need for a fifth video, which will be scripted and produced in Q1 2025. - Fifth video, “How You Can Support Community projects”. draft script and storyboard shared March 3, draft video shared March 24, and final video shared March 25, 2025.
Support module promotion and roll out | 2025-03-31
Submit final report to ARORP | 2025-04-15 | Yes