## Y1
Annotated Milestones
Organization: | Western Arkansas Counseling and Guidance Center
Project Title: | Horizon Renewal Center 23-026
Quarter: YEAR 1
Milestones were sent to each participant after receiving a notice of award. Please copy and paste these milestones and due dates into the first and second columns. Please upload any supplemental materials through the quarterly reporting form.
Quarter 1 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Description (Please provide one to two sentence of description include details like who, what, where, when, and how).
EXAMPLE: Hire staff | EXAMPLE: January 1, 2024 | Yes | EXAMPLE: Jane Doe was hired into the Peer Position at ARORP on 2/28/23 at a salary of $55,000.
Provide update on renovations | Prior to July 1, 2023 | Yes | Renovations met delays due to unforeseen issues regarding the water supply and pressure not meeting coding requirements. Nabholz was able to find the most reasonable path to allow for Horizon to have its own water tank and water supply; WACGC was able to aquire the additional funds to cover the unforeseen cost that was over the awarded amount.
Launch residential treatment services | Prior to July 1, 2023 | Yes, late | Due to the issues regarding delayed renovations, residential treatment services were not started by the estimated milestone date. Residential treatment services were launched August 19, 2024.
Begin staff training and licensure | Prior to July 1, 2023 | Yes | Few staff members were hired or transferred to the Horizon Renewal Center project at this time, again due to the delayed renovation schedule. Kasey Wilson oversaw the project at this point before selecting Graham Baty to oversee Horizon Renewal as Program Director 3/15/24 at a salary of $45,000. Additional staff were hired on for roles of MHP, Peer Specialist, ADC, and Admissions Intake Coordinator.
Develop data tracking system | Prior to July 1, 2023 | Yes | Tye Brown, APR developed data tracking spreadsheets to comply with ARORP requests and reporting efforts.
Submit first quarterly ARORP report | Submit July 1, 2023 | Yes | Initial report was submitted by Kasey Wilson; Tye Brown re-submitted first quarterly ARORP report in March 2024.
Quarter 2 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Complete renovations | Prior to August 1, 2023 | Yes, late | Renovations were delayed due to the issues regarding the water tank. Per Nabholz, the water tank that would supply the adequate water pressure for fire suppression, as well as the insulation cover to prevent the tank from freezing, were both backordered. Both the tank and the insulation cover were vital components in the renovations process to ensure the safety of residents and staff, as well as meeting local coding ordinances. The tank was not delivered until 1/3/2024; the cover for insulation was delivered 3/4/2024. Another delay came when waiting for Northwest to come install everything correctly, which was completed on 3/27/2024. During that time between delivery and installation, all final inspections were completed by state and city personnel, including the Fire Marshalls running tests on the sprinkler system. Once all inspections were completed, licensure walkthroughs began for CARF accreditation and SUD licensures. CARF accreditation was obtained 4/8/2024. On 5/8/2024, final licensure walkthroughs were completed.
Provide update on services | Prior to October 1, 2023 | Yes, late | Services have yet to begin due to the delays involving renovations.
Submit quarterly ARORP report | Submit October 1, 2023 | Yes | Initial report was submitted by Kasey Wilson; Tye Brown re-submitted second quarterly ARORP report in March 2024.
Quarter 3 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Complete staff training and licensure | Prior to January 1, 2024 | Yes | Graham Baty appointed as Program Director 3/15/24 at a salary of $45,000. Lenel Scharbor (moved to Admissions Coordinator 5/5/2024 at $18.50/hr), John Hockaday (hired 3/18/24 as a Peer Specialist at $13/hr), Mark Hadlock (hired 3/25/24 as a CIT/QBHP at $16/hr) were all brought on to fulfill roles at Horizon. Final licensures are pending supervisor review.
Provide update on services | Prior to January 1, 2024 | Yes | Services have yet to begin due to the delays involving renovations.
Submit quarterly ARORP report | Submit January 1, 2024 | Yes | Initial report was submitted by Kasey Wilson; Tye Brown re-submitted third quarterly ARORP report in March 2024.
Quarter 4 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Obtain CARF accreditation | Prior to April 1, 2024 | Yes | CARF Accreditation obtained 4/8/2024; SUD license walkthrough and review completed on 5/8/2024; currently awaiting Supervisor Approval for the invoice of licensure to pay.
Provide update on services | Prior to April 1, 2024 | Yes | Services have yet to begin due to the delays involving renovations.
Attend annual ARORP evaluation meeting | Prior to April 1, 2024 | Yes | Marla Kendrick, Rachel Abshere, Gina Miesner, Joseph Lee, Graham Baty, and Tye Brown will attend evaluation meeting scheduled for 5/28/2024.
Submit annual ARORP report | Submit April 1, 2024 | Yes | Submitted by Tye Brown in March 2024.

## Y2
Annotated Milestones
Organization: | Western Arkansas Counseling and Guidance Center
Project Title: | Horizon Renewal Center 23-026
Quarter: YEAR 2
Milestones were sent to each participant after receiving a notice of award. Please copy and paste these milestones and due dates into the first and second columns. Please upload any supplemental materials through the quarterly reporting form.
Quarter 1 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Description (Please provide one to two sentence of description include details like who, what, where, when, and how).
EXAMPLE: Hire staff | EXAMPLE: January 1, 2024 | Yes | EXAMPLE: Jane Doe was hired into the Peer Position at ARORP on 2/28/23 at a salary of $55,000.
Provide update on treatment and recovery services | June 30, Annually | No | The HRC ribbon cutting ceremony took place June 14th and was attended by community partners, local law enforcement, WAGC staff, and ARORP representatives. Services have not begun as final preparations are completed. Treatment and recovery services will include: provide health and behavioral health monitoring, medication management, nutritional management, relapse prevention, counseling, peer support, education, supportive employment.
Submit first quarterly ARORP report | July 15, Annually | Yes | Submitted by Tye Brown 6/24/2024.
Quarter 2 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Continue treatment and recovery services | September 30, Annually | Yes | Horizon Renewal Center welcomed its first admissions August 19th, immediately providing services to individuals living with SUD and OUD. Since opening, Horizon Renewal Center has successfully graduated 10 individuals from the treatment program. Our diverse group of graduates includes those referred by DCFS, the court system, federal probation, self-referrals, and our Crisis Stabilization Unit. This early success highlights the effectiveness of our tailored approach to treatment, demonstrating our commitment to supporting individuals from various backgrounds on their journey to recovery. Services rendered to individuals during their stay with us include group and individual counseling, peer support, case management, access to psychiatric care and medication management. Participants engage in a variety of other daily enrichment activities such as equine therapy, art therapy, yoga, and therapeutic outings to some of the most serene countryside in Arkansas. We look forward to continuing to empower more individuals to achieve and sustain remission from substance use disorder as we expand our impact in the community.
Submit quarterly ARORP report | October 15, Annually | Yes | Submitted by Tye Brown 10/15/2024.
Quarter 3 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Continue treatment and recovery services | December 31, Annually
Submit quarterly ARORP report | January 15, Annually
Quarter 4 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Continue treatment and recovery services | March 31, Annually
Submit quarterly ARORP report | April 15, Annually
Attend annual ARORP evaluation meeting | Scheduled by ARORP

## Y3
Annotated Milestones
Organization: | Western Arkansas Counseling and Guidance Center
Project Title: | Horizon Renewal Center 23-026
Quarter: YEAR 3
Milestones were sent to each participant after receiving a notice of award. Please copy and paste these milestones and due dates into the first and second columns. Please upload any supplemental materials through the quarterly reporting form.
Quarter 1 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Description (Please provide one to two sentence of description include details like who, what, where, when, and how).
EXAMPLE: Hire staff | EXAMPLE: January 1, 2024 | Yes | EXAMPLE: Jane Doe was hired into the Peer Position at ARORP on 2/28/23 at a salary of $55,000.
Continue treatment and recovery services | June 30, Annually
Submit first quarterly ARORP report | July 15, Annually | Yes
Quarter 2 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Continue treatment and recovery services | September 30, Annually
Submit quarterly ARORP report | October 15, Annually
Quarter 3 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Continue treatment and recovery services | December 31, Annually
Submit quarterly ARORP report | January 15, Annually
Quarter 4 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Continue treatment and recovery services | March 31, Annually
Submit quarterly ARORP report | April 15, Annually
Attend annual ARORP evaluation meeting | Scheduled by ARORP

## Y4
Annotated Milestones
Organization: | Western Arkansas Counseling and Guidance Center
Project Title: | Horizon Renewal Center 23-026
Quarter: YEAR 4
Milestones were sent to each participant after receiving a notice of award. Please copy and paste these milestones and due dates into the first and second columns. Please upload any supplemental materials through the quarterly reporting form.
Quarter 1 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Description (Please provide one to two sentence of description include details like who, what, where, when, and how).
EXAMPLE: Hire staff | EXAMPLE: January 1, 2024 | Yes | EXAMPLE: Jane Doe was hired into the Peer Position at ARORP on 2/28/23 at a salary of $55,000.
Continue treatment and recovery services | June 30, Annually
Submit first quarterly ARORP report | July 15, Annually | Yes
Quarter 2 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Continue treatment and recovery services | September 30, Annually
Submit quarterly ARORP report | October 15, Annually
Quarter 3 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Continue treatment and recovery services | December 31, Annually
Submit quarterly ARORP report | January 15, Annually
Quarter 4 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Continue treatment and recovery services | March 31, Annually
Submit quarterly ARORP report | April 15, Annually
Attend annual ARORP evaluation meeting | Scheduled by ARORP

## Y5
Annotated Milestones
Organization: | Western Arkansas Counseling and Guidance Center
Project Title: | Horizon Renewal Center 23-026
Quarter: YEAR 5
Milestones were sent to each participant after receiving a notice of award. Please copy and paste these milestones and due dates into the first and second columns. Please upload any supplemental materials through the quarterly reporting form.
Quarter 1 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Description (Please provide one to two sentence of description include details like who, what, where, when, and how).
EXAMPLE: Hire staff | EXAMPLE: January 1, 2024 | Yes | EXAMPLE: Jane Doe was hired into the Peer Position at ARORP on 2/28/23 at a salary of $55,000.
Continue treatment and recovery services | June 30, Annually
Submit first quarterly ARORP report | July 15, Annually | Yes | Submitted by Tye Brown 6/24/2024.
Quarter 2 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Continue treatment and recovery services | September 30, Annually
Submit quarterly ARORP report | October 15, Annually
Quarter 3 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Continue treatment and recovery services | December 31, Annually
Submit quarterly ARORP report | January 15, Annually
Quarter 4 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Continue treatment and recovery services | March 31, Annually
Submit quarterly ARORP report | April 15, Annually
Attend annual ARORP evaluation meeting | Scheduled by ARORP