## Sheet1
Annotated Milestones
Organization: | WYSAC
Project Title: | ARORP Evaluation
Quarter: | Year Two First Quarter (October through December 2024)
Milestones were sent to each participant after receiving a notice of award. Please copy and paste these milestones and due dates into the first and second columns. Please upload any supplemental materials through the quarterly reporting form.
Quarter 1 Milestones (Copy and paste the milestones provided by ARORP into this column) (Jan - Mar 2025) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Description (Please provide one to two sentence of description include details like who, what, where, when, and how).
EXAMPLE: Hire staff | EXAMPLE: January 1, 2024 | Yes | EXAMPLE: Jane Doe was hired into the Peer Position at ARORP on 2/28/23 at a salary of $55,000.
Update on collecting transparency evaluation data | 2024-12-31 | Yes | The second round of transparency scoring and brief were completed. WYSAC worked with ARORP to identify limitations, and we will create an updated transparency evaluation plan and scoring rubric in the next quarter.
Analyze and provide process data for ARORP quarterly briefs. Provide a quarterly brief. | 2024-12-31 | Yes | Process data for the previous quarter was analyzed and put into the quarterly report during October and November, 2024. The report was finalized and published on 11/18/24.
Ongoing Redcap technical assistance | 2024-12-31 | Yes | WYSAC provided technical assistance on REDCap to grantees throughout the quarter. We also worked on a complete update to the system, making it easier and more accurate. The REDCap update will be finished in the second quarter.
Create a qualitative impact assessment research design | 2024-12-31 | Yes | The QuIP design was developed and finalized in December, 2024. It will focus on housing projects and include up to 15 interviews with individuals who received housing services funded by ARORP. Tools will be developed in the spring of 2025 and interviews conducted in the summer of 2025.
Submit WYSAC quarterly report | 2025-01-15 | Yes | WYSAC submitted the quarterly report and these milestones on January 15, 2025.
Quarter 2 Milestones (Copy and paste the milestones provided by ARORP into this column) (Apr -June 2025) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Collect transparency evaluation data and create a fact sheet | 2025-03-31 | Yes | Evaluators collected transparency data from five independent, anonymous reviewers who assessed project documentation and reporting against established criteria. Their feedback was synthesized into a report that detailed transparency scores and highlighted key strengths and areas for improvement. Completed in February 2025.
Analyze and provide process data for ARORP quarterly briefs. Provide a quarterly brief. | 2025-03-31 | Yes | The quarterly brief was provided on July 9, 2025. Delay in reporting was due to updates in the REDCAP system and changes in the data collection process.
Create an annual evaluation report based upon the evaluation plan | 2025-03-31 | Yes | We completed the annual report, but we will work in April to perfect it for the Advisory Board and publication.
Implement the qualitative impact assessment | 2025-03-31 | No | In collaboration with the ARORP team, we decided to put the QuIP design on the back burner and implement a gap assessment mapping project instead. Evaluators have begun collecting data and creating a database for the project.
Ongoing Redcap technical assistance | 2025-03-31 | Yes | WYSAC provided continuous support for vendors in using the REDCap system, assisting approximately 200 organizations with collecting and uploading their data. The submitted information was then analyzed and incorporated into the quarterly report.
Submit WYSAC quarterly report (REDCAP) | 2025-04-15 | Yes, late | Current WYSAC system was completed on 5/27/2025. WYSAC submitted the quarterly report and these milestones using this current project 23-120 on July 9, 2025.
Quarter 3 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Analyze and provide process data for ARORP quarterly reports. Provide a quarter brief. | 2025-06-30 | Yes | Data has been collected, ARORP personnel requested a hold on the report to review and reanalyze data. Data were collected by the due date of June 30, 2025, and researchers finalized the report on October 2, 2025.
Implement the qualitative impact assessment | 2025-06-30 | Yes | In collaboration with the ARORP team, we decided to put the QuIP design on the back burner and implement a gap assessment mapping project instead. Evaluators have begun collecting data and creating a database for the project.
Ongoing Redcap technical assistance | 2025-06-30 | Yes | WYSAC provided continuous support for vendors in using the REDCap system, assisting approximately 200 organizations with collecting and uploading their data. The submitted information was then analyzed and incorporated into the quarterly report.
Submit WYSAC quarterly report | 2025-07-15 | Yes | WYSAC submitted the quarterly report and these milestones on July 9, 2025. This date is correct. The current program was completed and both Quarter 1 and Quarter 2 milestones were created on the same day and uploaded together.
Quarter 4 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Analyze and provide process data for ARORP quarterly briefs. Provide a quarterly brief. | 31-Sept-25 | No | Data have been collected, and researchers working to finalize this quarter’s report as of October 23, 2025.
Analyze the qualitative impact assessment | 31-Sept-25 | Yes | In consultation with the ARORP team, evaluators determined that it would be more strategic to temporarily set aside the QuIP design and, in its place, undertake a comprehensive gap assessment mapping initiative. This project focused on systematically identifying areas across the state where treatment and recovery services remain limited or absent. As part of this effort, evaluators developed detailed county-level maps that visually highlight disparities in access to both treatment and recovery resources, providing stakeholders with a clearer picture of regional service gaps and unmet needs. Beyond the mapping work, evaluators also advanced several complementary studies. This included 1) qualitative research and reporting of the structure, practices, and lived experiences within faith-based men’s recovery facilities, offering insights into how these programs contribute to recovery pathways, and 2) a qualitative study examining a pilot initiative to explore innovative ways of integrating prevention and recovery supports within educational settings, including both schools and universities. Both reports were finalized and submitted.
Collect transparency evaluation data and create a fact sheet | 31-Sept-25 | Yes | Evaluators collected transparency data from five independent, anonymous reviewers who assessed project documentation and reporting against established criteria. Their feedback was synthesized into a report that detailed transparency scores and highlighted key strengths and areas for improvement. Completed in September 2025.
Ongoing Redcap technical assistance | 31-Sept-25 | Yes | WYSAC provided continuous support for vendors in using the REDCap system, assisting approximately 200 organizations with collecting and uploading their data. The submitted information was then analyzed and incorporated into the quarterly report.
Submit WYSAC quarterly report | 2025-10-15 | Yes, late | WYSAC submitted the quarterly report and these milestones on October 24, 2025.
Attend WYSAC/ARORP annual evaluation meeting | 2025-10-06 | Yes | At the annual evaluation meeting, all individuals assigned to the project were asked to provide a comprehensive set of documentation to ensure transparency and accountability. Specifically, each team member was required to submit monthly paystubs verifying compensation, detailed monthly percentages reflecting the proportion of their time allocated to the project, and all receipts for expenses directly tied to project activities. In addition, participants were instructed to prepare a full written description of their assigned duties and responsibilities, along with an account of the tasks they completed over the course of the reporting period. This information was requested to create a clear record of contributions, support accurate financial tracking, and provide ARORP with a complete documentation of how project resources were utilized.