## Sheet1
Annotated Milestones
Organization: | Carter's Crew
Project Title: | Carter's Crew Treatment, Prevention and Recovery Program
Quarter: | Quarter 2 2025
Milestones were sent to each participant after receiving a notice of award. Please copy and paste these milestones and due dates into the first and second columns. Please upload any supplemental materials through the quarterly reporting form.
Quarter 3 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Description (Please provide one to two sentence of description include details like who, what, where, when, and how).
EXAMPLE: Hire staff | EXAMPLE: January 1, 2024 | Yes | EXAMPLE: Jane Doe was hired into the Peer Position at ARORP on 2/28/23 at a salary of $55,000.
Hire Educator, case manager and peer recovery specialist | 2024-09-30 | yes | Jahquette Davis was hired as the peer recovery specialist on July 1, 2024 . Jennifer Hall was hired as the substance abuse educator on July 1, 2024. Shana Flenoy was hired as the case manager on July 17,2024. Salaries are as written in the grant.
Complete 2 modules | 2024-09-30 | yes | Modules were submitted for review prior to going public on September 11, 2024.
Launch program | 2024-09-30 | yes | Program was launched on August 1, 2024.
Develop data tracking system | 2024-09-30 | yes | Redcap system is provided by ARORP.
Quarter 4 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Continue prevention services | 2024-12-31 | yes | The team has continued with education and prevention services for our referrals. The team has also worked with the school districts and are delivering the curriculum during a dedicated school period.
Complete 3 modules | 2024-12-31 | Yes,late | Modules are completed in house with my leadership. I was out of the office for two weeks at the end of December. We also had some scheduling conflicts with my schedule and the moderator. We are currently editing and finalizing the modules. Will be completed prior to the end of the month.
Submit quarterly ARORP report | 2025-01-15 | yes | Report is ready to be submitted and will be done by 1/15/2025. Redcap is down for maintenance until after January 10th.
Quarter 1 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Continue prevention services | 2025-03-31 | Yes | The team has continued with education and prevention services for our referrals. The team has also worked with the school districts, colleges and other nonprofit agencies to deliver the curriculum. We have an additional request from Southwest High School for a recurring session with 9-12th grade.
Complete 3 modules | 2025-03-31 | Yes | We are ahead of schedule with this milestone. As of the time of the report all remaining modules have been created and submitted for review to the ARORP team.
Submit quarterly ARORP report | 2025-04-15 | Yes | Report is complete.
Quarter 2 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Continue prevention services | 2025-06-30 | yes | The team has continued with education and prevention services for our referrals. The team has also worked with the school districts, colleges and other nonprofit agencies to deliver the curriculum.
Complete 2 modules | 2025-06-30 | yes | All final modules were completed ahead of time in last quarter and submitted to ARORP team for review.
Submit quarterly ARORP report | 2025-06-30 | yes | Report is complete.