## Sheet1
Annotated Milestones
Organization: Riverview Hope Campus
Project Title: Riverview Hope Campus Peer Recovery Support
Quarter: 1
Milestones were sent to each participant after receiving a notice of award. Please copy and paste these milestones and due dates into the first and second columns. Please upload any supplemental materials through the quarterly reporting form.
Quarter 4 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Description (Please provide one to two sentence of description include details like who, what, where, when, and how).
EXAMPLE: Hire staff | EXAMPLE: January 1, 2024 | Yes | EXAMPLE: Jane Doe was hired into the Peer Position at ARORP on 2/28/23 at a salary of $55,000.
ARORP project start date | 2024-11-01 | Yes | Hired the Peer November 18th
Hire peer December 31, 2024 This project begins in the middle of the | 2024-12-31 | Yes | See note above
Submit first quarterly ARORP report | 2025-01-15 | Yes | Report will cover November 1, 2024 through December 31, 2024.
Quarter 1 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Continue peer services | 2025-03-31 | Yes | Teena our PR continued to provide peer services to the homeless. One thing we noticed is 85% of our touches to provide peer services were for the first time with that individual. Teena has started a recovery group, does a life skills class, and has provided court advocacy. Teena is most proud of talking to our many homeless about recovery. She has been providing a service that says they don't have to live a life like this, just by her presents.
Submit quarterly ARORP report | 2025-04-15 | Yes | Just made the deadline and submitted the day of
Develop data tracking system | 2024-12-31 | Yes | Developed and going well had it ready before the deadling
Quarter 2 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Continue peer services | 2025-06-30 | Yes | The peer is providing wonderful services and is being effective in our community
Submit quarterly ARORP report | 2025-07-15 | Yes | Submitted one day late. There was good data collected
Quarter 3 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Continue peer services | Sept 30, 2025 | Yes | Teena has continued to provide peer support services for the homeless. Last winter she passed her peer support test and is now a PRSS. Honing in on her skill of being a peer support specialist. She has provided vital support for many of individuals coming through our doors with substance use disorder or opioid use disorder. She has done a phenomenal job following up with her peers.
Annual review is scheduled | Nov. 7th 2025 | Yes | Attended on November 17, 2025