## Sheet1
Annotated Milestones
Organization: Hot Springs School District
Project Title: Peer Prevention
Quarter: 1 Year 2
Milestones were sent to each participant after receiving a notice of award. Please copy and paste these milestones and due dates into the first and second columns. Please upload any supplemental materials through the quarterly reporting form.
Quarter 1 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Description (Please provide one to two sentence of description include details like who, what, where, when, and how).
Provide update on prevention and recovery efforts | Prior to March 1, 2025 | yes | SERVICES PROVIDED: From January through March 2025, the Prevention Specialist worked with 15 students ages 12–17 who violated the school’s substance use policy, with zero reoffenses during the quarter. The specialist conducted five one-on-one sessions for students needing extra guidance and hosted one support meeting with four students. Additionally, the Hot Springs School District maintained two active Drug Free Youth Coalitions—each with 20 members at the Junior Academy and High School campuses—that met once this quarter with active elected officials. Coalition members also participated in a advocacy event at the Arkansas State Capitol to promote prevention awareness around gaming and substance use.
On January 8, 2025, Prevention Specialist joined the Rx Drug Prevention Community Advisory Board (CAB) for the Adolescent Rx Drug Misuse Prevention Project. This milestone reflects active involvement in guiding community-based strategies to prevent prescription drug misuse among adolescents.
On January 22, 2025, a high school student who had previously completed our prevention program recognized a peer showing early signs of substance use struggles and referred them to the Prevention Specialist. This milestone highlights the program’s growing impact in fostering a culture of care, accountability, and peer support that promotes a drug-free and positive school environment.
On February 11, 2025, a Drug Free Youth Coalition meeting was held on the High School campus with 25 participants, including the school nurse, staff members, law enforcement, and key community stakeholders. This milestone demonstrated strong collaboration and community engagement in supporting youth prevention and promoting a drug-free school environment.
On February 13, 2025, at the High School campus, Prevention Specialist created a unique Letterman Jacket design to promote substance use prevention. This creative milestone symbolizes students’ pride in living drug-free and highlights the specialist’s dedication to early intervention and inspiring a culture of prevention within the school community.
Submit first quarterly ARORP report | Prior to March 1, 2025 | yes | Submitted after March 1, 2025
Quarter 2 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Provide update on prevention and recovery efforts | Prior to June 1, 2025 | yes | SERVICES PROVIDED: From April through June 2025, the Prevention Specialist worked with 25 students ages 12–17 who violated the school’s substance use policy, with five students reoffending during the quarter. The specialist conducted five one-on-one sessions with students needing additional guidance and hosted one support meeting with three students in attendance. The Hot Springs School District maintained two active Drug Free Youth Coalitions—each with 20 members at the Junior Academy and High School campuses—that met twice this quarter with active elected officials. Additionally, Hot Springs School District students participated in the Region 8 Build a Better You Youth Conference at National Park College, where Hot Springs School District President of the Drug Free Youth Coalition led an interactive breakout session that united students from multiple schools to foster dialogue and empower youth leadership in promoting drug-free lifestyles on their campuses.
On March 11, 2025, Junior Academy and High School Drug Free Youth Coalition members visited the Arkansas State Capitol in collaboration with the Arkansas Problem Gaming and Gambling Council. This milestone offered students a valuable hands-on experience to advocate for prevention, learn about the connection between gaming, gambling, and substance use.
On April 8, 2025, at Hot Springs World Class High School, the Prevention Specialist hosted an award ceremony recognizing students who had previously violated the school’s substance use policy but successfully completed the program without reoffending. This milestone celebrated positive behavior change, reinforced accountability, and highlighted the program’s effectiveness in supporting students to make healthy, substance-free choices.
On April 8, 2025, the Prevention Specialist hosted a Drug Free Youth Coalition meeting at the High School campus with 33 participants, including the school nurse, staff members, law enforcement, and key community stakeholders. This milestone demonstrated continued community collaboration and engagement in supporting youth prevention and fostering a drug-free school environment.
On April 22, 2025, the Prevention Specialist planned and organized the Hot Springs Junior Academy Drug Prevention Conference at the school, successfully engaging 320 students. This milestone showcased the specialist’s leadership while educating students on the dangers of opioids and reinforcing the critical message: “One Pill Can Kill.”
On April 22, 2025, at Hot Springs Junior Academy, our Prevention Specialist guided Drug Free Youth Coalition members who are musicians in forming a band for the Drug Prevention Conference. With the specialist’s mentorship, the students performed an anti-drug song, demonstrating peer leadership, creativity, and a strong commitment to promoting a substance-free message within their school community.
On May 5, 2025, the Prevention Specialist organized and helped plan the Regional Prevention Conference at National Park College in partnership with our regional prevention provider. During the event, the President of our Drug Free Youth Coalition led an interactive breakout session, bringing together students from multiple schools to foster dialogue and empower youth leadership in promoting drug-free lifestyles on their campuses.
On May 13, 2025, the Prevention Specialist hosted a Drug Free Youth Coalition meeting at the High School campus with 21 participants, including the school nurse, staff members, law enforcement, and key community stakeholders. This milestone highlighted ongoing collaboration and engagement in supporting youth prevention and promoting a drug-free school environment.
On May 19, 2025, the Prevention Specialist attended the National Gaming and Gambling Conference in Toronto to gain a deeper understanding of student gaming addictions and the connections to substance use, such as using drugs to stay awake or engaging in risky online behaviors. This milestone provided critical insights into youth gaming habits, strengthened the specialist’s capacity to support at-risk students, and fulfilled continued education requirements in prevention and intervention strategies.
Submit Quarterly ARORP report | By June 1, 2025 | yes | Submitted after June 1, 2025
Quarter 3 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Provide update on prevention and recovery efforts | Prior to October 1, 2025 | yes | SERVICES PROVIDED: From July through September 2025, the Prevention Specialist worked with 31 students ages 12–17 who violated the school’s substance use policy, with four students reoffending during the quarter. The specialist conducted four one-on-one sessions with students needing additional guidance and hosted one support meeting with three students in attendance. The Hot Springs School District maintained two active Drug Free Youth Coalitions—each with 20 members at the Junior Academy and High School campuses—that met four times during the quarter with active elected officials. Additionally, Hot Springs School District students participated in the Arkansas Juvenile Officials Association Conference, where the Drug Free Youth Coalition President co-led a breakout session on asset mapping with the Prevention Specialist. Students also attended Prevention Day at Dickey-Stephens Baseball Park, where one of our members had the honor of throwing the first pitch.
On June 6, 2025, the Prevention Specialist attended the Safety First Curriculum Training, a widely recognized primary prevention education program featuring the Tobacco Prevention Toolkit and Cannabis Awareness and Prevention Toolkit. This annual milestone ensured the specialist stayed current with best practices and resources for effectively educating youth on substance use prevention.
On July 31, 2025, the Prevention Specialist assisted the Drug-Free Youth Coalition President in leading a breakout session on asset mapping and drug prevention at the Arkansas Juvenile Officers Association (AJOA) Summer Conference held at the Embassy in Hot Springs, AR. This milestone highlighted student leadership and active engagement in promoting drug prevention strategies among peers.
On August 2, 2025, the Prevention Specialist delivered a presentation to the Hot Springs High School Trojans offensive and defensive linemen about the dangers of substance use. This milestone emphasized personal accountability, teamwork, and the importance of staying drug-free to remain dependable both on and off the field.
On August 12, 2025, Prevention Specialist hosted a High School Drug Free Youth Coalition meeting on campus with 23 participants, including the school nurse, staff members, law enforcement, and key community stakeholders. This milestone demonstrated continued collaboration and community engagement in supporting youth prevention and promoting a drug-free school environment.
On August 20, 2025, Prevention Specialist hosted a High School Drug Free Youth Coalition meeting on campus with 14 participants, including the school nurse, staff members, law enforcement, and key community stakeholders. This milestone highlighted ongoing collaboration and engagement in supporting youth prevention and fostering a drug-free school environment.
On September 3, 2025, our Prevention Specialist completed specialized training with Stanford Medicine’s REACH Lab, earning CEUs in substance use prevention. This milestone demonstrates our commitment to professional development and maintaining a program guided by the latest evidence-based practices in prevention and early intervention.
On September 5, 2025, 25 students were recognized for their commitment to substance use prevention during Prevention Day at the Arkansas Travelers baseball game. A key milestone of the event was a Drug Free Youth Coalition member throwing the first pitch, highlighting student leadership and promoting public awareness of living a drug-free lifestyle.
On September 11, 2025, the Prevention Specialist delivered a presentation to the Junior Academy Health Class on the dangers of opioids and other drugs. This milestone provided students with vital prevention education and increased awareness about the risks associated with substance use.
On September 16, 2025, a Junior Academy student emailed the Prevention Specialist after attending a Drug Free Youth Coalition meeting, following a suggestion from a coalition member. This milestone highlights student engagement and the influence of peer encouragement in fostering participation in prevention activities. "I'm serious about being in your group because last year my sister died of a terrible death. She was murdered on Beard Street in hot springs. She got murdered because of drugs by our own family. i struggled with drugs after her death because i needed something to cope with eventually i woke up out of my depression state and stopped doing drugs and found god i feel like drug free prevention is a safe space for me to talk about what happened and i want to help others stop doing drugs or even prevent them before doing it i used to have friends that did drugs and i cut them off i found god and peace and the big drug raid that just happened not to long ago me and my mother but one of them food and drinks everyday trying to help him get a job we even bought him new clothes so he could get a job and get off the streets and weeks later he is in jail for a drug raid. I went through a lot of childhood trauma in my life and I used drugs to cope..... so I'm very serious about this position."
On September 16, 2025, our Prevention Specialist hosted a Junior Academy Drug Free Youth Coalition meeting on campus with 44 participants, including the school nurse, staff members, law enforcement, and key community stakeholders. This milestone demonstrated strong community collaboration and active engagement in promoting youth substance use prevention.
On September 19, 2025, our Prevention Specialist hosted a High School Drug Free Youth Coalition meeting on campus with 23 participants, including the school nurse, staff members, law enforcement, and key community stakeholders. This milestone highlighted continued collaboration and commitment to supporting youth prevention and fostering a drug-free school environment.
On September 22–23, 2025, our Prevention Specialist completed training with Prevention Training Services on Addressing Opioid Overdose and Understanding the Role in Prevention, earning CEUs. This milestone strengthened the program’s ability to respond to opioid-related risks and reinforced our commitment to evidence-based substance use prevention strategies.
On September 23–24, 2025, our Prevention Specialist updated a PowerPoint presentation with the latest information on opioids and Naloxone and delivered an awareness and prevention session to the high school Criminal Justice class. This milestone highlighted the program’s commitment to providing current, evidence-based education while equipping students with life-saving knowledge and skills to respond to opioid-related emergencies.
On September 25, 2025, the Prevention Specialist collaborated with the regional prevention provider to promote a prevention message at Hot Springs World Class High School during home football games. The message—“Students—make smart moves on and off the field! Stay drug free, make healthy choices, and remember—prevention saves lives!”—highlighted community partnership and reinforced positive, drug-free decision-making among students.
Submit Quarterly ARORP report | By October 1, 2025 | yes | Submitted before October 1, 2025
Quarter 4 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Provide update on prevention and recovery efforts | Prior to December 1, 2025 |  | SERVICES PROVIDED: From October through December 2025, the Prevention Specialist worked with 40 students ages 12–17 who violated the school’s substance use policy, with 10 students reoffending during the quarter. The specialist conducted 10 one-on-one sessions with students needing additional guidance and hosted 0 support meeting with 0 students in attendance. The Hot Springs School District maintained two active Drug Free Youth Coalitions—each with 20 members at the Junior Academy and High School campuses—that met 4 times during the quarter with active elected officials. Additionally, Hot Springs School District students participated in the Arkansas Drug Take Back event held in the Sam’s Club parking lot. Also the Prevention Specialist gave a Red Ribbon Week presentation at Oaklawn Middle School on the importance of choosing to live drug-free, in collaboration with the regional prevention provider from Harbor House, The Prevention Specialist took 24 Hot Springs School District students to the Stop Overdose Summit, where they learned about addiction risks, emerging drug trends, and engaged with Arkansas State Drug Director Tom Fisher, Attorney General Tim Griffin, and peers from across the state, and Emma Jones one of our own coalition members received the Outstanding Youth Award from the Prevention Professionals of Arkansas. The ceremony was held at the Waters Hotel in downtown Hot Springs, where Emma was celebrated alongside her family, previous award recipient Kaziah Olive, and Prevention Specialist Anthony Tidwell. Emma was nominated for this well-deserved honor, and her achievements continue to inspire her peers and the community. Arkansas Opioid Recovery Partnership Executives Kirk Lane and Tenesha Barnes were also present to congratulate and recognize Emma’s accomplishments.
On October 7, 2025, the Prevention Specialist hosted the Junior Academy Drug Free Youth Coalition meeting, where members prepared for Red Ribbon Week by reading aloud inspirational letters written by Ms. Bartlett’s JAG class to be included in gift bags for community members in recovery. This milestone was deeply emotional, as students and the school resource officer shared personal stories of overcoming challenges related to addiction, highlighting the power of hope, resilience, and peer support in fostering a caring, drug-free school community.
On October 24, 2025, Drug Free Youth Coalition members assembled care packages for adults in substance abuse recovery across Garland County. This milestone demonstrated youth compassion and community engagement while supporting individuals on their journey toward recovery.
On October 24, 2025, the Prevention Team collaborated with the Hot Springs School District to share Arkansas Drug Take Back information districtwide through social media. This milestone helped increase community participation in safely disposing of outdated and unwanted prescription medications, supporting local prevention efforts.
On October 25, 2025, Drug Free Youth Coalition members, alongside the Prevention Specialist, assisted with the Drug Take Back event held in the Sam’s Club parking lot. This milestone demonstrated student leadership and community involvement in promoting the safe disposal of unused medications and preventing prescription drug misuse.
On October 30, 2025, the Prevention Specialist took Drug Free Youth Coalition leaders to the Hot Springs Police Station, where they heard presentations from the Chief of Police, the Executive Director of a long-term recovery center, and a Peer Support Specialist. This milestone recognized the coalition’s efforts in assembling care packages and heartfelt messages for individuals in recovery, while also providing students with a meaningful tour and firsthand insight into community partnerships supporting substance misuse prevention.
On October 31, 2025, the Prevention Specialist gave a Red Ribbon Week presentation at Oaklawn Middle School on the importance of choosing to live drug-free, in collaboration with the regional prevention provider from Harbor House. This milestone promoted youth awareness and strengthened community partnerships in substance use prevention education.
On November 17, 2025, Emma Jones one of our own coalition members received the Outstanding Youth Award from the Prevention Professionals of Arkansas. The ceremony was held at the Waters Hotel in downtown Hot Springs, where Emma was celebrated alongside her family, previous award recipient Kaziah Olive, and Prevention Specialist Anthony Tidwell. Emma was nominated for this well-deserved honor, and her achievements continue to inspire her peers and the community. Arkansas Opioid Recovery Partnership Executives Kirk Lane and Tenesha Barnes were also present to congratulate and recognize Emma’s accomplishments.
On November 18, 2025, the Prevention Specialist took 24 Hot Springs School District students to the Stop Overdose Summit, where they learned about addiction risks, emerging drug trends, and engaged with Arkansas State Drug Director Tom Fisher, Attorney General Tim Griffin, and peers from across the state.
Complete Associate Preventionist Training and Peer Recovery Support Specialist Certification | Prior to December 1, 2025 | yes | The Prevention Specialist completed all required training and education for certification as a Certified Prevention Consultant and submitted all necessary documentation to the Prevention Professionals of Arkansas. This milestone reflects a high level of professional achievement and commitment to maintaining excellence in substance use prevention practices.
Attend annual ARORP evaluation meeting | Prior to December 1, 2025 | yes
Submit annual ARORP report | By December 1, 2025 | yes