## Sheet1
Annotated Milestones
Organization: Sevier County Detention Center
Project Title: : Sevier County RSAT/Community Outreach Program
Quarters: 1 st,2nd,3rd, and 4th Quarters
Milestones were sent to each participant after receiving a notice of award. Please copy and paste these milestones and due dates into the first and second columns. Please upload any supplemental materials through the quarterly reporting form.
Quarter 1 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Description (Please provide one to two sentence of description include details like who, what, where, when, and how).
Hire all staff | Prior to July 1, 2023 3 months after Funding | Completed | For our 1st Quarter we hire two Program Coordinators -Eleuterio Hernandez started at ARORP on 5/01/23 at a salary of $37,502.00 and Ana Mejia started at ARORP on 05/01/23 art a salary of $37,502.00
For our 1st Quarter we hire two full time Peer specialist and one part Peer specialist -WLynette Hanley started at ARORP on 5/01/23 at a salary of $37,502.00 and Galena Gallardo started at ARORP on 5/01/23 at a salary of $37,502.00 and our Part time Terry Smith started at ARORP on 5/01/23 at a salary of $18,751.00.
Update on services provided for incarcerated & outpatient participants | Prior to July 1, 2023 3 months after Funding | Completed | For our 1st Quarter we offer the following services-Drug testing, Community outreach, Metamorphosis counseling, Transitions counseling, Peer Recovery training, Educational classes, (Fatherhood classes, Adult education, Criminal thinking/mindset, Motherhood, Social poverty, Wages class, Career development, Substance abuse education, Narcotics anonymous, Celebrate recovery, Alcoholics anonymous, Anger management)
Update on staff training | Prior to July 1, 2023 3 months after Funding | Pending | For our 1st Quarter no training or conference was set up, with Peer conference, state/county meetings, county/state conferences, peer/recovery meetings, Harbor house trainings meetings, and speaking engagements
Develop Data tracking system | Prior to July 1, 2023 3 months after Funding | Completed
Submit first ARORP report | July 1, 2023 2023 3 months after funding | Completed
Quarter 2 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Update on services provided for incarcerated & outpatient participants | Prior to October 1, 2023 6 months after funding | Completed | For our 2nd Quarter we continue the same services as our 1st quarter report, and we added the TRADE Program to our participants inside the jail portion. The TRADE program consists jobs training for the Gas and Oil industry , This type of program was design to help our participants to get a job after the completion of the jail portion.
Update on staff training | Prior to October 1, 2023 6 months after funding | Completed | For our 2nd Quarter our Peer Specialist Mr. William Jeanes , Mrs. Lynette Hanley and Mrs. Galena Gallardo went to Peer conference on July 11 and 12 of 2023 to Little Rock, Arkansas. The Conference host was Caring for Communities. We will continue with state/county meetings, county/state conferences, peer/recovery meetings, Harbor house trainings meetings, and speaking engagements as they become available.
Submit Quarterly ARORP report | October 1, 2023 6 months after funding | Completed
Quarter 3 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Updated on services provided for | Prior to January 1, 2024 9 months after funding | Completed | For our 3rd Quarter we continue the same services as our 1st quarter and 2nd quarter. As we mention in our 2nd Quarter about Trade program to incarcerated participants. This program was extended to our Outreach Center where is available to the public.
incarcerated & outpatient participants
Update on staff training | January 1, 2024 9 months after funding | Completed | For our 3rd Quarter Our Peer Specialist Mr. William Jeanes , Mrs. Lynette Hanley and Mrs. Galena Gallardo went to Peer conference to Little Rock, Arkansas. The conference was hosted with the title Into the Flames Training. We will continue with state/county meetings, county/state conferences, peer/recovery meetings, Harbor house trainings meetings, and speaking engagements as they become available.
Submit Quarterly ARORP report | January 1, 2024 9 months after funding | Completed
Quarter 4 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Updated on services provided for | Prior to April 1, 2024 12 months after funding | Completed | For our 4th Quarter we continue the same services as previous quarters reporting.
incarcerated & outpatient participants
Update on staff training | Prior to April 1, 2024 12 months after funding | Completed | For our 4th Quarter our Peer Specialists Lynette Hanley went to Peer conference in Little Rock, Arkansas. Also, Lynette and Galena went to training Texarkana, Arkansas. We will continue with state/county meetings, county/state conferences, peer/recovery meetings, Harbor house trainings meetings, and speaking engagements as they become available.
Yearly ARORP Evaluation Meeting | Prior to April 1, 2024 12 months after funding | Completed
Submit Yearly ARORP report | April 1, 2024 12 months after funding | Completed
YEAR 2-3 PROJECT MILESTONS
1ST SET OF MILESTONES | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed ? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Continue services provided for | June 30 2024, Annually | Completed | For our 1st Quarter we continue the same services as previous, Drug Testing, Community Outreach, Peer Recovery Training, Educational Classes (Fatherhood Classes, Motherhood Classes, Adult Education, Criminal Thinking/Mindset Classes, Social Poverty, Wages Classes, Career Development, Substance Abuse Education, Narcotics Anonymous. Celebrate Recovery, Alcoholics Anonymous, and Anger Management)
incarcerated & outpatient participants
Submit first ARORP reports | July 15, 2024, Annually
2nd SET OF MILESTONES | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Continue services provided for | September 30, 2024, Annually | Completed | For our 2nd Quarter we continue the same services as previous, Drug Testing, Community Outreach, Peer Recovery Training, Educational Classes (Fatherhood Classes, Motherhood Classes, Adult Education, Criminal Thinking/Mindset Classes, Social Poverty, Wages Classes, Career Development, Substance Abuse Education, Narcotics Anonymous. Celebrate Recovery, Alcoholics Anonymous, and Anger Management)
incarcerated & outpatient participants
Submit Quarterly ARORP report | October 15, 2024, Annually | Completed
3rd SET OF MILESTONES | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Continue services provided for | December 31, 2024, Annually | Completed | For our 3rd Quarter we continue the same services as previous, Drug Testing, Community Outreach, Peer Recovery Training, Educational Classes (Fatherhood Classes, Motherhood Classes, Adult Education, Criminal Thinking/Mindset Classes, Social Poverty, Wages Classes, Career Development, Substance Abuse Education, Narcotics Anonymous. Celebrate Recovery, Alcoholics Anonymous, and Anger Management)
incarcerated & outpatient participants. |  |  | Also Minerva Martinez took Ana Mejia place as Program Coordinaror.
Submit Quarterly ARORP report | Januarty 15, 2025, Annually | Completed
4th SET OF MILESTONES | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Continue services provided for | March 31, 2025, Annually | Completed | For our 4th Quarter we continue the same services as previous, Drug Testing, Community Outreach, Peer Recovery Training, Educational Classes (Fatherhood Classes, Motherhood Classes, Adult Education, Criminal Thinking/Mindset Classes, Social Poverty, Wages Classes, Career Development, Substance Abuse Education, Narcotics Anonymous. Celebrate Recovery, Alcoholics Anonymous, and Anger Management)
incarcerated & outpatient participants.
Submit Quarterly ARORP report | April 15,2025, Annually | Completed
1ST SET OF MILESTONES | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed ? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Continue services provided for | June 30 2025, Annually | Completed | For our 1st Quarter we continue the same services as previous, Drug Testing, Community Outreach, Peer Recovery Training, Educational Classes (Fatherhood Classes, Motherhood Classes, Adult Education, Criminal Thinking/Mindset Classes, Social Poverty, Wages Classes, Career Development, Substance Abuse Education, Narcotics Anonymous. Celebrate Recovery, Alcoholics Anonymous, and Anger Management)
incarcerated & outpatient participants |  |  | Peer Lynett Hanley left in May of 2025, and William Don Jeans took a full-time Peer position.
Submit first ARORP reports | July 15, 2025, Annually |  | Minerva Martinez Program Coordinator left in June 2025.
2nd SET OF MILESTONES | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Continue services provided for | September 30, 2025, Annually | Completed | For our 2nd Quarter we continue the same services as previous, Drug Testing, Community Outreach, Peer Recovery Training, Educational Classes (Fatherhood Classes, Motherhood Classes, Adult Education, Criminal Thinking/Mindset Classes, Social Poverty, Wages Classes, Career Development, Substance Abuse Education, Narcotics Anonymous. Celebrate Recovery, Alcoholics Anonymous, and Anger Management)
incarcerated & outpatient participants |  |  | Jayme Barnes took William Don Jeans Part-Time Peer Position starting on July 2025
Submit Quarterly ARORP report | October 15, 2025, Annually | Completed | Also Aracely Ortiz took Minerva Martinez place as Program Coordinaror starting on July 2025.
3rd SET OF MILESTONES | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Continue services provided for | December 31, 2025, Annually | Completed | For our 3rd Quarter we continue the same services as previous, Drug Testing, Community Outreach, Peer Recovery Training, Educational Classes (Fatherhood Classes, Motherhood Classes, Adult Education, Criminal Thinking/Mindset Classes, Social Poverty, Wages Classes, Career Development, Substance Abuse Education, Narcotics Anonymous. Celebrate Recovery, Alcoholics Anonymous, and Anger Management)
incarcerated & outpatient participants.
Submit Quarterly ARORP report | Januarty 15, 2026, Annually | Completed
4 th SET OF MILESTONES | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Continue services provided for | March 31, 2026, Annually | Completed | For our 4th Quarter we continue the same services as previous, Drug Testing, Community Outreach, Peer Recovery Training, Educational Classes (Fatherhood Classes, Motherhood Classes, Adult Education, Criminal Thinking/Mindset Classes, Social Poverty, Wages Classes, Career Development, Substance Abuse Education, Narcotics Anonymous. Celebrate Recovery, Alcoholics Anonymous, and Anger Management)
incarcerated & outpatient participants.
Submit Quarterly ARORP report | April 15, 2026, Annually | Completed