## FY1 Budget
Organization: Pulaski County Sheriff's Office
Project Title: Pulaski Sheriff ORT ¦ ARORP24-296
Quarter: 4
You are responsible for keeping track of receipts for all purchases for your agency’s records. You will not submit receipts to ARORP until the end of the year.
Original Budget Line Item (Copy and paste your original budget line items from the budget that was approved by the ARORP Advisory Board.) | Original Amount Budgeted (Copy and paste the original amount budgeted from the budget that was approved by the ARORP Advisory Board.) | Description of Budget Line Item (Copy and paste the original description from the budget that was approved by the ARORP Advisory Board.) | Spent to Date (Money spent in this line item to date.) | Spend to Date Notes (Input the exact amount from each receipt or invoice. Include the date, vendor, items purchased, and unit price. For more than one receipt or invoice, create a new tab that is named after the line item. See example of "lawn equipment"). | Amount Left to Spend | Plan to Spend | Does this plan align with project milestones?
Investigator Salary | 50210.94 | Salary | 46348.56 | See Tab - Investigator Salary | 3862.38 | Unspent FY1 Funds May Be Returned | Yes
Peer Salary | 35360 | Salary | 31280 | See Tab - Peer Salary | 4080 | Unspent FY1 Funds May Be Returned | Yes
Investigator Health Insurance | 7200 | Fringe | 6588.06 | See Tab - Investigator Health Insurance | 611.94 | Unspent FY1 Funds May Be Returned | Yes
Peer Health Insurance | 7200 | Fringe | 0 | See Tab - Peer Health Insurance | 7200 | Unspent FY1 Funds May Be Returned | Yes
Investigator Life Insurance | 42 | Fringe | 20.9 | See Tab - Investigator Life Insurance | 21.1 | Unspent FY1 Funds May Be Returned | Yes
Peer Life Insurance | 42 | Fringe | 31.5 | See Tab - Peer Life Insurance | 10.5 | Unspent FY1 Funds May Be Returned | Yes
Peer Fringe | 9289.07 | Fringe | 8421.99 | See Tab - Peer Fringe | 867.08 | Unspent FY1 Funds May Be Returned | Yes
Investigator Fringe | 13190.41 | Fringe | 12507.14 | See Tab - Investigator Fringe | 683.27 | Unspent FY1 Funds May Be Returned | Yes
Ink Pens | 71.16 | General Office Supplies | 0 | See Tab - General Office Supplies | 71.16 | Unspent FY1 Funds May Be Returned | Yes
Notebooks | 55.56 | General Office Supplies | 0 | See Tab - General Office Supplies | 55.56 | Unspent FY1 Funds May Be Returned | Yes
Envelopes 9*12 | 31.99 | General Office Supplies | 0 | See Tab - General Office Supplies | 31.99 | Unspent FY1 Funds May Be Returned | Yes
Envelopes 6*9 | 16.29 | General Office Supplies | 0 | See Tab - General Office Supplies | 16.29 | Unspent FY1 Funds May Be Returned | Yes
Classification Folders | 181.96 | General Office Supplies | 0 | See Tab - General Office Supplies | 181.96 | Unspent FY1 Funds May Be Returned | Yes
Brochures | 143 | General Office Supplies | 0 | See Tab - General Office Supplies | 143 | Unspent FY1 Funds May Be Returned | Yes
Printer Ink | 688.17 | General Office Supplies | 0 | See Tab - General Office Supplies | 688.17 | Unspent FY1 Funds May Be Returned | Yes
Toughbook Computer 2 | 3531.42 | Equipment | 1759 | See Tab - Dell | 1772.42 | Unspent FY1 Funds May Be Returned | Yes
Docking Station | 460.57 | Equipment | 225 | See Tab - Dell | 235.57 | Unspent FY1 Funds May Be Returned | Yes
Computer Monitor 2 | 410.61 | Equipment | 0 | Not Applicable | 410.61 | Unspent FY1 Funds May Be Returned | Yes
Cell-Brite Premium | 93500 | Equipment | 88627 | See Tab - Carasoft (Cellebrite) | 4873 | Unspent FY1 Funds May Be Returned | Yes
Cell-Brite Guardian | 16800 | Equipment | 8712 | See Tab - Carasoft (Cellebrite) | 8088 | Unspent FY1 Funds May Be Returned | Yes
Tax | 7676.25 | Equipment | 498.51 | See Tab - Tax | 7177.74 | Unspent FY1 Funds May Be Returned | Yes
| 246101.4 | Spent to Date: | 205019.66 | Amount Left to Spend: | 41081.74

## FY2 Budget
Organization: Pulaski County Sheriff's Office
Project Title: Pulaski Sheriff ORT ¦ ARORP24-296
Quarter: 0
You are responsible for keeping track of receipts for all purchases for your agency’s records. You will not submit receipts to ARORP until the end of the year.
Original Budget Line Item (Copy and paste your original budget line items from the budget that was approved by the ARORP Advisory Board.) | Original Amount Budgeted (Copy and paste the original amount budgeted from the budget that was approved by the ARORP Advisory Board.) | Description of Budget Line Item (Copy and paste the original description from the budget that was approved by the ARORP Advisory Board.) | Spent to Date (Money spent in this line item to date.) | Spend to Date Notes (Input the exact amount from each receipt or invoice. Include the date, vendor, items purchased, and unit price. For more than one receipt or invoice, create a new tab that is named after the line item. See example of "lawn equipment"). | Amount Left to Spend | Plan to Spend | Does this plan align with project milestones?
Investigator Salary | 50210.94 | Salary | 0 |  | 50210.94
Peer Salary | 35360 | Salary | 0 |  | 35360
Investigator Health Insurance | 7200 | Fringe | 0 |  | 7200
Peer Health Insurance | 7200 | Fringe | 0 |  | 7200
Investigator Life Insurance | 42 | Fringe | 0 |  | 42
Peer Life Insurance | 42 | Fringe | 0 |  | 42
Peer Fringe | 9289.07 | Fringe | 0 |  | 9289.07
Investigator Fringe | 13190.41 | Fringe | 0 |  | 13190.41
Ink Pens | 71.16 | General Office Supplies | 0 |  | 71.16
Notebooks | 55.56 | General Office Supplies | 0 |  | 55.56
Envelopes 9*12 | 31.99 | General Office Supplies | 0 |  | 31.99
Envelopes 6*9 | 16.29 | General Office Supplies | 0 |  | 16.29
Classification Folders | 181.96 | General Office Supplies | 0 |  | 181.96
Brochures | 143 | General Office Supplies | 0 |  | 143
Printer Ink | 688.17 | General Office Supplies | 0 |  | 688.17
Toughbook Computer 2 | 0 | Equipment | 0 |  | 0
Docking Station | 0 | Equipment | 0 |  | 0
Computer Monitor 2 | 0 | Equipment | 0 |  | 0
Cell-Brite Premium | 0 | Equipment | 0 |  | 0
Cell-Brite Guardian | 0 | Equipment | 0 |  | 0
Tax | 0 | Equipment | 0 |  | 0
| 123722.55 | Spent to Date: | 0 | Amount Left to Spend: | 123722.55

## Investigator Salary
Date | Vendor | Items Purchased with Unit Price |  | Investigator Salary
|  | SALARIES, FULL TIME | ARORP Amount Total | ARORP Award Amount | Actual Amount on Pay Stub | Difference Paid by Pulaski County
11/07/2024 | Pulaski County Government | Payroll Cycle 23 (10/19/2024-11/01/2024) | #REF! | 1931.19 | 1969.46 | 38.27
11/21/2024 | Pulaski County Government | Payroll Cycle 24 (11/02/2024-11/15/2024) | #REF! | 1931.19 | 1969.46 | 38.27
12/05/2024 | Pulaski County Government | Payroll Cycle 25 (11/16/2024-11/29/2024) | #REF! | 1931.19 | 1969.46 | 38.27
12/19/2024 | Pulaski County Government | Payroll Cycle 26 (11/30/2024-12/13/2024) | #REF! | 1931.19 | 1969.46 | 38.27
01/02/2025 | Pulaski County Government | Payroll Cycle 1 (12/14/2024-12/27/2024) | #REF! | 1931.19 | 1969.46 | 38.27
01/16/2025 | Pulaski County Government | Payroll Cycle 2 (12/28/2024-01/10/2025) | #REF! | 1931.19 | 1969.46 | 38.27
01/30/2025 | Pulaski County Government | Payroll Cycle 3 (01/11/2025-01/24/2025) | #REF! | 1931.19 | 1969.46 | 38.27
02/13/2025 | Pulaski County Government | Payroll Cycle 4 (01/25/2025-02/07/2025) | #REF! | 1931.19 | 1969.46 | 38.27
02/27/2025 | Pulaski County Government | Payroll Cycle 5 (02/08/2025-02/21/2025) | #REF! | 1931.19 | 1969.46 | 38.27
03/13/2025 | Pulaski County Government | Payroll Cycle 6 (02/22/2025-03/07/2025) | #REF! | 1931.19 | 1969.46 | 38.27
03/27/2025 | Pulaski County Government | Payroll Cycle 7 (03/08/2025-03/21/2025) | #REF! | 1931.19 | 1969.46 | 38.27
04/10/2025 | Pulaski County Government | Payroll Cycle 8 (03/22/2025-04/04/2025) | 3291.19 | 1931.19 | 1969.46 | 38.27
04/24/2025 | Pulaski County Government | Payroll Cycle 9 (04/05/2025-04/18/2025) | 3291.19 | 1931.19 | 1969.46 | 38.27
05/08/2025 | Pulaski County Government | Payroll Cycle 10 (04/19/2025-05/02/2025) | 3291.19 | 1931.19 | 1969.46 | 38.27
05/22/2025 | Pulaski County Government | Payroll Cycle 11 (05/03/2025-05/16/2025) | 3291.19 | 1931.19 | 1969.46 | 38.27
06/05/2025 | Pulaski County Government | Payroll Cycle 12 (05/17/2025-05/30/2025) | 3291.19 | 1931.19 | 1969.46 | 38.27
06/18/2025 | Pulaski County Government | Payroll Cycle 13 (05/31/2025-06/13/2025) | 3291.19 | 1931.19 | 1969.46 | 38.27
07/02/2025 | Pulaski County Government | Payroll Cycle 14 (06/14/2025-06/27/2025) |  | 1931.19 | 1969.46 | 38.27
07/17/2025 | Pulaski County Government | Payroll Cycle 15 (06/28/2025-07/11/2025) |  | 1931.19 | 1969.46 | 38.27
07/31/2025 | Pulaski County Government | Payroll Cycle 16 (07/12/2025-07/25/2025) |  | 1931.19 | 1969.46 | 38.27
08/14/2025 | Pulaski County Government | Payroll Cycle 17 (07/26/2025-08/08/2025) |  | 1931.19 | 1969.46 | 38.27
08/28/2025 | Pulaski County Government | Payroll Cycle 18 (08/09/2025-08/22/2025) |  | 1931.19 | 1969.46 | 38.27
09/11/2025 | Pulaski County Government | Payroll Cycle 19 (08/23/2025-09/05/2025) |  | 1931.19 | 1969.46 | 38.27
09/25/2025 | Pulaski County Government | Payroll Cycle 20 (09/06/2025-09/19/2025) |  | 1931.19 | 1969.46 | 38.27
|  |  | #REF! | 46348.56 | 47267.04 | 918.48

## Peer Salary
Date | Vendor | Items Purchased with Unit Price |  | Peer Salary
|  | SALARIES, FULL TIME | ARORP Amount Total | ARORP Award Amount | Actual Amount on Pay Stub | Difference Paid by Pulaski County
11/21/2024 | Pulaski County Government | Payroll Cycle 24 (11/02/2024-11/15/2024) | #REF! | 1360 | 1365.07 | 5.07
12/05/2024 | Pulaski County Government | Payroll Cycle 25 (11/16/2024-11/29/2024) | #REF! | 1360 | 1365.07 | 5.07
12/19/2024 | Pulaski County Government | Payroll Cycle 26 (11/30/2024-12/13/2024) | #REF! | 1360 | 1365.07 | 5.07
01/02/2025 | Pulaski County Government | Payroll Cycle 1 (12/14/2024-12/27/2024) | #REF! | 1360 | 1365.07 | 5.07
01/16/2025 | Pulaski County Government | Payroll Cycle 2 (12/28/2024-01/10/2025) | #REF! | 1360 | 1365.07 | 5.07
01/30/2025 | Pulaski County Government | Payroll Cycle 3 (01/11/2025-01/24/2025) | #REF! | 1360 | 1365.07 | 5.07
02/13/2025 | Pulaski County Government | Payroll Cycle 4 (01/25/2025-02/07/2025) | #REF! | 1360 | 1365.07 | 5.07
02/27/2025 | Pulaski County Government | Payroll Cycle 5 (02/08/2025-02/21/2025) | #REF! | 1360 | 1365.07 | 5.07
03/13/2025 | Pulaski County Government | Payroll Cycle 6 (02/22/2025-03/07/2025) | #REF! | 1360 | 1365.07 | 5.07
03/27/2025 | Pulaski County Government | Payroll Cycle 7 (03/08/2025-03/21/2025) | #REF! | 1360 | 1365.07 | 5.07
04/10/2025 | Pulaski County Government | Payroll Cycle 8 (03/22/2025-04/04/2025) | 3291.19 | 1360 | 1365.07 | 5.07
04/24/2025 | Pulaski County Government | Payroll Cycle 9 (04/05/2025-04/18/2025) | 3291.19 | 1360 | 1365.07 | 5.07
05/08/2025 | Pulaski County Government | Payroll Cycle 10 (04/19/2025-05/02/2025) | 3291.19 | 1360 | 1365.07 | 5.07
05/22/2025 | Pulaski County Government | Payroll Cycle 11 (05/03/2025-05/16/2025) | 3291.19 | 1360 | 1365.07 | 5.07
06/05/2025 | Pulaski County Government | Payroll Cycle 12 (05/17/2025-05/30/2025) | 3291.19 | 1360 | 1365.07 | 5.07
06/18/2025 | Pulaski County Government | Payroll Cycle 13 (05/31/2025-06/13/2025) | 3291.19 | 1360 | 1365.07 | 5.07
07/02/2025 | Pulaski County Government | Payroll Cycle 14 (06/14/2025-06/27/2025) |  | 1360 | 1365.07 | 5.07
07/17/2025 | Pulaski County Government | Payroll Cycle 15 (06/28/2025-07/11/2025) |  | 1360 | 1365.07 | 5.07
07/31/2025 | Pulaski County Government | Payroll Cycle 16 (07/12/2025-07/25/2025) |  | 1360 | 1365.07 | 5.07
08/14/2025 | Pulaski County Government | Payroll Cycle 17 (07/26/2025-08/08/2025) |  | 1360 | 1365.07 | 5.07
08/28/2025 | Pulaski County Government | Payroll Cycle 18 (08/09/2025-08/22/2025) |  | 1360 | 1365.07 | 5.07
09/11/2025 | Pulaski County Government | Payroll Cycle 19 (08/23/2025-09/05/2025) |  | 1360 | 1365.07 | 5.07
09/25/2025 | Pulaski County Government | Payroll Cycle 20 (09/06/2025-09/19/2025) |  | 1360 | 1365.07 | 5.07
|  |  | #REF! | 31280 | 31396.61 | 116.61

## Investigator Health Insurance
Date | Vendor | Items Purchased with Unit Price |  | Investigator
|  | HEALTH INSURANCE MATCHING | ARORP Amount
11/07/2024 | Pulaski County Government | Payroll Cycle 23 (10/19/2024-11/01/2024) | 257.37 | 257.37
11/21/2024 | Pulaski County Government | Payroll Cycle 24 (11/02/2024-11/15/2024) | 257.37 | 257.37
12/05/2024 | Pulaski County Government | Payroll Cycle 25 (11/16/2024-11/29/2024) | 257.37 | 257.37
12/19/2024 | Pulaski County Government | Payroll Cycle 26 (11/30/2024-12/13/2024) | 257.37 | 257.37
01/02/2025 | Pulaski County Government | Payroll Cycle 1 (12/14/2024-12/27/2024) | 308.81 | 308.81
01/16/2025 | Pulaski County Government | Payroll Cycle 2 (12/28/2024-01/10/2025) | 308.81 | 308.81
02/13/2025 | Pulaski County Government | Payroll Cycle 4 (01/25/2025-02/07/2025) | 308.81 | 308.81
02/27/2025 | Pulaski County Government | Payroll Cycle 5 (02/08/2025-02/21/2025) | 308.81 | 308.81
03/13/2025 | Pulaski County Government | Payroll Cycle 6 (02/22/2025-03/07/2025) | 308.81 | 308.81
03/27/2025 | Pulaski County Government | Payroll Cycle 7 (03/08/2025-03/21/2025) | 308.81 | 308.81
04/10/2025 | Pulaski County Government | Payroll Cycle 8 (03/22/2025-04/04/2025) | 308.81 | 308.81
04/24/2025 | Pulaski County Government | Payroll Cycle 9 (04/05/2025-04/18/2025) | 308.81 | 308.81
05/08/2025 | Pulaski County Government | Payroll Cycle 10 (04/19/2025-05/02/2025) | 308.81 | 308.81
05/22/2025 | Pulaski County Government | Payroll Cycle 11 (05/03/2025-05/16/2025) | 308.81 | 308.81
06/05/2025 | Pulaski County Government | Payroll Cycle 12 (05/17/2025-05/30/2025) | 308.81 | 308.81
06/18/2025 | Pulaski County Government | Payroll Cycle 13 (05/31/2025-06/13/2025) | 308.81 | 308.81
07/02/2025 | Pulaski County Government | Payroll Cycle 14 (06/14/2025-06/27/2025) |  | 308.81
07/17/2025 | Pulaski County Government | Payroll Cycle 15 (06/28/2025-07/11/2025) |  | 308.81
08/14/2025 | Pulaski County Government | Payroll Cycle 17 (07/26/2025-08/08/2025) |  | 308.81
08/28/2025 | Pulaski County Government | Payroll Cycle 18 (08/09/2025-08/22/2025) |  | 308.81
09/11/2025 | Pulaski County Government | Payroll Cycle 19 (08/23/2025-09/05/2025) |  | 308.81
09/25/2025 | Pulaski County Government | Payroll Cycle 20 (09/06/2025-09/19/2025) | 308.81 | 308.81
6588.06

## Peer Health Insurance
Date | Vendor | Items Purchased with Unit Price |  | Peer*
|  | HEALTH INSURANCE MATCHING | ARORP Amount
11/07/2024 | Pulaski County Government | Payroll Cycle 23 (10/19/2024-11/01/2024) | 257.37 | 0
11/21/2024 | Pulaski County Government | Payroll Cycle 24 (11/02/2024-11/15/2024) | 257.37 | 0
12/05/2024 | Pulaski County Government | Payroll Cycle 25 (11/16/2024-11/29/2024) | 257.37 | 0
12/19/2024 | Pulaski County Government | Payroll Cycle 26 (11/30/2024-12/13/2024) | 257.37 | 0
01/02/2025 | Pulaski County Government | Payroll Cycle 1 (12/14/2024-12/27/2024) | 308.81 | 0
01/16/2025 | Pulaski County Government | Payroll Cycle 2 (12/28/2024-01/10/2025) | 308.81 | 0
02/13/2025 | Pulaski County Government | Payroll Cycle 4 (01/25/2025-02/07/2025) | 308.81 | 0
02/27/2025 | Pulaski County Government | Payroll Cycle 5 (02/08/2025-02/21/2025) | 308.81 | 0
03/13/2025 | Pulaski County Government | Payroll Cycle 6 (02/22/2025-03/07/2025) | 308.81 | 0
03/27/2025 | Pulaski County Government | Payroll Cycle 7 (03/08/2025-03/21/2025) | 308.81 | 0
04/10/2025 | Pulaski County Government | Payroll Cycle 8 (03/22/2025-04/04/2025) | 308.81 | 0
04/24/2025 | Pulaski County Government | Payroll Cycle 9 (04/05/2025-04/18/2025) | 308.81 | 0
05/08/2025 | Pulaski County Government | Payroll Cycle 10 (04/19/2025-05/02/2025) | 308.81 | 0
05/22/2025 | Pulaski County Government | Payroll Cycle 11 (05/03/2025-05/16/2025) | 308.81 | 0
06/05/2025 | Pulaski County Government | Payroll Cycle 12 (05/17/2025-05/30/2025) | 308.81 | 0
06/18/2025 | Pulaski County Government | Payroll Cycle 13 (05/31/2025-06/13/2025) | 308.81 | 0
07/02/2025 | Pulaski County Government | Payroll Cycle 14 (06/14/2025-06/27/2025) |  | 0
07/17/2025 | Pulaski County Government | Payroll Cycle 15 (06/28/2025-07/11/2025) |  | 0
08/14/2025 | Pulaski County Government | Payroll Cycle 17 (07/26/2025-08/08/2025) |  | 0
08/28/2025 | Pulaski County Government | Payroll Cycle 18 (08/09/2025-08/22/2025) |  | 0
09/11/2025 | Pulaski County Government | Payroll Cycle 19 (08/23/2025-09/05/2025) |  | 0
09/25/2025 | Pulaski County Government | Payroll Cycle 20 (09/06/2025-09/19/2025) | 308.81 | 0
0
*No funds spent. The Peer opted for health insurance outside of what was provided by Pulaski County.

## Investigator Life Insurance
Date | Vendor | Items Purchased with Unit Price |  | Investigator
|  | LIFE INSURANCE | ARORP Amount
11/07/2024 | Pulaski County Government | Payroll Cycle 23 (10/19/2024-11/01/2024) | 0.95 | 0.95
11/21/2024 | Pulaski County Government | Payroll Cycle 24 (11/02/2024-11/15/2024) | 0.95 | 0.95
12/05/2024 | Pulaski County Government | Payroll Cycle 25 (11/16/2024-11/29/2024) | 0.95 | 0.95
12/19/2024 | Pulaski County Government | Payroll Cycle 26 (11/30/2024-12/13/2024) | 0.95 | 0.95
01/02/2025 | Pulaski County Government | Payroll Cycle 1 (12/14/2024-12/27/2024) | 2.7 | 0.95
01/16/2025 | Pulaski County Government | Payroll Cycle 2 (12/28/2024-01/10/2025) | 2.7 | 0.95
02/13/2025 | Pulaski County Government | Payroll Cycle 4 (01/25/2025-02/07/2025) | 2.7 | 0.95
02/27/2025 | Pulaski County Government | Payroll Cycle 5 (02/08/2025-02/21/2025) | 2.7 | 0.95
03/13/2025 | Pulaski County Government | Payroll Cycle 6 (02/22/2025-03/07/2025) | 2.7 | 0.95
03/27/2025 | Pulaski County Government | Payroll Cycle 7 (03/08/2025-03/21/2025) | 2.7 | 0.95
04/10/2025 | Pulaski County Government | Payroll Cycle 8 (03/22/2025-04/04/2025) | 2.7 | 0.95
04/24/2025 | Pulaski County Government | Payroll Cycle 9 (04/05/2025-04/18/2025) | 2.7 | 0.95
05/08/2025 | Pulaski County Government | Payroll Cycle 10 (04/19/2025-05/02/2025) | 2.7 | 0.95
05/22/2025 | Pulaski County Government | Payroll Cycle 11 (05/03/2025-05/16/2025) | 2.7 | 0.95
06/05/2025 | Pulaski County Government | Payroll Cycle 12 (05/17/2025-05/30/2025) | 2.7 | 0.95
06/18/2025 | Pulaski County Government | Payroll Cycle 13 (05/31/2025-06/13/2025) | 2.7 | 0.95
07/02/2025 | Pulaski County Government | Payroll Cycle 14 (06/14/2025-06/27/2025) |  | 0.95
07/17/2025 | Pulaski County Government | Payroll Cycle 15 (06/28/2025-07/11/2025) |  | 0.95
08/14/2025 | Pulaski County Government | Payroll Cycle 17 (07/26/2025-08/08/2025) |  | 0.95
08/28/2025 | Pulaski County Government | Payroll Cycle 18 (08/09/2025-08/22/2025) |  | 0.95
09/11/2025 | Pulaski County Government | Payroll Cycle 19 (08/23/2025-09/05/2025) |  | 0.95
09/25/2025 | Pulaski County Government | Payroll Cycle 20 (09/06/2025-09/19/2025) | 2.7 | 0.95
20.9

## Peer Life Insurance
Date | Vendor | Items Purchased with Unit Price |  | Peer
|  | LIFE INSURANCE | ARORP Amount
11/07/2024 | Pulaski County Government | Payroll Cycle 23 (10/19/2024-11/01/2024) | 0.95 | 0
11/21/2024 | Pulaski County Government | Payroll Cycle 24 (11/02/2024-11/15/2024) | 0.95 | 0
12/05/2024 | Pulaski County Government | Payroll Cycle 25 (11/16/2024-11/29/2024) | 0.95 | 0
12/19/2024 | Pulaski County Government | Payroll Cycle 26 (11/30/2024-12/13/2024) | 0.95 | 0
01/02/2025 | Pulaski County Government | Payroll Cycle 1 (12/14/2024-12/27/2024) | 2.7 | 1.75
01/16/2025 | Pulaski County Government | Payroll Cycle 2 (12/28/2024-01/10/2025) | 2.7 | 1.75
02/13/2025 | Pulaski County Government | Payroll Cycle 4 (01/25/2025-02/07/2025) | 2.7 | 1.75
02/27/2025 | Pulaski County Government | Payroll Cycle 5 (02/08/2025-02/21/2025) | 2.7 | 1.75
03/13/2025 | Pulaski County Government | Payroll Cycle 6 (02/22/2025-03/07/2025) | 2.7 | 1.75
03/27/2025 | Pulaski County Government | Payroll Cycle 7 (03/08/2025-03/21/2025) | 2.7 | 1.75
04/10/2025 | Pulaski County Government | Payroll Cycle 8 (03/22/2025-04/04/2025) | 2.7 | 1.75
04/24/2025 | Pulaski County Government | Payroll Cycle 9 (04/05/2025-04/18/2025) | 2.7 | 1.75
05/08/2025 | Pulaski County Government | Payroll Cycle 10 (04/19/2025-05/02/2025) | 2.7 | 1.75
05/22/2025 | Pulaski County Government | Payroll Cycle 11 (05/03/2025-05/16/2025) | 2.7 | 1.75
06/05/2025 | Pulaski County Government | Payroll Cycle 12 (05/17/2025-05/30/2025) | 2.7 | 1.75
06/18/2025 | Pulaski County Government | Payroll Cycle 13 (05/31/2025-06/13/2025) | 2.7 | 1.75
07/02/2025 | Pulaski County Government | Payroll Cycle 14 (06/14/2025-06/27/2025) |  | 1.75
07/17/2025 | Pulaski County Government | Payroll Cycle 15 (06/28/2025-07/11/2025) |  | 1.75
08/14/2025 | Pulaski County Government | Payroll Cycle 17 (07/26/2025-08/08/2025) |  | 1.75
08/28/2025 | Pulaski County Government | Payroll Cycle 18 (08/09/2025-08/22/2025) |  | 1.75
09/11/2025 | Pulaski County Government | Payroll Cycle 19 (08/23/2025-09/05/2025) |  | 1.75
09/25/2025 | Pulaski County Government | Payroll Cycle 20 (09/06/2025-09/19/2025) | 2.7 | 1.75
31.5

## Peer Fringe
Date | Vendor | Items Purchased with Unit Price | Peer
SOCIAL SECURITY MATCHING (FICA)
11/21/2024 | Pulaski County Government | Payroll Cycle 24 (11/02/2024-11/15/2024) | 104.42
12/05/2024 | Pulaski County Government | Payroll Cycle 25 (11/16/2024-11/29/2024) | 104.42
12/19/2024 | Pulaski County Government | Payroll Cycle 26 (11/30/2024-12/13/2024) | 104.42
01/02/2025 | Pulaski County Government | Payroll Cycle 1 (12/14/2024-12/27/2024) | 104.42
01/16/2025 | Pulaski County Government | Payroll Cycle 2 (12/28/2024-01/10/2025) | 104.42
01/30/2025 | Pulaski County Government | Payroll Cycle 3 (01/11/2025-01/24/2025) | 104.42
02/13/2025 | Pulaski County Government | Payroll Cycle 4 (01/25/2025-02/07/2025) | 102.46
02/27/2025 | Pulaski County Government | Payroll Cycle 5 (02/08/2025-02/21/2025) | 102.46
03/13/2025 | Pulaski County Government | Payroll Cycle 6 (02/22/2025-03/07/2025) | 102.46
03/27/2025 | Pulaski County Government | Payroll Cycle 7 (03/08/2025-03/21/2025) | 102.46
04/10/2025 | Pulaski County Government | Payroll Cycle 8 (03/22/2025-04/04/2025) | 102.46
04/24/2025 | Pulaski County Government | Payroll Cycle 9 (04/05/2025-04/18/2025) | 102.46
05/08/2025 | Pulaski County Government | Payroll Cycle 10 (04/19/2025-05/02/2025) | 102.4
05/22/2025 | Pulaski County Government | Payroll Cycle 11 (05/03/2025-05/16/2025) | 102.4
06/05/2025 | Pulaski County Government | Payroll Cycle 12 (05/17/2025-05/30/2025) | 102.4
06/18/2025 | Pulaski County Government | Payroll Cycle 13 (05/31/2025-06/13/2025) | 102.4
07/02/2025 | Pulaski County Government | Payroll Cycle 14 (06/14/2025-06/27/2025) | 102.4
07/17/2025 | Pulaski County Government | Payroll Cycle 15 (06/28/2025-07/11/2025) | 102.4
07/31/2025 | Pulaski County Government | Payroll Cycle 16 (07/12/2025-07/25/2025) | 104.42
08/14/2025 | Pulaski County Government | Payroll Cycle 17 (07/26/2025-08/08/2025) | 102.4
08/28/2025 | Pulaski County Government | Payroll Cycle 18 (08/09/2025-08/22/2025) | 102.4
09/11/2025 | Pulaski County Government | Payroll Cycle 19 (08/23/2025-09/05/2025) | 102.4
09/25/2025 | Pulaski County Government | Payroll Cycle 20 (09/06/2025-09/19/2025) | 102.4
2369.7
RETIREMENT MATCHING
11/21/2024 | Pulaski County Government | Payroll Cycle 24 (11/02/2024-11/15/2024) | 209.13
12/05/2024 | Pulaski County Government | Payroll Cycle 25 (11/16/2024-11/29/2024) | 209.13
12/19/2024 | Pulaski County Government | Payroll Cycle 26 (11/30/2024-12/13/2024) | 209.13
01/02/2025 | Pulaski County Government | Payroll Cycle 1 (12/14/2024-12/27/2024) | 209.13
01/16/2025 | Pulaski County Government | Payroll Cycle 2 (12/28/2024-01/10/2025) | 209.13
01/30/2025 | Pulaski County Government | Payroll Cycle 3 (01/11/2025-01/24/2025) | 209.13
02/13/2025 | Pulaski County Government | Payroll Cycle 4 (01/25/2025-02/07/2025) | 209.13
02/27/2025 | Pulaski County Government | Payroll Cycle 5 (02/08/2025-02/21/2025) | 209.13
03/13/2025 | Pulaski County Government | Payroll Cycle 6 (02/22/2025-03/07/2025) | 209.13
03/27/2025 | Pulaski County Government | Payroll Cycle 7 (03/08/2025-03/21/2025) | 209.13
04/10/2025 | Pulaski County Government | Payroll Cycle 8 (03/22/2025-04/04/2025) | 209.13
04/24/2025 | Pulaski County Government | Payroll Cycle 9 (04/05/2025-04/18/2025) | 209.13
05/08/2025 | Pulaski County Government | Payroll Cycle 10 (04/19/2025-05/02/2025) | 209.13
05/22/2025 | Pulaski County Government | Payroll Cycle 11 (05/03/2025-05/16/2025) | 209.13
06/05/2025 | Pulaski County Government | Payroll Cycle 12 (05/17/2025-05/30/2025) | 209.13
06/18/2025 | Pulaski County Government | Payroll Cycle 13 (05/31/2025-06/13/2025) | 209.13
07/02/2025 | Pulaski County Government | Payroll Cycle 14 (06/14/2025-06/27/2025) | 209.13
07/17/2025 | Pulaski County Government | Payroll Cycle 15 (06/28/2025-07/11/2025) | 209.13
07/31/2025 | Pulaski County Government | Payroll Cycle 16 (07/12/2025-07/25/2025) | 209.13
08/14/2025 | Pulaski County Government | Payroll Cycle 17 (07/26/2025-08/08/2025) | 209.13
08/28/2025 | Pulaski County Government | Payroll Cycle 18 (08/09/2025-08/22/2025) | 209.13
09/11/2025 | Pulaski County Government | Payroll Cycle 19 (08/23/2025-09/05/2025) | 209.13
09/25/2025 | Pulaski County Government | Payroll Cycle 20 (09/06/2025-09/19/2025) | 209.13
4809.99
WORKMAN'S COMP
01/10/2025 | Pulaski County Government | CERTIFICATE 8852/2025; 2025 ESTIMATED PREMIUM | 865.92
UNEMPLOYMENT COMPENSATION
2025-06-20 | Pulaski County Government | UNEMPLOYMENT COMPENSATION | 376.38
Total
8421.99

## Investigator Fringe
Date | Vendor | Items Purchased with Unit Price | Investigator
SOCIAL SECURITY MATCHING (FICA)
11/07/2024 | Pulaski County Government | Payroll Cycle 23 (10/19/2024-11/01/2024) | 144.41
11/21/2024 | Pulaski County Government | Payroll Cycle 24 (11/02/2024-11/15/2024) | 144.41
12/05/2024 | Pulaski County Government | Payroll Cycle 25 (11/16/2024-11/29/2024) | 144.41
12/19/2024 | Pulaski County Government | Payroll Cycle 26 (11/30/2024-12/13/2024) | 144.41
01/02/2025 | Pulaski County Government | Payroll Cycle 1 (12/14/2024-12/27/2024) | 144.41
01/16/2025 | Pulaski County Government | Payroll Cycle 2 (12/28/2024-01/10/2025) | 144.41
01/30/2025 | Pulaski County Government | Payroll Cycle 3 (01/11/2025-01/24/2025) | 150.67
02/13/2025 | Pulaski County Government | Payroll Cycle 4 (01/25/2025-02/07/2025) | 144.41
02/27/2025 | Pulaski County Government | Payroll Cycle 5 (02/08/2025-02/21/2025) | 144.41
03/13/2025 | Pulaski County Government | Payroll Cycle 6 (02/22/2025-03/07/2025) | 144.41
03/27/2025 | Pulaski County Government | Payroll Cycle 7 (03/08/2025-03/21/2025) | 144.41
04/10/2025 | Pulaski County Government | Payroll Cycle 8 (03/22/2025-04/04/2025) | 144.41
04/24/2025 | Pulaski County Government | Payroll Cycle 9 (04/05/2025-04/18/2025) | 144.41
05/08/2025 | Pulaski County Government | Payroll Cycle 10 (04/19/2025-05/02/2025) | 144.39
05/22/2025 | Pulaski County Government | Payroll Cycle 11 (05/03/2025-05/16/2025) | 144.39
06/05/2025 | Pulaski County Government | Payroll Cycle 12 (05/17/2025-05/30/2025) | 144.39
06/18/2025 | Pulaski County Government | Payroll Cycle 13 (05/31/2025-06/13/2025) | 144.39
07/02/2025 | Pulaski County Government | Payroll Cycle 14 (06/14/2025-06/27/2025) | 144.39
07/17/2025 | Pulaski County Government | Payroll Cycle 15 (06/28/2025-07/11/2025) | 144.39
07/31/2025 | Pulaski County Government | Payroll Cycle 16 (07/12/2025-07/25/2025) | 150.67
08/14/2025 | Pulaski County Government | Payroll Cycle 17 (07/26/2025-08/08/2025) | 144.39
08/28/2025 | Pulaski County Government | Payroll Cycle 18 (08/09/2025-08/22/2025) | 144.39
09/11/2025 | Pulaski County Government | Payroll Cycle 19 (08/23/2025-09/05/2025) | 144.39
09/25/2025 | Pulaski County Government | Payroll Cycle 20 (09/06/2025-09/19/2025) | 144.39
3478.16
RETIREMENT MATCHING
11/07/2024 | Pulaski County Government | Payroll Cycle 23 (10/19/2024-11/01/2024) | 301.72
11/21/2024 | Pulaski County Government | Payroll Cycle 24 (11/02/2024-11/15/2024) | 301.72
12/05/2024 | Pulaski County Government | Payroll Cycle 25 (11/16/2024-11/29/2024) | 301.72
12/19/2024 | Pulaski County Government | Payroll Cycle 26 (11/30/2024-12/13/2024) | 301.72
01/02/2025 | Pulaski County Government | Payroll Cycle 1 (12/14/2024-12/27/2024) | 301.72
01/16/2025 | Pulaski County Government | Payroll Cycle 2 (12/28/2024-01/10/2025) | 301.72
01/30/2025 | Pulaski County Government | Payroll Cycle 3 (01/11/2025-01/24/2025) | 301.72
02/13/2025 | Pulaski County Government | Payroll Cycle 4 (01/25/2025-02/07/2025) | 301.72
02/27/2025 | Pulaski County Government | Payroll Cycle 5 (02/08/2025-02/21/2025) | 301.72
03/13/2025 | Pulaski County Government | Payroll Cycle 6 (02/22/2025-03/07/2025) | 301.72
03/27/2025 | Pulaski County Government | Payroll Cycle 7 (03/08/2025-03/21/2025) | 301.72
04/10/2025 | Pulaski County Government | Payroll Cycle 8 (03/22/2025-04/04/2025) | 301.72
04/24/2025 | Pulaski County Government | Payroll Cycle 9 (04/05/2025-04/18/2025) | 301.72
05/08/2025 | Pulaski County Government | Payroll Cycle 10 (04/19/2025-05/02/2025) | 301.72
05/22/2025 | Pulaski County Government | Payroll Cycle 11 (05/03/2025-05/16/2025) | 301.72
06/05/2025 | Pulaski County Government | Payroll Cycle 12 (05/17/2025-05/30/2025) | 301.72
06/18/2025 | Pulaski County Government | Payroll Cycle 13 (05/31/2025-06/13/2025) | 301.72
07/02/2025 | Pulaski County Government | Payroll Cycle 14 (06/14/2025-06/27/2025) | 301.72
07/17/2025 | Pulaski County Government | Payroll Cycle 15 (06/28/2025-07/11/2025) | 301.72
07/31/2025 | Pulaski County Government | Payroll Cycle 16 (07/12/2025-07/25/2025) | 301.72
08/14/2025 | Pulaski County Government | Payroll Cycle 17 (07/26/2025-08/08/2025) | 301.72
08/28/2025 | Pulaski County Government | Payroll Cycle 18 (08/09/2025-08/22/2025) | 301.72
09/11/2025 | Pulaski County Government | Payroll Cycle 19 (08/23/2025-09/05/2025) | 301.72
09/25/2025 | Pulaski County Government | Payroll Cycle 20 (09/06/2025-09/19/2025) | 301.72
7241.28
WORKMAN'S COMP
01/10/2025 | Pulaski County Government | CERTIFICATE 8852/2025; 2025 ESTIMATED PREMIUM | 1246.08
UNEMPLOYMENT COMPENSATION
2025-06-20 | Pulaski County Government | UNEMPLOYMENT COMPENSATION | 541.62
Total
12507.14

## General Office Supplies
Total Cost per Receipt | Date | Vendor | Items Purchased with Unit Price*
- | N/A | N/A | N/A
*No funds spent under this line item.

## Carasoft (Cellebrite)
Total Cost per Receipt | Date | Vendor | Items Purchased with Unit Price | Invoice # IN2063592
Cell-Brite Premium
9108 | 09/19/2025 | Carasoft | Inseyets Pro UFED Subscription - 1 Year Term, Includes B-CNR-05-003 Upgrade to Inseyets, Online Pro S-UFD-04-059 Smart Translator 3 languag es translation Promotio POP DATES: 9/1/2025 8/31/2026
8316 | 09/19/2025 | Carasoft | Inseyets Pro PA Subscription - 1 Year TermPOP DATES: 9/1/2025 8/31/2026
3742.2 | 09/19/2025 | Carasoft | InsEYEts Kit
62439.3 | 09/19/2025 | Carasoft | Inseyets Online Limited Unlocks subscription - 26 unlocks -1 Year Term POP DATES: 9/1/2025 8/31/2026
1980 | 09/19/2025 | Carasoft | In-Person Virtual CCO - Cellebrite Certified Operator Inseyets 2 days
2821.5 | 09/19/2025 | Carasoft | In-Person Virtual CCPA - Cellebrite Certified Physical Analyst Inseyets 3 days
220 | 09/19/2025 | Carasoft | Shipping Charges
88627
Cell-Brite Gaurdain
8712 | 09/19/2025 | Carasoft | Guardian Core User Subscription - 1 Year TermPOP DATES: 9/1/2025 8/31/2026
(See Tax Tab for Taxes)

## Dell
Total Cost per Receipt | Date | Vendor | Items Purchased with Unit Price | Invoice # 10832730302
Toughbook Computer
1730 | 2025-09-19 | Dell | Dell Pro Rugged RB14250 XCTO
29 | 2025-09-19 | Dell | Dell USB Slim DVD +/1 RW Drive-DW316 1YR Ltd HW Warranty-Snp
1759
Docking Station
225 | 2025-09-19 | Dell | Dell Pro Thunderbolt 4 Smart Dock SD25TB4
(See Tax Tab for Taxes)

## Tax
Total Cost per Receipt | Date | Vendor | Items Purchased with Unit Price
341.74 | 09/19/2025 | Carasoft | Tax (Invoice # IN2063592)
156.77 | 2025-09-19 | Dell | Tax (Invoice # 10832730302)
Total Cost
498.51

## Annotated Milestones
Annotated Milestones
Organization: Pulaski County Sheriff's Office
Project Title: Pulaski County ORT ARORP24-296
Quarter: 4
Milestones were sent to each participant after receiving a notice of award. Please copy and paste these milestones and due dates into the first and second columns. Please upload any supplemental materials through the quarterly reporting form.
Quarter 1 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Description (Please provide one to two sentence of description include details like who, what, where, when, and how).
Hire Law Enforcement Investigator | 2024-12-31 | Yes | On 10/05/2024, a PCSO Deputy was transferred to the ORT Investigator position.
Hire Peer Support Specialist(s) | 2024-12-31 | Yes | Interviews began in October. On 11/4/2024, the ORT Peer Support position was filled.
Develop Recovery Support Program | 2024-12-31 | Yes | In November of 2024, ORT Peer Support established a program of outreach and assistance. They facilitated treatment options for recovery and provided on going support to overdose victims and families.
Develop Education Materials | 2024-12-31 | Yes | In November of 2024, ORT created a variety of pamphlet and educational materials. These materials described the purpose of the ORT and provided multiple points-of-contact for those seeking help.
Quarter 2 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Continue Recovery Support Program | 2025-03-31 | Yes | The Peer Support continued a program of outreach and assistance. They facilitated treatment options and provided ongoing support to overdose victims and families. Examples are outlined in the Quarter 2 report.
Quarter 3 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Continue Recovery Support Program | 2025-06-30 | Yes | The Peer Support continued a program of outreach and assistance. They facilitated treatment options and provided ongoing support to overdose victims and families. Examples are outlined in the Quarter 3 report.
Quarter 4 Milestones (Copy and paste the milestones provided by ARORP into this column) | Due Date (Copy and paste the due date listed on the milestones provided by ARORP) | Completed? | Updates/Notes (Please provide one to two sentence of description include details like who, what, where, when, and how).
Continue Recovery Support Program | 2025-09-30 | Yes | The Peer Support continued a program of outreach and assistance. They facilitated treatment options and provided ongoing support to overdose victims and families. Examples are outlined in the Quarter 4 report.